## Sheet1
kontrak | production | week | date | plan produksi | actual produksi | hm | km | cost_ooc | cost_actual
Kontrak BDM | Hauling Quarry;Quary Mined | w18 | 2024-05-31 | 0 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w18 | 2024-06-01 | 688.704 | 73.9 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w18 | 2024-06-02 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w18 | 2024-06-03 | 688.704 | 1341.2 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w18 | 2024-06-04 | 688.704 | 182.2 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w18 | 2024-06-05 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w18 | 2024-06-06 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w19 | 2024-06-07 | 280.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w19 | 2024-06-08 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w19 | 2024-06-09 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w19 | 2024-06-10 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w19 | 2024-06-11 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w19 | 2024-06-12 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w19 | 2024-06-13 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w20 | 2024-06-14 | 280.704 | 1312.6 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w20 | 2024-06-15 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w20 | 2024-06-16 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w20 | 2024-06-17 | 0 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w20 | 2024-06-18 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w20 | 2024-06-19 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w20 | 2024-06-20 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w21 | 2024-06-21 | 280.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w21 | 2024-06-22 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w21 | 2024-06-23 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w21 | 2024-06-24 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w21 | 2024-06-25 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w21 | 2024-06-26 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w21 | 2024-06-27 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w22 | 2024-06-28 | 280.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w22 | 2024-06-29 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Hauling Quarry;Quary Mined | w22 | 2024-06-30 | 688.704 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Ore Getting;Ore Hauling | w18 | 2024-05-31 | 0 | 0 | 420 | 1175 | 5594619.1367 | 99747795.0128
Kontrak BDM | Ore Getting;Ore Hauling | w18 | 2024-06-01 | 4785.48 | 0 | 102 | 0 | 3196925.221 | 18497387.1606
Kontrak BDM | Ore Getting;Ore Hauling | w18 | 2024-06-02 | 4785.48 | 4999.01 | 375.4 | 1675 | 3596540.8736 | 134963183.9121
Kontrak BDM | Ore Getting;Ore Hauling | w18 | 2024-06-03 | 4785.48 | 3982.54 | 402.2 | 1725 | 3196925.221 | 170283026.1561
Kontrak BDM | Ore Getting;Ore Hauling | w18 | 2024-06-04 | 4785.48 | 4289.67 | 354.6 | 1700 | 3196925.221 | 117030196.8108
Kontrak BDM | Ore Getting;Ore Hauling | w18 | 2024-06-05 | 4785.48 | 4488.22 | 386.2 | 1300 | 37647441.1423 | 162913161.3948
Kontrak BDM | Ore Getting;Ore Hauling | w18 | 2024-06-06 | 4785.48 | 5062.11 | 443.8 | 1825 | 3996156.5262 | 157699634.8181
Kontrak BDM | Ore Getting;Ore Hauling | w19 | 2024-06-07 | 1950.48 | 4398.62 | 416.6 | 1975 | 6176052.4013 | 153819298.9217
Kontrak BDM | Ore Getting;Ore Hauling | w19 | 2024-06-08 | 4785.48 | 4089.32 | 436.8 | 2050 | 24632248.7478 | 143240622.2983
Kontrak BDM | Ore Getting;Ore Hauling | w19 | 2024-06-09 | 4785.48 | 4230.24 | 379.4 | 1525 | 24232633.0952 | 146480310.7303
Kontrak BDM | Ore Getting;Ore Hauling | w19 | 2024-06-10 | 4785.48 | 4808.61 | 400.6 | 2000 | 3596540.8736 | 169612911.6578
Kontrak BDM | Ore Getting;Ore Hauling | w19 | 2024-06-11 | 4785.48 | 3340.81 | 462.8 | 1825 | 24232633.0952 | 180897668.8273
Kontrak BDM | Ore Getting;Ore Hauling | w19 | 2024-06-12 | 4785.48 | 4493.4 | 379 | 1800 | 3996156.5262 | 167670478.585
Kontrak BDM | Ore Getting;Ore Hauling | w19 | 2024-06-13 | 4785.48 | 2389.78 | 464.4 | 2025 | 27393577.8875 | 195588116.3556
Kontrak BDM | Ore Getting;Ore Hauling | w20 | 2024-06-14 | 1950.48 | 2842.69 | 652.2 | 1800 | 3996156.5262 | 213726728.8675
Kontrak BDM | Ore Getting;Ore Hauling | w20 | 2024-06-15 | 4785.48 | 3093.97 | 423 | 1725 | 3196925.221 | 154208858.4065
Kontrak BDM | Ore Getting;Ore Hauling | w20 | 2024-06-16 | 4785.48 | 2156.99 | 295.6 | 1025 | 2397693.9157 | 131951129.2812
Kontrak BDM | Ore Getting;Ore Hauling | w20 | 2024-06-17 | 0 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Ore Getting;Ore Hauling | w20 | 2024-06-18 | 4785.48 | 2233.61 | 410.6 | 1775 | 1598462.6105 | 156536039.2741
Kontrak BDM | Ore Getting;Ore Hauling | w20 | 2024-06-19 | 4785.48 | 2914.58 | 433 | 1925 | 0 | 170565925.4813
Kontrak BDM | Ore Getting;Ore Hauling | w20 | 2024-06-20 | 4785.48 | 2477.1 | 498 | 2300 | 23215603.7493 | 207803190.949
Kontrak BDM | Ore Getting;Ore Hauling | w21 | 2024-06-21 | 1950.48 | 0 | 432.6 | 1825 | 23215603.7493 | 184667044.9258
Kontrak BDM | Ore Getting;Ore Hauling | w21 | 2024-06-22 | 4785.48 | 0 | 442 | 2025 | 0 | 146410911.8573
Kontrak BDM | Ore Getting;Ore Hauling | w21 | 2024-06-23 | 4785.48 | 0 | 372 | 1500 | 0 | 167725187.0696
Kontrak BDM | Ore Getting;Ore Hauling | w21 | 2024-06-24 | 4785.48 | 0 | 397.8 | 1625 | 0 | 150853524.101
Kontrak BDM | Ore Getting;Ore Hauling | w21 | 2024-06-25 | 4785.48 | 0 | 427.4 | 1700 | 0 | 200755047.4443
Kontrak BDM | Ore Getting;Ore Hauling | w21 | 2024-06-26 | 4785.48 | 0 | 392.6 | 1175 | 7738534.5831 | 143363501.527
Kontrak BDM | Ore Getting;Ore Hauling | w21 | 2024-06-27 | 4785.48 | 0 | 420 | 1525 | 20636092.2216 | 193566782.9933
Kontrak BDM | Ore Getting;Ore Hauling | w22 | 2024-06-28 | 1950.48 | 0 | 397 | 1550 | 5159023.0554 | 136955209.2384
Kontrak BDM | Ore Getting;Ore Hauling | w22 | 2024-06-29 | 4785.48 | 0 | 413.4 | 2050 | 0 | 150547825.3088
Kontrak BDM | Ore Getting;Ore Hauling | w22 | 2024-06-30 | 4785.48 | 0 | 361.6 | 1500 | 0 | 137698504.3382
Kontrak BDM | Stripping Overburden | w18 | 2024-05-31 | 0 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Stripping Overburden | w18 | 2024-06-01 | 3030.2976 | 3479.3 | 45 | 0 | 15541976.9639 | 3778766.18
Kontrak BDM | Stripping Overburden | w18 | 2024-06-02 | 3030.2976 | 4946.7 | 94 | 0 | 18650372.3567 | 5422244.4445
Kontrak BDM | Stripping Overburden | w18 | 2024-06-03 | 3030.2976 | 1806.5 | 105 | 0 | 47865990.9033 | 45507149.9988
Kontrak BDM | Stripping Overburden | w18 | 2024-06-04 | 3030.2976 | 1306.3 | 189 | 0 | 55809668.0182 | 39074285.884
Kontrak BDM | Stripping Overburden | w18 | 2024-06-05 | 3030.2976 | 4020.9 | 30 | 0 | 10361317.9759 | 1626000
Kontrak BDM | Stripping Overburden | w18 | 2024-06-06 | 3030.2976 | 3507 | 167 | 0 | 44412218.2446 | 34559033.3326
Kontrak BDM | Stripping Overburden | w19 | 2024-06-07 | 1235.0976 | 3021.5 | 173 | 0 | 41274690.2499 | 45199927.7767
Kontrak BDM | Stripping Overburden | w19 | 2024-06-08 | 3030.2976 | 3703.3 | 158 | 0 | 59292573.2788 | 27597294.2006
Kontrak BDM | Stripping Overburden | w19 | 2024-06-09 | 3030.2976 | 5566.8 | 20 | 0 | 6907545.3173 | 1314350
Kontrak BDM | Stripping Overburden | w19 | 2024-06-10 | 3030.2976 | 2147.2 | 70 | 0 | 10361317.9759 | 3809794.4445
Kontrak BDM | Stripping Overburden | w19 | 2024-06-11 | 3030.2976 | 2390.1 | 163 | 0 | 43721463.7129 | 143127787.9147
Kontrak BDM | Stripping Overburden | w19 | 2024-06-12 | 3030.2976 | 3208.3 | 145 | 0 | 57582748.6819 | 32358321.2481
Kontrak BDM | Stripping Overburden | w19 | 2024-06-13 | 3030.2976 | 1062.2 | 129 | 0 | 54428158.9547 | 21380360.624
Kontrak BDM | Stripping Overburden | w20 | 2024-06-14 | 1235.0976 | 5618.2 | 168 | 0 | 31180916.7967 | 24439945.6886
Kontrak BDM | Stripping Overburden | w20 | 2024-06-15 | 3030.2976 | 1244.3 | 174 | 0 | 32907803.1261 | 22852465.6927
Kontrak BDM | Stripping Overburden | w20 | 2024-06-16 | 3030.2976 | 1767.6 | 118 | 0 | 16372966.2297 | 28786977.2907
Kontrak BDM | Stripping Overburden | w20 | 2024-06-17 | 0 | 0 | 0 | 0 | 0 | 0
Kontrak BDM | Stripping Overburden | w20 | 2024-06-18 | 3030.2976 | 3725.1 | 130 | 0 | 27565273.4715 | 28791784.0903
Kontrak BDM | Stripping Overburden | w20 | 2024-06-19 | 3030.2976 | 976.5 | 229 | 0 | 57960985.8082 | 51200333.3322
Kontrak BDM | Stripping Overburden | w20 | 2024-06-20 | 3030.2976 | 1476.7 | 172 | 0 | 23636300.8175 | 50767945.1167
Kontrak BDM | Stripping Overburden | w21 | 2024-06-21 | 1235.0976 | 0 | 220 | 0 | 24727296.5128 | 57831011.822
Kontrak BDM | Stripping Overburden | w21 | 2024-06-22 | 3030.2976 | 0 | 115 | 0 | 35405345.1237 | 35947715.6926
Kontrak BDM | Stripping Overburden | w21 | 2024-06-23 | 3030.2976 | 0 | 88 | 0 | 30673668.8642 | 34996221.7344
Kontrak BDM | Stripping Overburden | w21 | 2024-06-24 | 3030.2976 | 0 | 81 | 0 | 30627072.1353 | 23387444.444
Kontrak BDM | Stripping Overburden | w21 | 2024-06-25 | 3030.2976 | 0 | 128 | 0 | 39838240.8462 | 34474191.2481
Kontrak BDM | Stripping Overburden | w21 | 2024-06-26 | 3030.2976 | 0 | 51 | 0 | 17453626.3628 | 19620544.444
Kontrak BDM | Stripping Overburden | w21 | 2024-06-27 | 3030.2976 | 0 | 100 | 0 | 33652241.5276 | 22455941.524
Kontrak BDM | Stripping Overburden | w22 | 2024-06-28 | 1235.0976 | 0 | 136 | 0 | 42038258.7773 | 22388888.8881
Kontrak BDM | Stripping Overburden | w22 | 2024-06-29 | 3030.2976 | 0 | 201 | 0 | 52054199.4874 | 26757508.1902
Kontrak BDM | Stripping Overburden | w22 | 2024-06-30 | 3030.2976 | 0 | 137 | 0 | 35379127.8569 | 18416666.666
Kontrak KBM | Hauling Quarry;Quary Mined | w18 | 2024-05-31 | 0 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w18 | 2024-06-01 | 0 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w18 | 2024-06-02 | 204.4155 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w18 | 2024-06-03 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w18 | 2024-06-04 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w18 | 2024-06-05 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w18 | 2024-06-06 | 766.5581 | 14556.3 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w19 | 2024-06-07 | 525.5021 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w19 | 2024-06-08 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w19 | 2024-06-09 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w19 | 2024-06-10 | 766.5581 | 1185 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w19 | 2024-06-11 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w19 | 2024-06-12 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w19 | 2024-06-13 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w20 | 2024-06-14 | 525.5021 | 1067.4 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w20 | 2024-06-15 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w20 | 2024-06-16 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w20 | 2024-06-17 | 0 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w20 | 2024-06-18 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w20 | 2024-06-19 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w20 | 2024-06-20 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w21 | 2024-06-21 | 525.5021 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w21 | 2024-06-22 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w21 | 2024-06-23 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w21 | 2024-06-24 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w21 | 2024-06-25 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w21 | 2024-06-26 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w21 | 2024-06-27 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w22 | 2024-06-28 | 525.5021 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w22 | 2024-06-29 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Hauling Quarry;Quary Mined | w22 | 2024-06-30 | 766.5581 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Ore Getting;Ore Hauling | w18 | 2024-05-31 | 0 | 0 | 2925 | 20700 | 35166177.4308 | 185952224.0277
Kontrak KBM | Ore Getting;Ore Hauling | w18 | 2024-06-01 | 0 | 0 | 288 | 0 | 33168099.1677 | 34477161.4456
Kontrak KBM | Ore Getting;Ore Hauling | w18 | 2024-06-02 | 2928.3984 | 3326.29 | 1178 | 6375 | 34766561.7782 | 187118498.7389
Kontrak KBM | Ore Getting;Ore Hauling | w18 | 2024-06-03 | 2928.3984 | 3199.96 | 1166 | 5025 | 67565978.8912 | 248932632.4578
Kontrak KBM | Ore Getting;Ore Hauling | w18 | 2024-06-04 | 2928.3984 | 3199 | 1198.5 | 5275 | 63202039.1655 | 130691909.5888
Kontrak KBM | Ore Getting;Ore Hauling | w18 | 2024-06-05 | 2928.3984 | 2702.48 | 1209 | 5625 | 56524393.2107 | 212280077.7198
Kontrak KBM | Ore Getting;Ore Hauling | w18 | 2024-06-06 | 3656.4912 | 3601.06 | 1195.5 | 6225 | 60814956.0675 | 166982510.858
Kontrak KBM | Ore Getting;Ore Hauling | w19 | 2024-06-07 | 2506.6512 | 3697.19 | 1176 | 5400 | 40760796.5675 | 195013835.3806
Kontrak KBM | Ore Getting;Ore Hauling | w19 | 2024-06-08 | 3656.4912 | 3872.98 | 1219 | 5175 | 71583357.0529 | 283553088.2792
Kontrak KBM | Ore Getting;Ore Hauling | w19 | 2024-06-09 | 3656.4912 | 3047.57 | 1107 | 5175 | 47754070.4884 | 220517710.1614
Kontrak KBM | Ore Getting;Ore Hauling | w19 | 2024-06-10 | 3656.4912 | 3640.63 | 1324.5 | 5925 | 43757913.9622 | 161112885.8104
Kontrak KBM | Ore Getting;Ore Hauling | w19 | 2024-06-11 | 3656.4912 | 3222.02 | 1097 | 3975 | 46155607.8779 | 217911056.7589
Kontrak KBM | Ore Getting;Ore Hauling | w19 | 2024-06-12 | 3656.4912 | 3392.1 | 1118.5 | 5700 | 38163294.8255 | 194028661.3886
Kontrak KBM | Ore Getting;Ore Hauling | w19 | 2024-06-13 | 3656.4912 | 3828.4 | 919.5 | 2925 | 47754070.4884 | 118532283.2613
Kontrak KBM | Ore Getting;Ore Hauling | w20 | 2024-06-14 | 2506.6512 | 3346.68 | 777 | 3450 | 44557145.2674 | 144170899.0708
Kontrak KBM | Ore Getting;Ore Hauling | w20 | 2024-06-15 | 3656.4912 | 3585.89 | 984.5 | 4050 | 30770405.252 | 136998722.6819
Kontrak KBM | Ore Getting;Ore Hauling | w20 | 2024-06-16 | 3656.4912 | 1851.8 | 728.5 | 2775 | 26974056.552 | 112832012.6604
Kontrak KBM | Ore Getting;Ore Hauling | w20 | 2024-06-17 | 0 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Ore Getting;Ore Hauling | w20 | 2024-06-18 | 3656.4912 | 3243.04 | 760 | 2850 | 39362141.7833 | 118225600.5428
Kontrak KBM | Ore Getting;Ore Hauling | w20 | 2024-06-19 | 3656.4912 | 3708.48 | 1000.5 | 3825 | 38762718.3044 | 153507256.0032
Kontrak KBM | Ore Getting;Ore Hauling | w20 | 2024-06-20 | 3656.4912 | 4614.28 | 907 | 3375 | 42559067.0043 | 188955397.6237
Kontrak KBM | Ore Getting;Ore Hauling | w21 | 2024-06-21 | 2506.6512 | 0 | 738.5 | 3300 | 15385202.626 | 186695552.9303
Kontrak KBM | Ore Getting;Ore Hauling | w21 | 2024-06-22 | 3656.4912 | 0 | 815 | 3925 | 39362141.7833 | 112457598.0441
Kontrak KBM | Ore Getting;Ore Hauling | w21 | 2024-06-23 | 3656.4912 | 0 | 890.5 | 2925 | 38363102.6518 | 82839761.7032
Kontrak KBM | Ore Getting;Ore Hauling | w21 | 2024-06-24 | 3656.4912 | 0 | 1053.5 | 3375 | 45755992.2253 | 134282831.1924
Kontrak KBM | Ore Getting;Ore Hauling | w21 | 2024-06-25 | 3656.4912 | 0 | 1032 | 3450 | 43692693.4692 | 158038096.7637
Kontrak KBM | Ore Getting;Ore Hauling | w21 | 2024-06-26 | 3656.4912 | 0 | 913.5 | 2850 | 38363102.6518 | 243542912.9951
Kontrak KBM | Ore Getting;Ore Hauling | w21 | 2024-06-27 | 3656.4912 | 0 | 948.5 | 3300 | 41939285.4768 | 113764259.6451
Kontrak KBM | Ore Getting;Ore Hauling | w22 | 2024-06-28 | 2506.6512 | 0 | 862.5 | 3150 | 48488081.3007 | 104861601.9448
Kontrak KBM | Ore Getting;Ore Hauling | w22 | 2024-06-29 | 3656.4912 | 0 | 984.5 | 3375 | 45780496.6212 | 92142441.8255
Kontrak KBM | Ore Getting;Ore Hauling | w22 | 2024-06-30 | 3656.4912 | 0 | 527 | 2475 | 3996156.5262 | 118001824.4465
Kontrak KBM | Stripping Overburden | w18 | 2024-05-31 | 0 | 0 | 854 | 0 | 153661053.0485 | 159446941.4458
Kontrak KBM | Stripping Overburden | w18 | 2024-06-01 | 0 | 3320.9 | 451 | 0 | 70748767.6009 | 192917710.1349
Kontrak KBM | Stripping Overburden | w18 | 2024-06-02 | 1703.4624 | 392.6 | 490 | 0 | 76805879.2035 | 162218605.3093
Kontrak KBM | Stripping Overburden | w18 | 2024-06-03 | 1703.4624 | 455.5 | 140 | 0 | 22225365.085 | 162272377.0447
Kontrak KBM | Stripping Overburden | w18 | 2024-06-04 | 1703.4624 | 64.5 | 477 | 0 | 83161562.1098 | 99368888.9544
Kontrak KBM | Stripping Overburden | w18 | 2024-06-05 | 1703.4624 | 0 | 723 | 0 | 118712851.8409 | 176851280.6538
Kontrak KBM | Stripping Overburden | w18 | 2024-06-06 | 1703.4624 | 0 | 599 | 0 | 95077159.7295 | 203976194.1983
Kontrak KBM | Stripping Overburden | w19 | 2024-06-07 | 1167.7824 | 0 | 626 | 0 | 120794069.682 | 268419420.7597
Kontrak KBM | Stripping Overburden | w19 | 2024-06-08 | 1703.4624 | 344.5 | 619 | 0 | 119410818.3501 | 163484027.046
Kontrak KBM | Stripping Overburden | w19 | 2024-06-09 | 1703.4624 | 789.28 | 239 | 0 | 43212991.5502 | 194056229.4518
Kontrak KBM | Stripping Overburden | w19 | 2024-06-10 | 1703.4624 | 459.28 | 525 | 0 | 107475185.0968 | 124807131.8706
Kontrak KBM | Stripping Overburden | w19 | 2024-06-11 | 1703.4624 | 470.8 | 434 | 0 | 74707923.0156 | 197541308.1879
Kontrak KBM | Stripping Overburden | w19 | 2024-06-12 | 1703.4624 | 893.8 | 259 | 0 | 40986192.1739 | 129761004.5799
Kontrak KBM | Stripping Overburden | w19 | 2024-06-13 | 1703.4624 | 997.2 | 463 | 0 | 80086105.1308 | 124421704.0936
Kontrak KBM | Stripping Overburden | w20 | 2024-06-14 | 1167.7824 | 253.6 | 421 | 0 | 84736059.6049 | 143603692.9824
Kontrak KBM | Stripping Overburden | w20 | 2024-06-15 | 1703.4624 | 489.9 | 311 | 0 | 52183517.3666 | 101908298.5392
Kontrak KBM | Stripping Overburden | w20 | 2024-06-16 | 1703.4624 | 1213.8 | 250 | 0 | 61582129.9557 | 109928731.8717
Kontrak KBM | Stripping Overburden | w20 | 2024-06-17 | 0 | 0 | 0 | 0 | 0 | 0
Kontrak KBM | Stripping Overburden | w20 | 2024-06-18 | 1703.4624 | 734.1 | 460 | 0 | 116404133.9158 | 99703438.8872
Kontrak KBM | Stripping Overburden | w20 | 2024-06-19 | 1703.4624 | 1056 | 509 | 0 | 105729766.6053 | 161557184.0208
Kontrak KBM | Stripping Overburden | w20 | 2024-06-20 | 1703.4624 | 1607.7 | 577 | 0 | 113611284.6144 | 129448647.7208
Kontrak KBM | Stripping Overburden | w21 | 2024-06-21 | 1167.7824 | 0 | 321 | 0 | 26226940.9515 | 160222143.6249
Kontrak KBM | Stripping Overburden | w21 | 2024-06-22 | 1703.4624 | 0 | 167 | 0 | 29851505.2844 | 131501614.7183
Kontrak KBM | Stripping Overburden | w21 | 2024-06-23 | 1703.4624 | 0 | 113 | 0 | 21884567.0425 | 61898888.8881
Kontrak KBM | Stripping Overburden | w21 | 2024-06-24 | 1703.4624 | 0 | 446 | 0 | 86508200.4286 | 124582632.287
Kontrak KBM | Stripping Overburden | w21 | 2024-06-25 | 1703.4624 | 0 | 459 | 0 | 101948772.5921 | 123139622.9093
Kontrak KBM | Stripping Overburden | w21 | 2024-06-26 | 1703.4624 | 0 | 380 | 0 | 67570907.8357 | 148456838.4
Kontrak KBM | Stripping Overburden | w21 | 2024-06-27 | 1703.4624 | 0 | 532 | 0 | 102724930.2096 | 92258439.5759
Kontrak KBM | Stripping Overburden | w22 | 2024-06-28 | 1167.7824 | 0 | 302 | 0 | 69642537.7831 | 88160120.2738
Kontrak KBM | Stripping Overburden | w22 | 2024-06-29 | 1703.4624 | 0 | 590 | 0 | 95356773.3662 | 99565751.66
Kontrak KBM | Stripping Overburden | w22 | 2024-06-30 | 1703.4624 | 0 | 0 | 0 | 0 | 0