## Sheet1
my | kontrak | production | values | status
02/24 | Mining KBM | Stripping Overburden | 1 | p_plan
02/24 | Mining KBM | Hauling Quarry | 1 | p_plan
02/24 | Mining KBM | Development | 1 | p_plan
02/24 | Mining KBM | Ore Getting | 1 | p_plan
02/24 | Mining KBM | Hauling Ore | 1 | p_plan
02/24 | Mining KBM | Support Equipment | 1 | p_plan
03/24 | Mining KBM | Stripping Overburden | 1 | p_plan
03/24 | Mining KBM | Hauling Quarry | 1 | p_plan
03/24 | Mining KBM | Development | 1 | p_plan
03/24 | Mining KBM | Ore Getting | 1 | p_plan
03/24 | Mining KBM | Hauling Ore | 1 | p_plan
03/24 | Mining KBM | Support Equipment | 1 | p_plan
03/24 | Mining BDM | Stripping Overburden | 1 | p_plan
03/24 | Mining BDM | Hauling Quarry | 1 | p_plan
03/24 | Mining BDM | Development | 1 | p_plan
03/24 | Mining BDM | Ore Getting | 1 | p_plan
03/24 | Mining BDM | Hauling Ore | 1 | p_plan
03/24 | Mining BDM | Support Equipment | 1 | p_plan
04/24 | Mining KBM | Stripping Overburden | 1 | p_plan
04/24 | Mining KBM | Hauling Quarry | 1 | p_plan
04/24 | Mining KBM | Development | 1 | p_plan
04/24 | Mining KBM | Ore Getting | 1 | p_plan
04/24 | Mining KBM | Hauling Ore | 1 | p_plan
04/24 | Mining KBM | Support Equipment | 1 | p_plan
04/24 | Mining BDM | Stripping Overburden | 1 | p_plan
04/24 | Mining BDM | Hauling Quarry | 1 | p_plan
04/24 | Mining BDM | Development | 1 | p_plan
04/24 | Mining BDM | Ore Getting | 1 | p_plan
04/24 | Mining BDM | Hauling Ore | 1 | p_plan
04/24 | Mining BDM | Support Equipment | 1 | p_plan
05/24 | Mining KBM | Stripping Overburden | 1 | p_plan
05/24 | Mining KBM | Hauling Quarry | 1 | p_plan
05/24 | Mining KBM | Development | 1 | p_plan
05/24 | Mining KBM | Ore Getting | 1 | p_plan
05/24 | Mining KBM | Hauling Ore | 1 | p_plan
05/24 | Mining KBM | Support Equipment | 1 | p_plan
01/24 | Mining KBM | Stripping Overburden | 1 | p_plan
01/24 | Mining KBM | Hauling Quarry | 1 | p_plan
01/24 | Mining KBM | Development | 1 | p_plan
01/24 | Mining KBM | Ore Getting | 1 | p_plan
01/24 | Mining KBM | Hauling Ore | 1 | p_plan
01/24 | Mining KBM | Support Equipment | 1 | p_plan
01/24 | Mining BDM | Stripping Overburden | 1 | p_plan
01/24 | Mining BDM | Hauling Quarry | 1 | p_plan
01/24 | Mining BDM | Development | 1 | p_plan
01/24 | Mining BDM | Ore Getting | 1 | p_plan
01/24 | Mining BDM | Hauling Ore | 1 | p_plan
01/24 | Mining BDM | Support Equipment | 1 | p_plan
02/24 | Mining BDM | Stripping Overburden | 1 | p_plan
02/24 | Mining BDM | Hauling Quarry | 1 | p_plan
02/24 | Mining BDM | Development | 1 | p_plan
02/24 | Mining BDM | Ore Getting | 1 | p_plan
02/24 | Mining BDM | Hauling Ore | 1 | p_plan
02/24 | Mining BDM | Support Equipment | 1 | p_plan
05/24 | Mining BDM | Stripping Overburden | 1 | p_plan
05/24 | Mining BDM | Hauling Quarry | 1 | p_plan
05/24 | Mining BDM | Development | 1 | p_plan
05/24 | Mining BDM | Ore Getting | 1 | p_plan
05/24 | Mining BDM | Hauling Ore | 1 | p_plan
05/24 | Mining BDM | Support Equipment | 1 | p_plan
01/24 | Mining BDM | Hauling Quarry | 1 | p_plan
01/24 | Mining BDM | ROAD MAINTENANCE | 1 | p_plan
01/24 | Mining KBM | Hauling Quarry | 1 | p_plan
02/24 | Mining BDM | Hauling Quarry | 1 | p_plan
02/24 | Mining BDM | ROAD MAINTENANCE | 1 | p_plan
02/24 | Mining KBM | Hauling Quarry | 1 | p_plan
02/24 | Mining KBM | ROAD MAINTENANCE | 1 | p_plan
03/24 | Mining BDM | Hauling Quarry | 1 | p_plan
03/24 | Mining BDM | ROAD MAINTENANCE | 1 | p_plan
03/24 | Mining KBM | Hauling Quarry | 1 | p_plan
04/24 | Mining BDM | Hauling Quarry | 1 | p_plan
04/24 | Mining BDM | ROAD MAINTENANCE | 1 | p_plan
04/24 | Mining KBM | Hauling Quarry | 1 | p_plan
05/24 | Mining BDM | Hauling Quarry | 1 | p_plan
05/24 | Mining BDM | ROAD MAINTENANCE | 1 | p_plan
05/24 | Mining KBM | Hauling Quarry | 1 | p_plan
02/24 | Mining KBM | Stripping Overburden | 0.84961 | p_actual
02/24 | Mining KBM | Hauling Quarry | 0 | p_actual
02/24 | Mining KBM | Development | 0 | p_actual
02/24 | Mining KBM | Ore Getting | 0.66417 | p_actual
02/24 | Mining KBM | Hauling Ore | 0.55414 | p_actual
02/24 | Mining KBM | Support Equipment | 0 | p_actual
03/24 | Mining KBM | Stripping Overburden | 0.80105 | p_actual
03/24 | Mining KBM | Hauling Quarry | 0 | p_actual
03/24 | Mining KBM | Development | 0 | p_actual
03/24 | Mining KBM | Ore Getting | 0.65813 | p_actual
03/24 | Mining KBM | Hauling Ore | 0.7878 | p_actual
03/24 | Mining KBM | Support Equipment | 0 | p_actual
03/24 | Mining BDM | Stripping Overburden | 0.90019 | p_actual
03/24 | Mining BDM | Hauling Quarry | 0 | p_actual
03/24 | Mining BDM | Development | 0 | p_actual
03/24 | Mining BDM | Ore Getting | 1.1993 | p_actual
03/24 | Mining BDM | Hauling Ore | 1.713 | p_actual
03/24 | Mining BDM | Support Equipment | 0 | p_actual
04/24 | Mining KBM | Stripping Overburden | 0.89374 | p_actual
04/24 | Mining KBM | Hauling Quarry | 0 | p_actual
04/24 | Mining KBM | Development | 0 | p_actual
04/24 | Mining KBM | Ore Getting | 0.86595 | p_actual
04/24 | Mining KBM | Hauling Ore | 0.41311 | p_actual
04/24 | Mining KBM | Support Equipment | 0.14866 | p_actual
04/24 | Mining BDM | Stripping Overburden | 0.97405 | p_actual
04/24 | Mining BDM | Hauling Quarry | 0 | p_actual
04/24 | Mining BDM | Development | 0 | p_actual
04/24 | Mining BDM | Ore Getting | 1.1068 | p_actual
04/24 | Mining BDM | Hauling Ore | 2.9198 | p_actual
04/24 | Mining BDM | Support Equipment | 13.7975 | p_actual
05/24 | Mining KBM | Stripping Overburden | 0.91267 | p_actual
05/24 | Mining KBM | Hauling Quarry | 0 | p_actual
05/24 | Mining KBM | Development | 11398732.8381 | p_actual
05/24 | Mining KBM | Ore Getting | 1.0651 | p_actual
05/24 | Mining KBM | Hauling Ore | 0.70799 | p_actual
05/24 | Mining KBM | Support Equipment | 0.15817 | p_actual
01/24 | Mining KBM | Stripping Overburden | 0.8735 | p_actual
01/24 | Mining KBM | Hauling Quarry | 0 | p_actual
01/24 | Mining KBM | Development | 0 | p_actual
01/24 | Mining KBM | Ore Getting | 0.80831 | p_actual
01/24 | Mining KBM | Hauling Ore | 0.68378 | p_actual
01/24 | Mining KBM | Support Equipment | 0 | p_actual
01/24 | Mining BDM | Stripping Overburden | 0.88723 | p_actual
01/24 | Mining BDM | Hauling Quarry | 0 | p_actual
01/24 | Mining BDM | Development | 0 | p_actual
01/24 | Mining BDM | Ore Getting | 1.3748 | p_actual
01/24 | Mining BDM | Hauling Ore | 1.7661 | p_actual
01/24 | Mining BDM | Support Equipment | 0 | p_actual
02/24 | Mining BDM | Stripping Overburden | 0.91031 | p_actual
02/24 | Mining BDM | Hauling Quarry | 0 | p_actual
02/24 | Mining BDM | Development | 0 | p_actual
02/24 | Mining BDM | Ore Getting | 1.4078 | p_actual
02/24 | Mining BDM | Hauling Ore | 2.445 | p_actual
02/24 | Mining BDM | Support Equipment | 0 | p_actual
05/24 | Mining BDM | Stripping Overburden | 0.94852 | p_actual
05/24 | Mining BDM | Hauling Quarry | 0 | p_actual
05/24 | Mining BDM | Development | 0 | p_actual
05/24 | Mining BDM | Ore Getting | 1.0104 | p_actual
05/24 | Mining BDM | Hauling Ore | 2.1105 | p_actual
05/24 | Mining BDM | Support Equipment | 5.9132 | p_actual
01/24 | Mining BDM | Hauling Quarry | 399832317.4592 | p_actual
01/24 | Mining BDM | ROAD MAINTENANCE | 9025931.6592 | p_actual
01/24 | Mining KBM | Hauling Quarry | 345375221.5925 | p_actual
02/24 | Mining BDM | Hauling Quarry | 1298392200.2046 | p_actual
02/24 | Mining BDM | ROAD MAINTENANCE | 17919129.0294 | p_actual
02/24 | Mining KBM | Hauling Quarry | 905086898.2641 | p_actual
02/24 | Mining KBM | ROAD MAINTENANCE | 9952111.7036 | p_actual
03/24 | Mining BDM | Hauling Quarry | 829325740.0352 | p_actual
03/24 | Mining BDM | ROAD MAINTENANCE | 14069834.6453 | p_actual
03/24 | Mining KBM | Hauling Quarry | 1448591186.8373 | p_actual
04/24 | Mining BDM | Hauling Quarry | 783876195.5301 | p_actual
04/24 | Mining BDM | ROAD MAINTENANCE | 10751477.4176 | p_actual
04/24 | Mining KBM | Hauling Quarry | 1496339926.1949 | p_actual
05/24 | Mining BDM | Hauling Quarry | 1319405536.5084 | p_actual
05/24 | Mining BDM | ROAD MAINTENANCE | 11547883.1523 | p_actual
05/24 | Mining KBM | Hauling Quarry | 1408637471.6134 | p_actual