## SUMMARY
MINING COST (MEI)
| SUMMARY BDM BLOK 8 NAKULA | Mei 2023 |  |  | CV. SENTOSA ABADI
|  | PLAN | ACTUAL | ACH % | DAYS WORK |  | 30 | days
| OVERBURDEN REMOVAL | 47785.2672 | 15970.69 | 33.42% | WORKING HOUR |  | 270 | hours
| ORE MINING | 86937.2928 | 75392.73 | 86.72% | PHYSICHAL AVAILIBILITY |  | 90% | PA
| QUARRY MINING | 14335.5802 | 16301.3 | 113.7%
| STRIPING RATIO | 0.54965 | 0.21183 | 259.5% | Fuel Price / liter |  | 0
| FUEL RATIO OVERALL (L/Ton) | 2.2102 | 1.9537 | 113.1% | (fuel not include in contract)
| ADT HM 400 (bcm/hour) |  |  |  | Total Fuel Consumption | PLAN | 189044.3944 | Liter
| PRODUCTION hauler | 63.2 | 43.26 | 68.45% |  | ACTUAL | 147292 | Liter
[6 empty] | ACH % | 128.3%
| COST RENT + FUEL |  |  |  | COST ITEM / TON ORE
| COST OB REMOVAL | 1063487879.0274 |  |  | COST OB / TON | 21.48% | 14105.9739 | 0.95003
| COST QUARRY HAULING | 383750000 |  |  | COST QUARRY / TON | 7.752% | 5090.0133 | 0.34281
| COST DEVELOP ACT. | 0 |  |  | COST DEV / TON | 0% | 0 | 0
| COST ORE GETTING | 568760000 |  |  | COST ORE GETTING / TON | 11.49% | 7543.9635 | 0.50808
| COST ORE HAULING | 2898000000 |  |  | COST ORE HAULING / TON | 58.54% | 38438.7195 | 2.5888
| COST UNIT SUPPORT | 36210000 |  |  | COST SUPPORT / TON | 0.7315% | 480.285 | 0.032347
[6 empty] | 100% | 65658.9552 | 4.4221
| TOTAL COST | 4950207879.0274 |  |  | COST / TON ORE |  | 65658.9552
| INCOME | 8955450040.32 |  |  | ( USD / Ton ) |  | 4.4221
[5 empty] | KURS/$ |  | 14848
| RESULT | 4005242161.2926 |  |  | PRICE / TON ORE |  | 8
OKE…..

## SUMMARY MTD
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| last year (2022) | january | february | march | april | may | june | july | august | september | october | november | december | TOTAL 2022
OVERBURDEN REMOVAL | 25551.1 | 1 january: 23545.18; 2 february: 29931.98; 3 march: 18697.04; 4 april: 18697.04; 5 may: 15970.69 | 106841.93
ORE MINING | 125448.88 | 1 january: 64719.62; 2 february: 76341.76; 3 march: 71048.76; 4 april: 71048.76; 5 may: 75392.73 | 358551.63
QUARRY MINING | 12871.52 | 1 january: 746.51; 2 february: 647.58; 3 march: 7573.39; 4 april: 7573.39; 5 may: 16301.3 | 32842.17
STRIPING RATIO | 0.20368 | 1 january: 0.3638; 2 february: 0.39208; 3 march: 0.26316; 4 april: 0.26316; 5 may: 0.21183 | 0.29798
ACH % OVERBURDEN |  | 1 january: 84.91%; 2 february: 103.6%; 3 march: 39.13%; 4 april: 39.13%; 5 may: 33.42% | 60.03%
ACH % ORE MINING |  | 1 january: 118%; 2 february: 106.4%; 3 march: 81.72%; 4 april: 81.72%; 5 may: 86.72% | 94.92%
ACH % QUARRY |  | 1 january: 8.974%; 2 february: 7.469%; 3 march: 132.1%; 4 april: 132.1%; 5 may: 113.7% | 78.86%
PRODUCTION hauler | 249.917 | 1 january: 208.413; 2 february: 398.8638; 3 march: 250.4596; 4 april: 497.2039; 5 may: 43.26 | 279.6401
COST OB REMOVAL | 980772683.1761 | 1 january: 913930747.1515; 2 february: 963632138.4179; 3 march: 1138721618.3285; 4 april: 1103086793.8723; 5 may: 1063487879.0274 | 5182859176.7977
COST QUARRY HAULING | 747900000 | 1 january: 334050000; 2 february: 264500000; 3 march: 446450000; 4 april: 446450000; 5 may: 383750000 | 1875200000
COST DEVELOP ACT. | 0 | 1 january: 0; 2 february: 0; 3 march: 0; 4 april: 0; 5 may: 0 | 0
COST ORE GETTING | 1089025000 | 1 january: 434195000; 2 february: 532270000; 3 march: 553530000; 4 april: 445795000; 5 may: 568760000 | 2534550000
COST ORE HAULING | 4733400000 | 1 january: 2318400000; 2 february: 2898000000; 3 march: 2608200000; 4 april: 2994600000; 5 may: 2898000000 | 13717200000
COST UNIT SUPPORT | 80210000 | 1 january: 28210000; 2 february: 28210000; 3 march: 40210000; 4 april: 36210000; 5 may: 36210000 | 169050000
TOTAL COST | 7631307683.1761 | 1 january: 4028785747.1515; 2 february: 4686612138.4179; 3 march: 4787111618.3285; 4 april: 5026141793.8723; 5 may: 4950207879.0274 | 23478859176.7977
INCOME | 19557982187.52 | 1 january: 7687655342.08; 2 february: 9068179619.84; 3 march: 8439455907.84; 4 april: 6729864314.88; 5 may: 8955450040.32 | 40880605224.96
PROFIT | 11926674504.3439 | 1 january: 3658869594.9285; 2 february: 4381567481.4221; 3 march: 3652344289.5115; 4 april: 1703722521.0077; 5 may: 4005242161.2926 | 17401746048.1623
PERCENT COST | 39.02% | 1 january: 52.41%; 2 february: 51.68%; 3 march: 56.72%; 4 april: 74.68%; 5 may: 55.28% | 57.43%
PERCENT PROFIT | 60.98% | 1 january: 47.59%; 2 february: 48.32%; 3 march: 43.28%; 4 april: 25.32%; 5 may: 44.72% | 42.57%
FUEL RATIO (L/Ton) | 1.8718 | 1 january: 2.0366; 2 february: 2.0066; 3 march: 2.045; 4 april: 1.6507; 5 may: 1.9537 | 1.938
ACH % FUEL RATIO |  | 1 january: 104.1%; 2 february: 96.68%; 3 march: 106.5%; 4 april: 106.8%; 5 may: 113.1% | 105.4%
DAYS WORK | 61 | 1 january: 31; 2 february: 28; 3 march: 31; 4 april: 30; 5 may: 30 | 150
WORKING HOUR | 549 | 1 january: 279; 2 february: 252; 3 march: 279; 4 april: 270; 5 may: 270 | 1350
MECANICAL AVAILABILITY | 85% | 1 january: 85%; 2 february: 85%; 3 march: 85%; 4 april: 85%; 5 may: 90% | 86%
Total Fuel Consumption | 234819.598 | 1 january: 131810; 2 february: 153187.8031; 3 march: 145293; 4 april: 117279.338; 5 may: 147292 | 694862.1412
ACH % FUEL CONSUMPTION |  | 1 january: 88.23%; 2 february: 90.92%; 3 march: 130.3%; 4 april: 135.9%; 5 may: 128.3% | 114.7%
COST / TON ORE | 121718.5763 | 1 january: 62249.8362; 2 february: 61389.8886; 3 march: 67377.8349; 4 april: 88712.8178; 5 may: 65658.9552 | 345389.3326
( USD / Ton ) | 8.1976 | 1 january: 4.1925; 2 february: 4.1346; 3 march: 4.5378; 4 april: 5.9747; 5 may: 4.4221 | 23.2617

## REPORT unit OB
COST UNIT OVERBURDEN
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 400 - 01 | 118 | 950000 | 112100000 | 3599.7468 | 0 | 30.5063 | 112100000 | kbm | PC 400 LC SE-8 | KOMATSU PC 400 - 01 | K
2 | KOMATSU PC 400 - 03 | 42 | 950000 | 39900000 | 1228.6909 | 0 | 29.2545 | 39900000 | kbm | PC 400 LC SE-8 | KOMATSU PC 400 - 03 | K
3 | KOMATSU PC 300 - 12 | 10 | 400000 | 4000000 | 283.8683 | 0 | 28.3868 | 4000000 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 12 | K
4 | KOMATSU PC 300 - 17 | 35 | 400000 | 14000000 | 977.062 | 0 | 27.9161 | 14000000 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 17 | K
5 | KOMATSU PC 200 - 11 | 2 | 275000 | 550000 | 33.024 | 0 | 16.512 | 550000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 11 | K
6 | KOMATSU PC 200 - 23 | 10 | 275000 | 2750000 | 148.8841 | 0 | 14.8884 | 2750000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 23 | K
7 | KOBELCO SK 200 - 19 | 11 | 275000 | 3025000 | 135.6477 | 0 | 12.3316 | 3025000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 19 | K
8 | KOMATSU HM 400 - 06 | 84 | 1424304.3668 | 119641566.8102 | 1374.4932 | 0 | 16.363 | 119641566.8102 | kbm | HM 400-3R | KOMATSU HM 400 - 06 | K
9 | KOMATSU HM 400 - 07 | 131 | 1424304.3668 | 186583872.0493 | 1986.2235 | 0 | 15.162 | 186583872.0493 | kbm | HM 400-3R | KOMATSU HM 400 - 07 | K
10 | KOMATSU HM 400 - 08 | 76 | 1424304.3668 | 108247131.8759 | 1211.5294 | 0 | 15.9412 | 108247131.8759 | kbm | HM 400-3R | KOMATSU HM 400 - 08 | K
11 | KOMATSU HM 400 - 09 | 102 | 1424304.3668 | 145279045.4124 | 1564.9315 | 0 | 15.3425 | 145279045.4124 | kbm | HM 400-3R | KOMATSU HM 400 - 09 | K
12 | KOMATSU HM 400 - 10 | 106 | 1424304.3668 | 150976262.8796 | 1578.4487 | 0 | 14.891 | 150976262.8796 | kbm | HM 400-3R | KOMATSU HM 400 - 10 | K
13 | KOMATSU DOZER D65 - 11 | 170 | 425000 | 72250000 | 3504.3182 | 0 | 20.6136 | 72250000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 11 | K
14 | KOMATSU DOZER D65 - 12 | 99 | 425000 | 42075000 | 1884.1731 | 0 | 19.0321 | 42075000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 12 | K
15 | KOMATSU DOZER D85SS - 11 | 142 | 425000 | 60350000 | 2301.2353 | 0 | 16.2059 | 60350000 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 11 | K
16 | SAKAI - 01 | 8 | 220000 | 1760000 | 45.7017 | 0 | 5.7127 | 1760000 | kbm | SV 525 D | SAKAI - 01 | K
TOTAL |  | 1146 | 758845.1146 | 1063487879.0274 | 21857.9784 | 0 | 19.0733 | 1063487879.0274
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit QUARRY
COST UNIT QUARRY
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 400 - 01 | 40 | 1000000 | 40000000 | 1220.2532 | 0 | 30.5063 | 40000000 | kbm | PC 500 LCE-10R | KOMATSU PC 400 - 01 | K
2 | KOMATSU PC 400 - 03 | 13 | 1000000 | 13000000 | 380.3091 | 0 | 29.2545 | 13000000 | kbm | PC 500 LCE-10R | KOMATSU PC 400 - 03 | K
3 | KOMATSU PC 300 - 12 | 19 | 1000000 | 19000000 | 539.3498 | 0 | 28.3868 | 19000000 | kbm | PC 500 LCE-10R | KOMATSU PC 300 - 12 | K
4 | KOMATSU PC 300 - 17 | 59 | 1000000 | 59000000 | 1647.0474 | 0 | 27.9161 | 59000000 | kbm | PC 500 LCE-10R | KOMATSU PC 300 - 17 | K
5 | KOMATSU PC 200 - 10 | 15 | 1000000 | 15000000 | 1014.5068 | 0 | 67.6338 | 15000000 | kbm | PC 500 LCE-10R | KOMATSU PC 200 - 10 | K
6 | KOMATSU HM 400 - 06 | 62 | 1000000 | 62000000 | 727.7765 | 0 | 11.7383 | 62000000 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 06 | K
7 | KOMATSU HM 400 - 07 | 48 | 950000 | 45600000 | 685.4706 | 0 | 14.2806 | 45600000 | kbm | PC 400 LC SE-8 | KOMATSU HM 400 - 07 | K
8 | KOMATSU HM 400 - 08 | 43 | 950000 | 40850000 | 675.0685 | 0 | 15.6993 | 40850000 | kbm | PC 400 LC SE-8 | KOMATSU HM 400 - 08 | K
9 | KOMATSU HM 400 - 09 | 44 | 950000 | 41800000 | 744.5513 | 0 | 16.9216 | 41800000 | kbm | PC 400 LC SE-8 | KOMATSU HM 400 - 09 | K
10 | KOMATSU HM 400 - 10 | 50 | 950000 | 47500000 |  | 0 | 0 | 47500000 | kbm | PC 400 LC SE-8 | KOMATSU HM 400 - 10 | K
TOTAL |  | 393 | 980000 | 383750000 | 7634.3332 | 0 | 19.4258 | 383750000
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit DEVELOP
COST UNIT DEVELOPT
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | GRADER GD535 - 03 |  | 350000 | 0 |  | 0 | 0 | 0 | kbm | GD 511 A-1 | GRADER GD535 - 03 | K
2 | SAKAI - 03 |  | 220000 | 0 |  | 0 | 0 | 0 | kbm | SV 525 D | SAKAI - 03 | K
3 | SAKAI - 07 |  | 220000 | 0 |  | 0 | 0 | 0 | kbm | SV 525 D | SAKAI - 07 | K
TOTAL |  | 0 | 263333.3333 | 0 | 0 | 0 | 0 | 0
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit ORE GETTING
COST UNIT ORE GETTING
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 300 - 12 | 214 | 400000 | 85600000 | 6074.7819 | 0 | 28.3868 | 85600000 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 12 | K
2 | KOMATSU PC 300 - 17 | 180 | 400000 | 72000000 | 5024.8905 | 0 | 27.9161 | 72000000 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 17 | K
3 | KOMATSU PC 200 - 11 | 123 | 275000 | 33825000 | 2030.976 | 0 | 16.512 | 33825000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 11 | K
4 | KOMATSU PC 200 - 15 | 273 | 275000 | 75075000 | 3137 | 0 | 11.4908 | 75075000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 15 | K
5 | KOMATSU PC 200 - 23 | 223 | 275000 | 61325000 | 3320.1159 | 0 | 14.8884 | 61325000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 23 | K
6 | KOMATSU PC 200 - 24 | 310 | 275000 | 85250000 | 3128 | 0 | 10.0903 | 85250000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 24 | K
7 | KOBELCO SK 200 - 19 | 182 | 275000 | 50050000 | 2244.3523 | 0 | 12.3316 | 50050000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 19 | K
8 | KOMATSU DOZER D65 - 11 | 6 | 425000 | 2550000 | 123.6818 | 0 | 20.6136 | 2550000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 11 | K
9 | KOMATSU DOZER D65 - 12 | 57 | 425000 | 24225000 | 1084.8269 | 0 | 19.0321 | 24225000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 12 | K
10 | KOMATSU DOZER D85SS - 11 | 96 | 425000 | 40800000 | 1555.7647 | 0 | 16.2059 | 40800000 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 11 | K
11 | SAKAI - 01 | 173 | 220000 | 38060000 | 988.2983 | 0 | 5.7127 | 38060000 | kbm | SV 525 D | SAKAI - 01 | K
TOTAL |  | 1837 | 333636.3636 | 568760000 | 28712.6884 | 0 | 15.6302 | 568760000
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit DT HAUL
COST UNIT HAULING
NO | UNIT | TONNAGE |  | RENT |  | FUEL CONSUMPTION |  | RATIO |  |  | GRAND TOTAL COST | DESC. | TYPE
|  | Weight Bridge |  | Rate | Total | Fuel | Total
|  | Tonnage | Retase | ($/hour) |  | (liter) |  | (liter/ton) | (ton/ret) | (liter/ret)
1 | DT Hino 260 | 2047.65 | 53 | 460000 | 96600000 | 2599 | 0 | 1.2693 | 38.6349 | 49.0377 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 260
2 | DT Hino 261 | 2761.77 | 73 | 460000 | 96600000 | 3254 | 0 | 1.1782 | 37.8325 | 44.5753 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 261
3 | DT Hino 262 | 2155.94 | 56 | 460000 | 96600000 | 2542 | 0 | 1.1791 | 38.4989 | 45.3929 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 262
4 | DT Hino 264 | 1647.67 | 43 | 460000 | 96600000 | 1810 | 0 | 1.0985 | 38.3179 | 42.093 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 264
5 | DT Hino 265 | 3080.46 | 80 | 460000 | 96600000 | 3380 | 0 | 1.0972 | 38.5057 | 42.25 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 265
6 | DT Hino 266 | 3211.59 | 84 | 460000 | 96600000 | 3895 | 0 | 1.2128 | 38.2332 | 46.369 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 266
7 | DT Hino 268 | 2366.28 | 61 | 460000 | 96600000 | 2855 | 0 | 1.2065 | 38.7915 | 46.8033 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 268
8 | DT Hino 271 | 2119.07 | 56 | 460000 | 96600000 | 2702 | 0 | 1.2751 | 37.8405 | 48.25 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 271
9 | DT Hino 273 | 2224.07 | 57 | 460000 | 96600000 | 2634 | 0 | 1.1843 | 39.0188 | 46.2105 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 273
10 | DT Hino 275 | 3057.15 | 80 | 460000 | 96600000 | 3558 | 0 | 1.1638 | 38.2144 | 44.475 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 275
11 | DT Hino 278 | 2116.08 | 55 | 460000 | 96600000 | 2558 | 0 | 1.2088 | 38.4742 | 46.5091 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 278
12 | DT Hino 280 | 2349.31 | 61 | 460000 | 96600000 | 2793 | 0 | 1.1889 | 38.5133 | 45.7869 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 280
13 | DT Hino 282 | 3352.3 | 88 | 460000 | 96600000 | 3913 | 0 | 1.1673 | 38.0943 | 44.4659 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 282
14 | DT Hino 283 | 2426.87 | 64 | 460000 | 96600000 | 2904 | 0 | 1.1966 | 37.9198 | 45.375 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 283
15 | DT Hino 285 | 2420.51 | 65 | 460000 | 96600000 | 2647 | 0 | 1.0936 | 37.2386 | 40.7231 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 285
16 | DT Hino 286 | 3017.57 | 78 | 460000 | 96600000 | 3416 | 0 | 1.132 | 38.6868 | 43.7949 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 286
17 | DT Hino 287 | 3211.57 | 87 | 460000 | 96600000 | 3571 | 0 | 1.1119 | 36.9146 | 41.046 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 287
18 | DT Hino 288 | 2702.74 | 71 | 460000 | 96600000 | 3159 | 0 | 1.1688 | 38.0668 | 44.493 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 288
19 | DT Hino 289 | 2142.88 | 55 | 460000 | 96600000 | 2519 | 0 | 1.1755 | 38.9615 | 45.8 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 289
20 | DT Hino 290 | 3099.32 | 81 | 460000 | 96600000 | 3398 | 0 | 1.0964 | 38.2632 | 41.9506 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 290
21 | DT Hino 292 | 1719.8 | 45 | 460000 | 96600000 | 1616 | 0 | 0.93964 | 38.2178 | 35.9111 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 292
22 | DT Hino 293 | 3000.06 | 77 | 460000 | 96600000 | 3485 | 0 | 1.1616 | 38.9618 | 45.2597 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 293
23 | DT Hino 295 | 1621.27 | 42 | 460000 | 96600000 | 1922 | 0 | 1.1855 | 38.6017 | 45.7619 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 295
24 | DT Hino 296 | 2189.38 | 57 | 460000 | 96600000 | 2376 | 0 | 1.0852 | 38.4102 | 41.6842 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 296
25 | DT Hino 297 | 2697.47 | 70 | 460000 | 96600000 | 3029 | 0 | 1.1229 | 38.5353 | 43.2714 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 297
26 | DT Hino 299 | 2818.84 | 74 | 460000 | 96600000 | 3300 | 0 | 1.1707 | 38.0924 | 44.5946 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 299
27 | DT Hino 301 | 2702.66 | 70 | 460000 | 96600000 | 3217 | 0 | 1.1903 | 38.6094 | 45.9571 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 301
28 | DT Hino 302 | 2502.12 | 66 | 460000 | 96600000 | 3046 | 0 | 1.2174 | 37.9109 | 46.1515 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 302
29 | DT Hino 304 | 2432.52 | 64 | 460000 | 96600000 | 2668 | 0 | 1.0968 | 38.0081 | 41.6875 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 304
30 | DT Hino 308 | 2197.81 | 58 | 460000 | 96600000 | 2576 | 0 | 1.1721 | 37.8933 | 44.4138 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 308
TOTAL |  | 75392.73 | 1971 |  | 2898000000 | 87342 | 0 | 1.1585 | 38.251 | 44.3135 | 2898000000
HINO 700
KURS USD | 14848
FUEL PRICE | 0
Min Charge | 210 | Hour

## REPORT unit LV & support
COST UNIT SUPPORT
NO | UNIT | RENT PER MONTH | FUEL CONSUMPTION |  | RATIO | GRAND TOTAL COST | DESC. | TYPE
|  |  | Fuel | Total
|  | (Rp/month) | (liter) |  | (liter/km)
1 | LV HILUX MERAH - 06 | 8000000 | 89 | 0 |  | 8000000 |  | LV | LV HILUX MERAH - 06
2 | LV TRITON PUTIH - 28 | 8000000 | 304 | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 28
3 | LV TRITON PUTIH - 31 | 8000000 | 119 | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 31
4 | FUEL TRUCK - 02 | 210000 | 957 | 0 |  | 210000 |  | FM 260 Ti | FUEL TRUCK - 02
5 | WELDER CAR (LT-07) | 12000000 | 276 | 0 |  | 12000000 |  | LT | WELDER CAR (LT-07)
TOTAL |  | 36210000 | 1745 | 0 | 0 | 36210000
KURS USD | 14848
FUEL PRICE | 0

## HOUR METER (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
D | NO | ID UNIT | DAYLY REPORT HM | [30 empty] | TOTAL HM | TOTAL FUEL 1- 31
N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WEEK 1 | : | 0 | DAYLY REPORT HM 22: Di setujui oleh :; DAYLY REPORT HM 29: Di buat oleh :
WEEK 2 | : | 0
WEEK 3 | : | 0
WEEK 4 | : | 0 | bar: DAYLY REPORT HM 5
WEEK 5 | : | 0 | DAYLY REPORT HM 22: Internal Kontrol; DAYLY REPORT HM 29: MPE Team
0
BENAR

## FUEL UNIT (hidden)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| D | NO | ID UNIT | DAYLY REPORT FUEL | [30 empty] | TOTAL FUEL | TOTAL HM 1- 31
| N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
SM-BW 211-02 | TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
SM-BW 211-03 | TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
| TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
SM-D85ESS-08 | TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
| TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
| TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
| TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
| TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
| TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
| TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
| ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
| ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
| ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
| ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
| ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
| ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
| ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
| DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
| DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
| DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
| DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
| DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
| TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
| TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DAYLY REPORT FUEL 30: TOTAL FUEL | 0
| WEEK 1 | : | 0 | DAYLY REPORT FUEL 22: Di setujui oleh :; DAYLY REPORT FUEL 29: Di buat oleh :
| WEEK 2 | : | 0
| WEEK 3 | : | 0
| WEEK 4 | : | 0
| WEEK 5 | : | 0 | DAYLY REPORT FUEL 22: Internal Kontrol; DAYLY REPORT FUEL 29: MPE Team
0
BENAR

## list rate unit
RATE
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | unit | type
NO | UNIT | Ltr/Hr | Rent/Hr | Column1 | Column2 | Description | Column4 | Column5 | Column6 | Column7 |  | KOMATSU PC 500 - 01 | PC 500 LCE-10R
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  | KOMATSU PC 500 - 02 | PC 500 LCE-10R
|  |  | Unit Only (Internal) | Incl. Operator | Incl. Operator & Fuel | [6 empty] | KOMATSU PC 500 - 03 | PC 500 LCE-10R
1 | PC 195 LC-8 | 20 | 16.5432 | 19.5084 | 35.3704 | Excavator | 239875.7064 | 282871.4905 | 512871.4905 | 275000 | 200 | KOMATSU PC 500 - 04 | PC 500 LCE-10R
2 | PC 200-8 MO | 22 | 23.2254 | 26.1906 | 43.6389 | Excavator | 336767.7028 | 379763.4868 | 632763.4868 | 275000 | 200 | KOMATSU PC 400 - 01 | PC 400 LC SE-8
3 | PC 300 SE-8 | 30 | 41.2152 | 44.1804 | 69.5598 | Excavator | 597620.6927 | 640616.4768 | 1008616.4768 | 400000 | 300 | KOMATSU PC 400 - 03 | PC 400 LC SE-8
4 | PC 400 LC SE-8 | 38 | 58.29 | 61.6 | 87.81 | Excavator | 845205 | 893200 | 1273245 | 950000 | 400 | KOMATSU PC 400 - 04 | PC 400 LC SE-8
5 | PC 500 LCE-10R | 45 | 63.54 | 66.85 | 98.05 | Excavator | 921330 | 969325 | 1421725 | 1000000 |  | KOMATSU PC 400 - 05 | PC 400 LC SE-8
6 | SK 200-8 SX | 20 | 17.6502 | 20.6154 | 36.4775 | Excavator | 255927.8486 | 298923.6327 | 528923.6327 | 275000 | 200 | KOMATSU PC 400 - 06 | PC 400 LC SE-8
7 | SK 330-8 | 28 | 34.235 | 37.2002 | 59.4071 | Excavator | 496407.8395 | 539403.6235 | 861403.6235 | 400000 |  | KOMATSU PC 300 - 10 | PC 300 SE-8
8 | HM 400-3R | 30 | 98.2279 | 101.5379 | 127.7104 | Artic | 1424304.3668 | 1472300.1508 | 1851800.1508 | 1424304.3668 |  | KOMATSU PC 300 - 11 | PC 300 SE-8
9 | D 85 ESS-2 | 30 | 42.331 | 45.2962 | 69.0893 | Bulldozer | 613799.3709 | 656795.155 | 1001795.155 | 425000 |  | KOMATSU PC 300 - 12 | PC 300 SE-8
10 | D 65 P-12 | 33 | 42.7792 | 45.7445 | 71.9169 | Bulldozer | 620298.906 | 663294.6901 | 1042794.6901 | 425000 |  | KOMATSU PC 300 - 14 | PC 300 SE-8
11 | GD 511 A-1 | 15 | 32.851 | 35.8163 | 47.7128 | Grader | 476340.0889 | 519335.8729 | 691835.8729 | 350000 |  | KOMATSU PC 300 - 15 | PC 300 SE-8
12 | SV 525 D | 11 | 13.1981 | 16.1633 | 24.0943 | Compactor | 191372.0947 | 234367.8788 | 349367.8788 | 220000 |  | KOMATSU PC 300 - 16 | PC 300 SE-8
13 | BW 211 D-40 | 11 | 9.9397 | 12.9049 | 20.8359 | Compactor | 144125.031 | 187120.8151 | 302120.8151 | 220000 |  | KOMATSU PC 300 - 17 | PC 300 SE-8
14 | XG 6121 | 11 | 8.6243 | 11.5895 | 19.5206 | Compactor | 125052.5178 | 168048.3018 | 283048.3018 |  |  | KOBELCO SK 330 - 10 | SK 330-8
15 | XG 955-III | 20 | 12.8699 | 15.8352 | 31.6972 | Whell Loader | 186614.0656 | 229609.8497 | 459609.8497 |  |  | KOBELCO SK 330 - 11 | SK 330-8
16 | WA 380-3 | 20 | 34.0145 | 36.9797 | 52.8418 | Whell Loader | 493209.9817 | 536205.7657 | 766205.7657 |  |  | KOMATSU PC 200 - 11 | PC 200-8 MO
17 | FM 260 Ti | 15 | 17.3403 | 18.9483 | 30.0517 | Dump Truck | 251435.0252 | 274750.1408 | 435750.1408 | 210000 |  | KOMATSU PC 200 - 12 | PC 200-8 MO
18 | 700 Provia | 20 | 31.1718 | 32.9521 | 48.8142 | Dump Truck | 451990.7019 | 477805.8175 | 707805.8175 | 460000 |  | KOMATSU PC 200 - 14 | PC 200-8 MO
19 | 700 Provia/12 | 28 | 32.42 | 34.21 | 53.52 | Dump Truck | 470090 | 496045 | 776040 | 500000 |  | KOMATSU PC 200 - 15 | PC 200-8 MO
20 | LV | 10 |  |  |  |  | 8000000 |  |  | 8000000 |  | KOMATSU PC 200 - 16 | PC 200-8 MO
21 | GENSET | 4 |  |  |  |  | 3000000 |  |  | 3000000 |  | KOMATSU PC 200 - 22 | PC 200-8 MO
22 | LT | 10 |  |  |  |  | 12000000 |  |  | 12000000 |  | KOMATSU PC 200 - 23 | PC 200-8 MO
RATE MOBILISASI | [11 empty] | KOMATSU PC 200 - 24 | PC 200-8 MO
[9 empty] | source data ( owning & operating cost) |  |  | KOMATSU SK 200 - 19 | PC 200-8 MO
NO | UNIT | $ / KM | [9 empty] | KOMATSU PC 200 - 25 | PC 200-8 MO
1 | PC 400 | 24 | [9 empty] | KOMATSU PC 195 - 01 | PC 195 LC-8
2 | PC 300 | 16 | [9 empty] | KOBELCO SK 200 - 07 | SK 200-8 SX
3 | PC 200 | 8 | [9 empty] | KOBELCO SK 200 - 08 | SK 200-8 SX
4 | BULLDOZER | 16 | [9 empty] | KOBELCO SK 200 - 10 | SK 200-8 SX
5 | COMPACTOR | 8 | [9 empty] | KOBELCO SK 200 - 11 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 13 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 15 | SK 200-8 SX
| 14652.34 | [10 empty] | KOBELCO SK 200 - 16 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 18 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 19 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 20 | SK 200-8 SX
[12 empty] | KOMATSU HM 400 - 01 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 02 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 04 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 05 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 06 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 07 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 08 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 09 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 10 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 11 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 12 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 13 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 14 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 15 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 16 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 17 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 18 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 19 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 20 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 21 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 22 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 23 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 24 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 25 | HM 400-3R
[12 empty] | KOMATSU DOZER D65 - 05 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 10 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 11 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 12 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 13 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 15 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 16 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 18 | D 65 P-12
[12 empty] | KOMATSU DOZER D85SS - 11 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 14 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 17 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 18 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 20 | D 85 ESS-2
[12 empty] | GRADER GD535 - 03 | GD 511 A-1
[12 empty] | LOADER WA380 - 02 | WA 380-3
[12 empty] | SAKAI - 01 | SV 525 D
[12 empty] | SAKAI - 02 | SV 525 D
[12 empty] | SAKAI - 03 | SV 525 D
[12 empty] | SAKAI - 07 | SV 525 D
[12 empty] | LV HILUX HITAM - 05 | LV
[12 empty] | LV PAJERO PUTIH - 06 | LV
[12 empty] | LV TRITON HITAM - 08 | LV
[12 empty] | LV PAJERO PUTIH - 09 | LV
[12 empty] | LV HILUX SILVER - 10 | LV
[12 empty] | LV TRITON HITAM - 10 | LV
[12 empty] | LV TRITON PUTIH - 11 | LV
[12 empty] | LV HILUX HITAM - 11 | LV
[12 empty] | LV TRITON PUTIH - 12 | LV
[12 empty] | LV PAJERO HITAM - 15 | LV
[12 empty] | LV HILUX SILVER - 17 | LV
[12 empty] | LV HILUX HITAM - 18 | LV
[12 empty] | LV HILUX SILVER - 19 | LV
[12 empty] | LV PAJERO SILVER - 21 | LV
[12 empty] | LV HILUX PUTIH - 23 | LV
[12 empty] | LV TRITON PUTIH - 27 | LV
[12 empty] | LV LC-HIJAU - 29 | LV
[12 empty] | LV TRITON PUTIH (SAFETY) - 30 | LV
[12 empty] | LV TRITON PUTIH - 31 | LV
[12 empty] | LV TRITON PUTIH - 32 | LV
[12 empty] | MANHAUL - 02 | FM 260 Ti
[12 empty] | BUS APP - 03 | LT
[12 empty] | FUEL TRUCK - 02 | FM 260 Ti
[12 empty] | FUEL TRUCK - 03 | FM 260 Ti
[12 empty] | FUEL TRUCK - 05 | FM 260 Ti
[12 empty] | FUEL TRUCK - 06 | FM 260 Ti
[12 empty] | TRUCK WELDER - LT-04 | LT
[12 empty] | TRUCK TYRE - LT-08 | LT
[12 empty] | TRUCK MAINTENANCE - LT-09 | LT
[12 empty] | TRUCK TYRE - LT-10 | LT
MEKANIK CAMP
[12 empty] | LV TRITON PUTIH - 28 | LV
[12 empty] | TRUCK TYRE (LT-06) | LT
[12 empty] | WELDER CAR (LT-07) | LT
[12 empty] | LV HILUX MERAH - 06 | LV