## SUMMARY
MINING COST (JULI)
| SUMMARY BDM BLOK 8 NAKULA | Juli 2023 |  |  | CV. SENTOSA ABADI
|  | PLAN | ACTUAL | ACH % | DAYS WORK |  | 31 | days
| OVERBURDEN REMOVAL | 42612.9792 | 37840.7 | 88.8% | WORKING HOUR |  | 279 | hours
| ORE MINING | 87756.4616 | 68836.02 | 78.44% | PHYSICHAL AVAILIBILITY |  | 90% | PA
| QUARRY MINING | 5113.5575 | 4019.2 | 78.6%
| STRIPING RATIO | 0.48558 | 0.54972 | 88.33% | Fuel Price / liter |  | 0
| FUEL RATIO OVERALL (L/Ton) | 2.0532 | 2.1764 | 94.34% | (fuel not include in contract)
kurangnya produktifitas unit hauling dikarenakan rendahnya angka PA unit
| ADT HM 400 (bcm/hour) |  |  |  | Total Fuel Consumption | PLAN | 180179.5353 | Liter
| PRODUCTION hauler | 63.2 | 58.3961 | 92.4% |  | ACTUAL | 149817 | Liter
[6 empty] | ACH % | 120.3%
| COST RENT + FUEL |  |  |  | COST ITEM / TON ORE
| COST OB REMOVAL | 1309474229.6789 |  |  | COST OB / TON | 25.3% | 19023.0962 | 1.2812
| COST QUARRY HAULING | 344950000 |  |  | COST QUARRY / TON | 6.664% | 5011.1846 | 0.3375
| COST DEVELOP ACT. | 0 |  |  | COST DEV / TON | 0% | 0 | 0
| COST ORE GETTING | 575360000 |  |  | COST ORE GETTING / TON | 11.12% | 8358.4147 | 0.56293
| COST ORE HAULING | 2898000000 |  |  | COST ORE HAULING / TON | 55.99% | 42100.0517 | 2.8354
| COST UNIT SUPPORT | 48210000 |  |  | COST SUPPORT / TON | 0.9314% | 700.3601 | 0.047169
[6 empty] | 100% | 75193.1072 | 5.0642
| TOTAL COST | 5175994229.6789 |  |  | COST / TON ORE |  | 75193.1072
| INCOME | 8176617799.68 |  |  | ( USD / Ton ) |  | 5.0642
[5 empty] | KURS/$ |  | 14848
| RESULT | 3000623570.0011 |  |  | PRICE / TON ORE |  | 8
OKE…..

## SUMMARY MTD
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| last year (2022) | january | february | march | april | may | june | july | august | september | october | november | december | TOTAL 2022
OVERBURDEN REMOVAL | 25551.1 | 1 january: 23545.18; 2 february: 29931.98; 3 march: 18697.04; 4 april: 18697.04; 5 may: 15970.69; 6 june: 21341.3; 7 july: 37840.7 | 166023.93
ORE MINING | 125448.88 | 1 january: 64719.62; 2 february: 76341.76; 3 march: 71048.76; 4 april: 71048.76; 5 may: 75392.73; 6 june: 65676.39; 7 july: 68836.02 | 493064.04
QUARRY MINING | 12871.52 | 1 january: 746.51; 2 february: 647.58; 3 march: 7573.39; 4 april: 7573.39; 5 may: 16301.3; 6 june: 0; 7 july: 4019.2 | 36861.37
STRIPING RATIO | 0.20368 | 1 january: 0.3638; 2 february: 0.39208; 3 march: 0.26316; 4 april: 0.26316; 5 may: 0.21183; 6 june: 0.32495; 7 july: 0.54972 | 0.33672
ACH % OVERBURDEN |  | 1 january: 84.91%; 2 february: 103.6%; 3 march: 39.13%; 4 april: 39.13%; 5 may: 33.42%; 6 june: 60.55%; 7 july: 88.8% | 64.21%
ACH % ORE MINING |  | 1 january: 118%; 2 february: 106.4%; 3 march: 81.72%; 4 april: 81.72%; 5 may: 86.72%; 6 june: 85.45%; 7 july: 78.44% | 91.21%
ACH % QUARRY |  | 1 january: 8.974%; 2 february: 7.469%; 3 march: 132.1%; 4 april: 132.1%; 5 may: 113.7%; 6 june: 0%; 7 july: 78.6% | 67.56%
PRODUCTION hauler | 249.917 | 1 january: 208.413; 2 february: 398.8638; 3 march: 250.4596; 4 april: 497.2039; 5 may: 43.26; 6 june: 39.5209; 7 july: 58.3961 | 213.7311
COST OB REMOVAL | 980772683.1761 | 1 january: 913930747.1515; 2 february: 963632138.4179; 3 march: 1138721618.3285; 4 april: 1103086793.8723; 5 may: 1063487879.0274; 6 june: 1108555488.1971; 7 july: 1309474229.6789 | 7600888894.6737
COST QUARRY HAULING | 747900000 | 1 january: 334050000; 2 february: 264500000; 3 march: 446450000; 4 april: 446450000; 5 may: 383750000; 6 june: 156750000; 7 july: 344950000 | 2376900000
COST DEVELOP ACT. | 0 | 1 january: 0; 2 february: 0; 3 march: 0; 4 april: 0; 5 may: 0; 6 june: 0; 7 july: 0 | 0
COST ORE GETTING | 1089025000 | 1 january: 434195000; 2 february: 532270000; 3 march: 553530000; 4 april: 445795000; 5 may: 568760000; 6 june: 546440000; 7 july: 575360000 | 3656350000
COST ORE HAULING | 4733400000 | 1 january: 2318400000; 2 february: 2898000000; 3 march: 2608200000; 4 april: 2994600000; 5 may: 2898000000; 6 june: 2801400000; 7 july: 2898000000 | 19416600000
COST UNIT SUPPORT | 80210000 | 1 january: 28210000; 2 february: 28210000; 3 march: 40210000; 4 april: 36210000; 5 may: 36210000; 6 june: 48210000; 7 july: 48210000 | 265470000
TOTAL COST | 7631307683.1761 | 1 january: 4028785747.1515; 2 february: 4686612138.4179; 3 march: 4787111618.3285; 4 april: 5026141793.8723; 5 may: 4950207879.0274; 6 june: 4661355488.1971; 7 july: 5175994229.6789 | 33316208894.6737
INCOME | 19557982187.52 | 1 january: 7687655342.08; 2 february: 9068179619.84; 3 march: 8439455907.84; 4 april: 6729864314.88; 5 may: 8955450040.32; 6 june: 7801304309.76; 7 july: 8176617799.68 | 56858527334.4
PROFIT | 11926674504.3439 | 1 january: 3658869594.9285; 2 february: 4381567481.4221; 3 march: 3652344289.5115; 4 april: 1703722521.0077; 5 may: 4005242161.2926; 6 june: 3139948821.5629; 7 july: 3000623570.0011 | 23542318439.7263
PERCENT COST | 39.02% | 1 january: 52.41%; 2 february: 51.68%; 3 march: 56.72%; 4 april: 74.68%; 5 may: 55.28%; 6 june: 59.75%; 7 july: 63.3% | 58.59%
PERCENT PROFIT | 60.98% | 1 january: 47.59%; 2 february: 48.32%; 3 march: 43.28%; 4 april: 25.32%; 5 may: 44.72%; 6 june: 40.25%; 7 july: 36.7% | 41.41%
FUEL RATIO (L/Ton) | 1.8718 | 1 january: 2.0366; 2 february: 2.0066; 3 march: 2.045; 4 april: 1.6507; 5 may: 1.9537; 6 june: 2.0772; 7 july: 2.1764 | 1.9898
ACH % FUEL RATIO |  | 1 january: 104.1%; 2 february: 96.68%; 3 march: 106.5%; 4 april: 106.8%; 5 may: 113.1%; 6 june: 96.97%; 7 july: 94.34% | 102.6%
DAYS WORK | 61 | 1 january: 31; 2 february: 28; 3 march: 31; 4 april: 30; 5 may: 31; 6 june: 30; 7 july: 31 | 212
WORKING HOUR | 549 | 1 january: 279; 2 february: 252; 3 march: 279; 4 april: 270; 5 may: 270; 6 june: 270; 7 july: 279 | 1899
MECANICAL AVAILABILITY | 85% | 1 january: 85%; 2 february: 85%; 3 march: 85%; 4 april: 85%; 5 may: 90%; 6 june: 90%; 7 july: 90% | 87.14%
Total Fuel Consumption | 234819.598 | 1 january: 131810; 2 february: 153187.8031; 3 march: 145293; 4 april: 117279.338; 5 may: 147292; 6 june: 136424; 7 july: 149817 | 981103.1412
ACH % FUEL CONSUMPTION |  | 1 january: 88.23%; 2 february: 90.92%; 3 march: 130.3%; 4 april: 135.9%; 5 may: 128.3%; 6 june: 1.1347; 7 july: 1.2027 | 115.4%
COST / TON ORE | 121718.5763 | 1 january: 62249.8362; 2 february: 61389.8886; 3 march: 67377.8349; 4 april: 88712.8178; 5 may: 65658.9552; 6 june: 70974.5997; 7 july: 75193.1072 | 491557.0395
( USD / Ton ) | 8.1976 | 1 january: 4.1925; 2 february: 4.1346; 3 march: 4.5378; 4 april: 5.9747; 5 may: 4.4221; 6 june: 4.7801; 7 july: 5.0642 | 33.1059

## REPORT unit OB
COST UNIT OVERBURDEN
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 400 - 01 | 92 | 950000 | 87400000 | 2633.8286 | 0 | 28.6286 | 87400000 | bdm | PC 400 LC SE-8 | KOMATSU PC 400 - 01 | K
2 | KOMATSU PC 400 - 07 | 117 | 950000 | 111150000 | 4374 | 0 | 37.3846 | 111150000 | bdm | PC 400 LC SE-8 | KOMATSU PC 400 - 07 | K
3 | KOMATSU PC 300 - 12 | 48 | 400000 | 19200000 | 1246.4895 | 0 | 25.9685 | 19200000 | bdm | PC 300 SE-8 | KOMATSU PC 300 - 12 | K
4 | KOMATSU PC 300 - 17 | 15 | 400000 | 6000000 | 394.9644 | 0 | 26.331 | 6000000 | bdm | PC 300 SE-8 | KOMATSU PC 300 - 17 | K
5 | KOMATSU HM 400 - 06 | 136 | 1424304.3668 | 193705393.8832 | 2391.1642 | 0 | 17.5821 | 193705393.8832 | bdm | HM 400-3R | KOMATSU HM 400 - 06 | K
6 | KOMATSU HM 400 - 07 | 136 | 1424304.3668 | 193705393.8832 | 2269.1507 | 0 | 16.6849 | 193705393.8832 | bdm | HM 400-3R | KOMATSU HM 400 - 07 | K
7 | KOMATSU HM 400 - 08 | 148 | 1424304.3668 | 210797046.2847 | 2847.2746 | 0 | 19.2383 | 210797046.2847 | bdm | HM 400-3R | KOMATSU HM 400 - 08 | K
8 | KOMATSU HM 400 - 09 | 112 | 1424304.3668 | 159522089.0803 | 1937.0492 | 0 | 17.2951 | 159522089.0803 | bdm | HM 400-3R | KOMATSU HM 400 - 09 | K
9 | KOMATSU HM 400 - 10 | 116 | 1424304.3668 | 165219306.5475 | 2009.3425 | 0 | 17.3219 | 165219306.5475 | bdm | HM 400-3R | KOMATSU HM 400 - 10 | K
10 | KOMATSU DOZER D65 - 11 | 132 | 425000 | 56100000 | 2589.0857 | 0 | 19.6143 | 56100000 | bdm | D 65 P-12 | KOMATSU DOZER D65 - 11 | K
11 | KOMATSU DOZER D65 - 12 | 163 | 425000 | 69275000 | 3625.0419 | 0 | 22.2395 | 69275000 | bdm | D 65 P-12 | KOMATSU DOZER D65 - 12 | K
12 | KOMATSU DOZER D85SS - 11 | 88 | 425000 | 37400000 | 1705.5845 | 0 | 19.3816 | 37400000 | bdm | D 85 ESS-2 | KOMATSU DOZER D85SS - 11 | K
TOTAL |  | 1303 | 924710.1528 | 1309474229.6789 | 28022.9758 | 0 | 21.5065 | 1309474229.6789
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit QUARRY
COST UNIT QUARRY
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 400 - 01 | 13 | 1000000 | 13000000 | 372.1714 | 0 | 28.6286 | 13000000 | bdm | PC 500 LCE-10R | KOMATSU PC 400 - 01 | K
2 | KOMATSU PC 300 - 12 | 71 | 1000000 | 71000000 | 1843.7657 | 0 | 25.9685 | 71000000 | bdm | PC 500 LCE-10R | KOMATSU PC 300 - 12 | K
3 | KOMATSU PC 300 - 17 | 45 | 1000000 | 45000000 | 1184.8932 | 0 | 26.331 | 45000000 | bdm | PC 500 LCE-10R | KOMATSU PC 300 - 17 | K
4 | KOMATSU HM 400 - 06 | 65 | 1000000 | 65000000 | 1142.8358 | 0 | 17.5821 | 65000000 | bdm | PC 500 LCE-10R | KOMATSU HM 400 - 06 | K
5 | KOMATSU HM 400 - 07 | 10 | 1000000 | 10000000 | 166.8493 | 0 | 16.6849 | 10000000 | bdm | PC 500 LCE-10R | KOMATSU HM 400 - 07 | K
6 | KOMATSU HM 400 - 08 | 45 | 1000000 | 45000000 | 865.7254 | 0 | 19.2383 | 45000000 | bdm | PC 500 LCE-10R | KOMATSU HM 400 - 08 | K
7 | KOMATSU HM 400 - 09 | 71 | 950000 | 67450000 | 1227.9508 | 0 | 17.2951 | 67450000 | bdm | PC 400 LC SE-8 | KOMATSU HM 400 - 09 | K
8 | KOMATSU HM 400 - 10 | 30 | 950000 | 28500000 | 519.6575 | 0 | 17.3219 | 28500000 | bdm | PC 400 LC SE-8 | KOMATSU HM 400 - 10 | K
TOTAL |  | 350 | 987500 | 344950000 | 7323.8493 | 0 | 20.9253 | 344950000
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit DEVELOP
COST UNIT DEVELOPT
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | GRADER GD535 - 03 |  | 350000 | 0 |  | 0 | 0 | 0 | kbm | GD 511 A-1 | GRADER GD535 - 03 | K
2 | SAKAI - 03 |  | 220000 | 0 |  | 0 | 0 | 0 | kbm | SV 525 D | SAKAI - 03 | K
3 | SAKAI - 07 |  | 220000 | 0 |  | 0 | 0 | 0 | kbm | SV 525 D | SAKAI - 07 | K
TOTAL |  | 0 | 263333.3333 | 0 | 0 | 0 | 0 | 0
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit ORE GETTING
COST UNIT ORE GETTING
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 300 - 12 | 167 | 400000 | 66800000 | 4336.7448 | 0 | 25.9685 | 66800000 | bdm | PC 300 SE-8 | KOMATSU PC 300 - 12 | K
2 | KOMATSU PC 300 - 17 | 221 | 400000 | 88400000 | 5819.1423 | 0 | 26.331 | 88400000 | bdm | PC 300 SE-8 | KOMATSU PC 300 - 17 | K
3 | KOMATSU PC 200 - 11 | 202 | 275000 | 55550000 | 3428 | 0 | 16.9703 | 55550000 | bdm | PC 200-8 MO | KOMATSU PC 200 - 11 | K
4 | KOMATSU PC 200 - 15 | 305 | 275000 | 83875000 | 3476 | 0 | 11.3967 | 83875000 | bdm | PC 200-8 MO | KOMATSU PC 200 - 15 | K
5 | KOMATSU PC 200 - 23 | 292 | 275000 | 80300000 | 4298 | 0 | 14.7192 | 80300000 | bdm | PC 200-8 MO | KOMATSU PC 200 - 23 | K
6 | KOMATSU PC 200 - 24 | 309 | 275000 | 84975000 | 3302 | 0 | 10.6861 | 84975000 | bdm | PC 200-8 MO | KOMATSU PC 200 - 24 | K
7 | KOBELCO SK 200 - 19 | 123 | 275000 | 33825000 | 1631 | 0 | 13.2602 | 33825000 | bdm | SK 200-8 SX | KOBELCO SK 200 - 19 | K
8 | KOMATSU DOZER D65 - 11 | 8 | 425000 | 3400000 | 156.9143 | 0 | 19.6143 | 3400000 | bdm | D 65 P-12 | KOMATSU DOZER D65 - 11 | K
9 | KOMATSU DOZER D65 - 12 | 4 | 425000 | 1700000 | 88.9581 | 0 | 22.2395 | 1700000 | bdm | D 65 P-12 | KOMATSU DOZER D65 - 12 | K
10 | KOMATSU DOZER D85SS - 11 | 119 | 425000 | 50575000 | 2306.4155 | 0 | 19.3816 | 50575000 | bdm | D 85 ESS-2 | KOMATSU DOZER D85SS - 11 | K
11 | SAKAI - 01 | 118 | 220000 | 25960000 | 678 | 0 | 5.7458 | 25960000 | bdm | SV 525 D | SAKAI - 01 | K
TOTAL |  | 1868 | 333636.3636 | 575360000 | 29521.1749 | 0 | 15.8036 | 575360000
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit DT HAUL
COST UNIT HAULING
NO | UNIT | TONNAGE |  | RENT |  | FUEL CONSUMPTION |  | RATIO |  |  | GRAND TOTAL COST | DESC. | TYPE
|  | Weight Bridge |  | Rate | Total | Fuel | Total
|  | Tonnage | Retase | ($/hour) |  | (liter) |  | (liter/ton) | (ton/ret) | (liter/ret)
1 | DT Hino 260 | 831.78 | 22 | 460000 | 96600000 | 1086 | 0 | 1.3056 | 37.8082 | 49.3636 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 260
2 | DT Hino 261 | 3473.71 | 93 | 460000 | 96600000 | 4067 | 0 | 1.1708 | 37.3517 | 43.7312 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 261
3 | DT Hino 262 | 2419.76 | 64 | 460000 | 96600000 | 2834 | 0 | 1.1712 | 37.8087 | 44.2812 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 262
4 | DT Hino 265 | 2427.18 | 65 | 460000 | 96600000 | 2839 | 0 | 1.1697 | 37.3412 | 43.6769 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 265
5 | DT Hino 266 | 2806.02 | 75 | 460000 | 96600000 | 3384 | 0 | 1.206 | 37.4136 | 45.12 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 266
6 | DT Hino 268 | 2698.31 | 73 | 460000 | 96600000 | 3320 | 0 | 1.2304 | 36.9632 | 45.4795 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 268
7 | DT Hino 271 | 2000.98 | 53 | 460000 | 96600000 | 2467 | 0 | 1.2329 | 37.7543 | 46.5472 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 271
8 | DT Hino 273 | 2426.63 | 65 | 460000 | 96600000 | 3204 | 0 | 1.3203 | 37.3328 | 49.2923 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 273
9 | DT Hino 275 | 3040.32 | 81 | 460000 | 96600000 | 3355 | 0 | 1.1035 | 37.5348 | 41.4198 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 275
10 | DT Hino 278 | 2237.08 | 60 | 460000 | 96600000 | 2773 | 0 | 1.2396 | 37.2847 | 46.2167 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 278
11 | DT Hino 280 | 2537.5 | 67 | 460000 | 96600000 | 2952 | 0 | 1.1633 | 37.8731 | 44.0597 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 280
12 | DT Hino 282 | 4261.94 | 114 | 460000 | 96600000 | 5138 | 0 | 1.2056 | 37.3854 | 45.0702 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 282
13 | DT Hino 283 | 2686.29 | 71 | 460000 | 96600000 | 3284 | 0 | 1.2225 | 37.8351 | 46.2535 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 283
14 | DT Hino 285 | 2944.35 | 79 | 460000 | 96600000 | 3590 | 0 | 1.2193 | 37.2703 | 45.443 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 285
15 | DT Hino 286 | 2471.98 | 67 | 460000 | 96600000 | 3072 | 0 | 1.2427 | 36.8952 | 45.8507 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 286
16 | DT Hino 287 | 1993.93 | 55 | 460000 | 96600000 | 2373 | 0 | 1.1901 | 36.2533 | 43.1455 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 287
17 | DT Hino 288 | 2220.32 | 59 | 460000 | 96600000 | 2577 | 0 | 1.1606 | 37.6325 | 43.678 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 288
18 | DT Hino 289 | 3487.84 | 94 | 460000 | 96600000 | 3964 | 0 | 1.1365 | 37.1047 | 42.1702 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 289
19 | DT Hino 290 | 112.18 | 3 | 460000 | 96600000 | 0 | 0 | 0 | 37.3933 | 0 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 290
20 | DT Hino 292 | 2610.89 | 70 | 460000 | 96600000 | 3088 | 0 | 1.1827 | 37.2984 | 44.1143 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 292
21 | DT Hino 293 | 2489.56 | 66 | 460000 | 96600000 | 2916 | 0 | 1.1713 | 37.7206 | 44.1818 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 293
22 | DT Hino 294 | 1711.61 | 45 | 460000 | 96600000 | 1970 | 0 | 1.151 | 38.0358 | 43.7778 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 294
23 | DT Hino 295 | 1480.69 | 40 | 460000 | 96600000 | 1860 | 0 | 1.2562 | 37.0173 | 46.5 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 295
24 | DT Hino 296 | 1748.01 | 47 | 460000 | 96600000 | 2258 | 0 | 1.2918 | 37.1917 | 48.0426 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 296
25 | DT Hino 297 | 2610.15 | 70 | 460000 | 96600000 | 3063 | 0 | 1.1735 | 37.2879 | 43.7571 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 297
26 | DT Hino 299 | 1745.17 | 47 | 460000 | 96600000 | 2030 | 0 | 1.1632 | 37.1313 | 43.1915 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 299
27 | DT Hino 301 | 2510.97 | 67 | 460000 | 96600000 | 3047 | 0 | 1.2135 | 37.4772 | 45.4776 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 301
28 | DT Hino 302 | 1088.55 | 29 | 460000 | 96600000 | 1318 | 0 | 1.2108 | 37.5362 | 45.4483 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 302
29 | DT Hino 304 | 2560.39 | 68 | 460000 | 96600000 | 3181 | 0 | 1.2424 | 37.6528 | 46.7794 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 304
30 | DT Hino 308 | 1201.93 | 32 | 460000 | 96600000 | 1412 | 0 | 1.1748 | 37.5603 | 44.125 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 308
TOTAL |  | 68836.02 | 1841 |  | 2898000000 | 82422 | 0 | 1.1974 | 37.3906 | 44.7702 | 2898000000
HINO 700
KURS USD | 14848
FUEL PRICE | 0
Min Charge | 210 | Hour

## REPORT unit LV & support
COST UNIT SUPPORT
NO | UNIT | RENT PER MONTH | FUEL CONSUMPTION |  | RATIO | GRAND TOTAL COST | DESC. | TYPE
|  |  | Fuel | Total
|  | (Rp/month) | (liter) |  | (liter/km)
1 | LV HILUX MERAH - 06 | 8000000 | 185 | 0 |  | 8000000 |  | LV | LV HILUX MERAH - 06
2 | LV TRITON PUTIH - 28 | 8000000 | 524 | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 28
3 | LV TRITON PUTIH - 31 | 8000000 | 271 | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 31
4 | FUEL TRUCK - 02 | 210000 | 1011 | 0 |  | 210000 |  | FM 260 Ti | FUEL TRUCK - 02
5 | TRUCK TYRE (LT-06) | 12000000 | 124 | 0 |  | 12000000 |  | LT | TRUCK TYRE (LT-06)
6 | WELDER CAR (LT-07) | 12000000 | 412 | 0 |  | 12000000 |  | LT | WELDER CAR (LT-07)
TOTAL |  | 48210000 | 2527 | 0 | 0 | 48210000
KURS USD | 14848
FUEL PRICE | 0

## HOUR METER (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
D | NO | ID UNIT | DAYLY REPORT HM | [30 empty] | TOTAL HM | TOTAL FUEL 1- 31
N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WEEK 1 | : | 0 | DAYLY REPORT HM 22: Di setujui oleh :; DAYLY REPORT HM 29: Di buat oleh :
WEEK 2 | : | 0
WEEK 3 | : | 0
WEEK 4 | : | 0 | bar: DAYLY REPORT HM 5
WEEK 5 | : | 0 | DAYLY REPORT HM 22: Internal Kontrol; DAYLY REPORT HM 29: MPE Team
0
BENAR

## FUEL UNIT (hidden)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| D | NO | ID UNIT | DAYLY REPORT FUEL | [30 empty] | TOTAL FUEL | TOTAL HM 1- 31
| N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
SM-BW 211-02 | TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
SM-BW 211-03 | TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
| TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
SM-D85ESS-08 | TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
| TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
| TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
| TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
| TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
| TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
| TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
| ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
| ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
| ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
| ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
| ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
| ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
| ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
| DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
| DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
| DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
| DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
| DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
| TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
| TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DAYLY REPORT FUEL 30: TOTAL FUEL | 0
| WEEK 1 | : | 0 | DAYLY REPORT FUEL 22: Di setujui oleh :; DAYLY REPORT FUEL 29: Di buat oleh :
| WEEK 2 | : | 0
| WEEK 3 | : | 0
| WEEK 4 | : | 0
| WEEK 5 | : | 0 | DAYLY REPORT FUEL 22: Internal Kontrol; DAYLY REPORT FUEL 29: MPE Team
0
BENAR

## list rate unit
RATE
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | unit | type
NO | UNIT | Ltr/Hr | Rent/Hr | Column1 | Column2 | Description | Column4 | Column5 | Column6 | Column7 |  | KOMATSU PC 500 - 01 | PC 500 LCE-10R
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  | KOMATSU PC 500 - 02 | PC 500 LCE-10R
|  |  | Unit Only (Internal) | Incl. Operator | Incl. Operator & Fuel | [6 empty] | KOMATSU PC 500 - 03 | PC 500 LCE-10R
1 | PC 195 LC-8 | 20 | 16.5432 | 19.5084 | 35.3704 | Excavator | 239875.7064 | 282871.4905 | 512871.4905 | 275000 | 200 | KOMATSU PC 500 - 04 | PC 500 LCE-10R
2 | PC 200-8 MO | 22 | 23.2254 | 26.1906 | 43.6389 | Excavator | 336767.7028 | 379763.4868 | 632763.4868 | 275000 | 200 | KOMATSU PC 400 - 01 | PC 400 LC SE-8
3 | PC 300 SE-8 | 30 | 41.2152 | 44.1804 | 69.5598 | Excavator | 597620.6927 | 640616.4768 | 1008616.4768 | 400000 | 300 | KOMATSU PC 400 - 03 | PC 400 LC SE-8
4 | PC 400 LC SE-8 | 38 | 58.29 | 61.6 | 87.81 | Excavator | 845205 | 893200 | 1273245 | 950000 | 400 | KOMATSU PC 400 - 04 | PC 400 LC SE-8
5 | PC 500 LCE-10R | 45 | 63.54 | 66.85 | 98.05 | Excavator | 921330 | 969325 | 1421725 | 1000000 |  | KOMATSU PC 400 - 05 | PC 400 LC SE-8
6 | SK 200-8 SX | 20 | 17.6502 | 20.6154 | 36.4775 | Excavator | 255927.8486 | 298923.6327 | 528923.6327 | 275000 | 200 | KOMATSU PC 400 - 06 | PC 400 LC SE-8
7 | SK 330-8 | 28 | 34.235 | 37.2002 | 59.4071 | Excavator | 496407.8395 | 539403.6235 | 861403.6235 | 400000 |  | KOMATSU PC 300 - 10 | PC 300 SE-8
8 | HM 400-3R | 30 | 98.2279 | 101.5379 | 127.7104 | Artic | 1424304.3668 | 1472300.1508 | 1851800.1508 | 1424304.3668 |  | KOMATSU PC 300 - 11 | PC 300 SE-8
9 | D 85 ESS-2 | 30 | 42.331 | 45.2962 | 69.0893 | Bulldozer | 613799.3709 | 656795.155 | 1001795.155 | 425000 |  | KOMATSU PC 300 - 12 | PC 300 SE-8
10 | D 65 P-12 | 33 | 42.7792 | 45.7445 | 71.9169 | Bulldozer | 620298.906 | 663294.6901 | 1042794.6901 | 425000 |  | KOMATSU PC 300 - 14 | PC 300 SE-8
11 | GD 511 A-1 | 15 | 32.851 | 35.8163 | 47.7128 | Grader | 476340.0889 | 519335.8729 | 691835.8729 | 350000 |  | KOMATSU PC 300 - 15 | PC 300 SE-8
12 | SV 525 D | 11 | 13.1981 | 16.1633 | 24.0943 | Compactor | 191372.0947 | 234367.8788 | 349367.8788 | 220000 |  | KOMATSU PC 300 - 16 | PC 300 SE-8
13 | BW 211 D-40 | 11 | 9.9397 | 12.9049 | 20.8359 | Compactor | 144125.031 | 187120.8151 | 302120.8151 | 220000 |  | KOMATSU PC 300 - 17 | PC 300 SE-8
14 | XG 6121 | 11 | 8.6243 | 11.5895 | 19.5206 | Compactor | 125052.5178 | 168048.3018 | 283048.3018 |  |  | KOBELCO SK 330 - 10 | SK 330-8
15 | XG 955-III | 20 | 12.8699 | 15.8352 | 31.6972 | Whell Loader | 186614.0656 | 229609.8497 | 459609.8497 |  |  | KOBELCO SK 330 - 11 | SK 330-8
16 | WA 380-3 | 20 | 34.0145 | 36.9797 | 52.8418 | Whell Loader | 493209.9817 | 536205.7657 | 766205.7657 |  |  | KOMATSU PC 200 - 11 | PC 200-8 MO
17 | FM 260 Ti | 15 | 17.3403 | 18.9483 | 30.0517 | Dump Truck | 251435.0252 | 274750.1408 | 435750.1408 | 210000 |  | KOMATSU PC 200 - 12 | PC 200-8 MO
18 | 700 Provia | 20 | 31.1718 | 32.9521 | 48.8142 | Dump Truck | 451990.7019 | 477805.8175 | 707805.8175 | 460000 |  | KOMATSU PC 200 - 14 | PC 200-8 MO
19 | 700 Provia/12 | 28 | 32.42 | 34.21 | 53.52 | Dump Truck | 470090 | 496045 | 776040 | 500000 |  | KOMATSU PC 200 - 15 | PC 200-8 MO
20 | LV | 10 |  |  |  |  | 8000000 |  |  | 8000000 |  | KOMATSU PC 200 - 16 | PC 200-8 MO
21 | GENSET | 4 |  |  |  |  | 3000000 |  |  | 3000000 |  | KOMATSU PC 200 - 22 | PC 200-8 MO
22 | LT | 10 |  |  |  |  | 12000000 |  |  | 12000000 |  | KOMATSU PC 200 - 23 | PC 200-8 MO
RATE MOBILISASI | [11 empty] | KOMATSU PC 200 - 24 | PC 200-8 MO
[9 empty] | source data ( owning & operating cost) |  |  | KOMATSU SK 200 - 19 | PC 200-8 MO
NO | UNIT | $ / KM | [9 empty] | KOMATSU PC 200 - 25 | PC 200-8 MO
1 | PC 400 | 24 | [9 empty] | KOMATSU PC 195 - 01 | PC 195 LC-8
2 | PC 300 | 16 | [9 empty] | KOBELCO SK 200 - 07 | SK 200-8 SX
3 | PC 200 | 8 | [9 empty] | KOBELCO SK 200 - 08 | SK 200-8 SX
4 | BULLDOZER | 16 | [9 empty] | KOBELCO SK 200 - 10 | SK 200-8 SX
5 | COMPACTOR | 8 | [9 empty] | KOBELCO SK 200 - 11 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 13 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 15 | SK 200-8 SX
| 14652.34 | [10 empty] | KOBELCO SK 200 - 16 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 18 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 19 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 20 | SK 200-8 SX
[12 empty] | KOMATSU HM 400 - 01 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 02 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 04 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 05 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 06 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 07 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 08 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 09 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 10 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 11 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 12 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 13 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 14 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 15 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 16 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 17 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 18 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 19 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 20 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 21 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 22 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 23 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 24 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 25 | HM 400-3R
[12 empty] | KOMATSU DOZER D65 - 05 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 10 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 11 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 12 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 13 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 15 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 16 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 18 | D 65 P-12
[12 empty] | KOMATSU DOZER D85SS - 11 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 14 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 17 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 18 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 20 | D 85 ESS-2
[12 empty] | GRADER GD535 - 03 | GD 511 A-1
[12 empty] | LOADER WA380 - 02 | WA 380-3
[12 empty] | SAKAI - 01 | SV 525 D
[12 empty] | SAKAI - 02 | SV 525 D
[12 empty] | SAKAI - 03 | SV 525 D
[12 empty] | SAKAI - 07 | SV 525 D
[12 empty] | LV HILUX HITAM - 05 | LV
[12 empty] | LV PAJERO PUTIH - 06 | LV
[12 empty] | LV TRITON HITAM - 08 | LV
[12 empty] | LV PAJERO PUTIH - 09 | LV
[12 empty] | LV HILUX SILVER - 10 | LV
[12 empty] | LV TRITON HITAM - 10 | LV
[12 empty] | LV TRITON PUTIH - 11 | LV
[12 empty] | LV HILUX HITAM - 11 | LV
[12 empty] | LV TRITON PUTIH - 12 | LV
[12 empty] | LV PAJERO HITAM - 15 | LV
[12 empty] | LV HILUX SILVER - 17 | LV
[12 empty] | LV HILUX HITAM - 18 | LV
[12 empty] | LV HILUX SILVER - 19 | LV
[12 empty] | LV PAJERO SILVER - 21 | LV
[12 empty] | LV HILUX PUTIH - 23 | LV
[12 empty] | LV TRITON PUTIH - 27 | LV
[12 empty] | LV LC-HIJAU - 29 | LV
[12 empty] | LV TRITON PUTIH (SAFETY) - 30 | LV
[12 empty] | LV TRITON PUTIH - 31 | LV
[12 empty] | LV TRITON PUTIH - 32 | LV
[12 empty] | MANHAUL - 02 | FM 260 Ti
[12 empty] | BUS APP - 03 | LT
[12 empty] | FUEL TRUCK - 02 | FM 260 Ti
[12 empty] | FUEL TRUCK - 03 | FM 260 Ti
[12 empty] | FUEL TRUCK - 05 | FM 260 Ti
[12 empty] | FUEL TRUCK - 06 | FM 260 Ti
[12 empty] | TRUCK WELDER - LT-04 | LT
[12 empty] | TRUCK TYRE - LT-08 | LT
[12 empty] | TRUCK MAINTENANCE - LT-09 | LT
[12 empty] | TRUCK TYRE - LT-10 | LT
MEKANIK CAMP
[12 empty] | LV TRITON PUTIH - 28 | LV
[12 empty] | TRUCK TYRE (LT-06) | LT
[12 empty] | WELDER CAR (LT-07) | LT
[12 empty] | LV HILUX MERAH - 06 | LV
[12 empty] | KOMATSU PC 400 - 07 | PC 400 LC SE-8