## SUMMARY
MINING COST (MARET)
| SUMMARY KBM BLOK B & C | Maret 2023 |  |  | CV ADIL PRIMA PERKASA
|  | PLAN | ACTUAL | ACH % | DAYS WORK |  | 31 | days
| OVERBURDEN REMOVAL | 199424.1902 | 141007.28 | 70.71% | WORKING HOUR |  | 279 | hours
| ORE MINING | 304945.5469 | 220801.4 | 72.41% | PHYSICHAL AVAILIBILITY |  | 85% | PA
| QUARRY MINING | 39884.838 | 34352.26 | 86.13%
| STRIPING RATIO | 0.65 | 0.63862 | 101.8% | Fuel Price / liter |  | 11500
| FUEL RATIO OVERALL (L/Ton) | 1.93 | 2.0214 | 95.48% | (fuel not include in contract)
| PC 500 (bcm/hour) |  |  |  | Total Fuel Consumption | PLAN | 588846.7467 | Liter
| PRODUCTION excavator | 355 | 213.9575 | 60.27% |  | ACTUAL | 446332 | Liter
[6 empty] | ACH % | 131.9%
| COST RENT + FUEL |  |  |  | COST ITEM / TON ORE
| COST OB REMOVAL | 7633760648.9457 |  |  | COST OB / TON | 35.79% | 34572.9721 | 2.3285
| COST QUARRY HAULING | 1215626563.5057 |  |  | COST QUARRY / TON | 5.699% | 5505.5202 | 0.37079
| COST DEVELOP ACT. | 112614000 |  |  | COST DEV / TON | 0.528% | 510.0239 | 0.03435
| COST ORE GETTING | 2216656000.4909 |  |  | COST ORE GETTING / TON | 10.39% | 10039.1392 | 0.67613
| COST ORE HAULING | 9946061000 |  |  | COST ORE HAULING / TON | 46.63% | 45045.2805 | 3.0338
| COST UNIT SUPPORT | 204840000 |  |  | COST SUPPORT / TON | 0.9604% | 927.7115 | 0.062481
[6 empty] | 100% | 96600.6475 | 6.506
| TOTAL COST | 21329558212.9423 |  |  | COST / TON ORE |  | 96600.6475
| INCOME | 34423821465.6 |  |  | ( USD / Ton ) |  | 6.506
[5 empty] | KURS/$ |  | 14848
| RESULT | 13094263252.6577 |  |  | PRICE / TON ORE |  | 10.5
OKE…..

## SUMMARY 2 (hidden)
MINING COST (FEBRUARY)
| SUMMARY KBM BLOK B & C | February 2023 |  | CV. ADIL PRIMA PERKASA
| WASTE REMOVAL |  | 170387.16 | DAYS WORK |  | 28
| ORE MINING |  | 220801.4 | WORKING HOUR |  | 252
| QUARRY MINING |  | 33006.63 | MECANICAL AVAILABILITY |  | 85%
| STRIPING RATIO |  | 0.77168
|  |  |  | Fuel Price / liter | Rp | 11500
| PC 500 (bcm/hour) |  |  | (fuel include in contract)
| PRODUCTION excavator |  | 1112.5468 | Total Fuel Consumption | Liter | 446332
COST RENT + FUEL
| COST OB REMOVAL | Rp | 7633760648.9457 | COST OB / TON | 35.79% | 34572.9721 | 2.3285
| COST QUARRY HAULING | Rp | 1215626563.5057 | COST QUARRY / TON | 5.699% | 5505.5202 | 0.37079
| COST DEVELOP ACT. | Rp | 112614000 | COST DEV / TON | 0.528% | 510.0239 | 0.03435
| COST ORE GETTING | Rp | 2216656000.4909 | COST ORE GETTING / TON | 10.39% | 10039.1392 | 0.67613
| COST ORE HAULING | Rp | 9946061000 | COST ORE HAULING / TON | 46.63% | 45045.2805 | 3.0338
| COST UNIT SUPPORT | Rp | 204840000 | COST SUPPORT / TON | 0.9604% | 927.7115 | 0.062481
[5 empty] | 100% | 96600.6475 | 6.506
| TOTAL COST | Rp | 21329558212.9423 | COST / TON ORE |  | 96600.6475
|  |  |  | ( USD / Ton ) |  | 6.506
| INCOME | Rp | 34423821465.6 | KURS/$ |  | 14848
|  |  |  | PRICE / TON ORE |  | 10.5
| RESULT | Rp | 13094263252.6577
OKE…..

## SUMMARY MTD
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| last year (2022) | january | february | march | april | may | june | july | august | september | october | november | december | TOTAL 2023
OVERBURDEN REMOVAL | 2593394.68 | 1 january: 162229.23; 2 february: 170387.16; 3 march: 141007.28 | 473623.67
ORE MINING | 2365922.32 | 1 january: 242547.79; 2 february: 231630.67; 3 march: 220801.4 | 694979.86
QUARRY MINING | 485042.22 | 1 january: 18017.98; 2 february: 33006.63; 3 march: 34352.26 | 85376.87
STRIPING RATIO | 1.0961 | 1 january: 0.66885; 2 february: 0.7356; 3 march: 0.63862 | 0.68149
ACH % OVERBURDEN |  | 1 january: 74.25%; 2 february: 83.77%; 3 march: 70.71% | 76.24%
ACH % ORE MINING |  | 1 january: 97.76%; 2 february: 102%; 3 march: 72.41% | 90.72%
ACH % QUARRY |  | 1 january: 41.23%; 2 february: 81.13%; 3 march: 86.13% | 69.5%
PRODUCTION excavator | 996.2529 | 1 january: 910.6566; 2 february: 1244.3993; 3 march: 213.9575 | 789.6711
COST OB REMOVAL | 117351549119.5926 | 1 january: 7778110546.1814; 2 february: 7751770028.8051; 3 march: 7633760648.9457 | 23163641223.9321
COST QUARRY HAULING | 15778967244.1131 | 1 january: 618619864.2204; 2 february: 1075055326.3787; 3 march: 1215626563.5057 | 2909301754.1048
COST DEVELOP ACT. | 279499500 | 1 january: 0; 2 february: 141737500; 3 march: 112614000 | 254351500
COST ORE GETTING | 36943314302.0272 | 1 january: 2360847500; 2 february: 2163072201.0775; 3 march: 2216656000.4909 | 6740575701.5684
COST ORE HAULING | 97545270500 | 1 january: 8362268500; 2 february: 8066319000; 3 march: 9946061000 | 26374648500
COST UNIT SUPPORT | 4177854000 | 1 january: 323262000; 2 february: 331087000; 3 march: 204840000 | 859189000
TOTAL COST | 272076454665.7328 | 1 january: 19443108410.4018; 2 february: 19529041056.2612; 3 march: 21329558212.9423 | 60301707679.6053
INCOME | 368856753377.28 | 1 january: 37814170652.16; 2 february: 36112147975.68; 3 march: 34423821465.6 | 108350140093.44
PROFIT | 96780298711.5471 | 1 january: 18371062241.7582; 2 february: 16583106919.4187; 3 march: 13094263252.6577 | 48048432413.8347
PERCENT COST | 73.76% | 1 january: 51.42%; 2 february: 54.08%; 3 march: 61.96% | 55.65%
PERCENT PROFIT | 26.24% | 1 january: 48.58%; 2 february: 45.92%; 3 march: 38.04% | 44.35%
FUEL RATIO (L/Ton) | 2.4824 | 1 january: 1.7187; 2 february: 1.9425; 3 march: 2.0214 | 1.8895
ACH % FUEL RATIO |  | 1 january: 121%; 2 february: 108.6%; 3 march: 95.48% | 108.4%
DAYS WORK | 367 | 1 january: 31; 2 february: 28; 3 march: 31 | 90
WORKING HOUR | 3303 | 1 january: 279; 2 february: 252; 3 march: 279 | 810
MECANICAL AVAILABILITY | 85% | 1 january: 85%; 2 february: 85%; 3 march: 85% | 85%
Total Fuel Consumption | 5873252.2234 | 1 january: 416876; 2 february: 449940; 3 march: 446332 | 1313148
ACH % FUEL CONSUMPTION |  | 1 january: 124%; 2 february: 106.3%; 3 march: 131.9% | 120.7%
COST / TON ORE | 1535031.7437 | 1 january: 80161.9689; 2 february: 84311.1193; 3 march: 96600.6475 | 261073.7358
( USD / Ton ) | 104.7921 | 1 january: 5.3988; 2 february: 5.6783; 3 march: 6.506 | 17.5831
NOTE
ACH % OVERBURDEN
ACH % ORE MINING | 3 hari tidak ada kegiatan, karena grade pengiriman drop
ACH % QUARRY
ACH % FUEL RATIO | terjadi penurunan dikarenakan produksi ore menurun
ACH % FUEL CONSUMPTION

## REPORT unit OB
COST UNIT OVERBURDEN
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 500 - 01 | 265.1 | 1000000 | 265100000 | 7875 | 90562500 | 29.7058 | 355662500 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 01 | K
2 | KOMATSU PC 500 - 02 | 278 | 1000000 | 278000000 | 7675.3451 | 88266468.3099 | 27.6092 | 366266468.3099 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 02 | K
3 | KOMATSU PC 500 - 03 | 255.5 | 1000000 | 255500000 | 7350.1792 | 84527060.3291 | 28.7678 | 340027060.3291 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 03 | K
4 | KOMATSU PC 500 - 04 | 21 | 1000000 | 21000000 | 660.5301 | 7596096.3855 | 31.4538 | 28596096.3855 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 04 | K
5 | KOMATSU PC 400 - 04 | 169 | 950000 | 160550000 | 5111.6256 | 58783694.5813 | 30.2463 | 219333694.5813 | kbm | PC 400 LC SE-8 | KOMATSU PC 400 - 04 | K
6 | KOMATSU PC 300 - 11 | 21 | 400000 | 8400000 | 584.7 | 6724050 | 27.8429 | 15124050 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 11 | K
7 | KOBELCO SK 330 - 11 | 35 | 400000 | 14000000 | 632.9268 | 7278658.5366 | 18.0836 | 21278658.5366 | kbm | SK 330-8 | KOBELCO SK 330 - 11 | K
8 | KOBELCO SK 200 - 15 | 7 | 275000 | 1925000 | 91.5701 | 1053056.5611 | 13.0814 | 2978056.5611 | kbm | SK 200-8 SX | KOBELCO SK 200 - 15 | K
9 | KOMATSU HM 400 - 11 | 170 | 1424304.3668 | 242131742.354 | 2876.9856 | 33085334.9282 | 16.9234 | 275217077.2823 | kbm | HM 400-3R | KOMATSU HM 400 - 11 | K
10 | KOMATSU HM 400 - 12 | 160 | 1424304.3668 | 227888698.6861 | 3421.7544 | 39350175.4386 | 21.386 | 267238874.1247 | kbm | HM 400-3R | KOMATSU HM 400 - 12 | K
11 | KOMATSU HM 400 - 13 | 51 | 1424304.3668 | 72639522.7062 | 900.8607 | 10359897.541 | 17.6639 | 82999420.2472 | kbm | HM 400-3R | KOMATSU HM 400 - 13 | K
12 | KOMATSU HM 400 - 14 | 245 | 1424304.3668 | 348954569.8632 | 4750.9888 | 54636371.2687 | 19.3918 | 403590941.1318 | kbm | HM 400-3R | KOMATSU HM 400 - 14 | K
13 | KOMATSU HM 400 - 15 | 256 | 1424304.3668 | 364621917.8978 | 5167.5152 | 59426424.2424 | 20.1856 | 424048342.1403 | kbm | HM 400-3R | KOMATSU HM 400 - 15 | K
14 | KOMATSU HM 400 - 16 | 247 | 1424304.3668 | 351803178.5967 | 5338 | 61387000 | 21.6113 | 413190178.5967 | kbm | HM 400-3R | KOMATSU HM 400 - 16 | K
15 | KOMATSU HM 400 - 17 | 177 | 1424304.3668 | 252101872.9216 | 3674.8213 | 42260444.6809 | 20.7617 | 294362317.6024 | kbm | HM 400-3R | KOMATSU HM 400 - 17 | K
16 | KOMATSU HM 400 - 18 | 176 | 1424304.3668 | 250677568.5548 | 2987.2857 | 34353785.7143 | 16.9732 | 285031354.269 | kbm | HM 400-3R | KOMATSU HM 400 - 18 | K
17 | KOMATSU HM 400 - 19 | 220 | 1424304.3668 | 313346960.6935 | 3711.0526 | 42677105.2632 | 16.8684 | 356024065.9566 | kbm | HM 400-3R | KOMATSU HM 400 - 19 | K
18 | KOMATSU HM 400 - 20 | 133 | 1424304.3668 | 189432480.7829 | 2361.6486 | 27158959.4595 | 17.7568 | 216591440.2423 | kbm | HM 400-3R | KOMATSU HM 400 - 20 | K
19 | KOMATSU HM 400 - 21 | 224 | 1424304.3668 | 319044178.1606 | 4288.3855 | 49316433.7349 | 19.1446 | 368360611.8955 | kbm | HM 400-3R | KOMATSU HM 400 - 21 | K
20 | KOMATSU HM 400 - 22 | 258.4 | 1424304.3668 | 368040248.3781 | 4626 | 53199000 | 17.9025 | 421239248.3781 | kbm | HM 400-3R | KOMATSU HM 400 - 22 | K
21 | KOMATSU HM 400 - 23 | 250 | 1424304.3668 | 356076091.6971 | 4902.1318 | 56374515.5039 | 19.6085 | 412450607.201 | kbm | HM 400-3R | KOMATSU HM 400 - 23 | K
22 | KOMATSU HM 400 - 24 | 252 | 1424304.3668 | 358924700.4307 | 4501.1077 | 51762738.4615 | 17.8615 | 410687438.8922 | kbm | HM 400-3R | KOMATSU HM 400 - 24 | K
23 | KOMATSU HM 400 - 25 | 156 | 1424304.3668 | 222191481.219 | 2396.6694 | 27561697.9592 | 15.3633 | 249753179.1782 | kbm | HM 400-3R | KOMATSU HM 400 - 25 | K
24 | KOMATSU DOZER D65 - 10 | 114 | 425000 | 48450000 | 2732 | 31418000 | 23.9649 | 79868000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 10 | K
25 | KOMATSU DOZER D65 - 13 | 249 | 425000 | 105825000 | 7063 | 81224500 | 28.3655 | 187049500 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 13 | K
26 | KOMATSU DOZER D65 - 15 | 297 | 425000 | 126225000 | 7088 | 81512000 | 23.8653 | 207737000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 15 | K
27 | KOMATSU DOZER D65 - 16 | 303 | 425000 | 128775000 | 7340 | 84410000 | 24.2244 | 213185000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 16 | K
28 | KOMATSU DOZER D65 - 18 | 256 | 425000 | 108800000 | 7355 | 84582500 | 28.7305 | 193382500 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 18 | K
29 | KOMATSU DOZER D85SS - 06 | 97 | 425000 | 41225000 | 1710.0235 | 19665269.9531 | 17.6291 | 60890269.9531 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 06 | K
30 | KOMATSU DOZER D85SS - 14 | 122 | 425000 | 51850000 | 2981.4101 | 34286216.5899 | 24.4378 | 86136216.5899 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 14 | K
31 | KOMATSU DOZER D85SS - 17 | 248 | 425000 | 105400000 | 5669.2251 | 65196088.5609 | 22.8598 | 170596088.5609 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 17 | K
32 | KOMATSU DOZER D85SS - 18 | 244 | 425000 | 103700000 | 4194 | 48231000 | 17.1885 | 151931000 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 18 | K
33 | KOMATSU DOZER D85SS - 20 | 76 | 425000 | 32300000 | 1794.208 | 20633392 | 23.608 | 52933392 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 20 | K
TOTAL |  | 6033 | 958774.7122 | 6094900212.9423 | 133813.951 | 1538860436.0034 | 22.1803 | 7633760648.9457
KURS USD | 14848
FUEL PRICE | 11500

## REPORT unit QUARRY
COST UNIT QUARRY
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 500 - 02 | 6 | 1000000 | 6000000 | 165.6549 | 1905031.6901 | 27.6092 | 7905031.6901 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 02 | K
2 | KOMATSU PC 500 - 03 | 18 | 1000000 | 18000000 | 517.8208 | 5954939.6709 | 28.7678 | 23954939.6709 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 03 | K
3 | KOMATSU PC 500 - 04 | 228 | 1000000 | 228000000 | 7171.4699 | 82471903.6145 | 31.4538 | 310471903.6145 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 04 | K
4 | KOMATSU PC 400 - 04 | 34 | 1000000 | 34000000 | 1028.3744 | 11826305.4187 | 30.2463 | 45826305.4187 | kbm | PC 500 LCE-10R | KOMATSU PC 400 - 04 | K
5 | KOMATSU PC 400 - 05 | 8 | 1000000 | 8000000 | 245 | 2817500 | 30.625 | 10817500 | kbm | PC 500 LCE-10R | KOMATSU PC 400 - 05 | K
6 | KOMATSU PC 300 - 11 | 44 | 1000000 | 44000000 | 1225.0857 | 14088485.7143 | 27.8429 | 58088485.7143 | kbm | PC 500 LCE-10R | KOMATSU PC 300 - 11 | K
7 | KOMATSU PC 300 - 14 | 10 | 1000000 | 10000000 | 277.6316 | 3192763.1579 | 27.7632 | 13192763.1579 | kbm | PC 500 LCE-10R | KOMATSU PC 300 - 14 | K
8 | KOMATSU PC 200 - 12 | 7 | 1000000 | 7000000 | 99.3144 | 1142115.7205 | 14.1878 | 8142115.7205 | kbm | PC 500 LCE-10R | KOMATSU PC 200 - 12 | K
9 | KOMATSU PC 200 - 22 | 12 | 1000000 | 12000000 | 53 | 609500 | 4.4167 | 12609500 | kbm | PC 500 LCE-10R | KOMATSU PC 200 - 22 | K
10 | KOBELCO SK 200 - 15 | 41 | 1000000 | 41000000 | 536.3394 | 6167902.7149 | 13.0814 | 47167902.7149 | kbm | PC 500 LCE-10R | KOBELCO SK 200 - 15 | K
11 | KOMATSU HM 400 - 11 | 39 | 1000000 | 39000000 | 660.0144 | 7590165.0718 | 16.9234 | 46590165.0718 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 11 | K
12 | KOMATSU HM 400 - 12 | 11 | 1000000 | 11000000 | 235.2456 | 2705324.5614 | 21.386 | 13705324.5614 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 12 | K
13 | KOMATSU HM 400 - 13 | 193 | 1000000 | 193000000 | 3409.1393 | 39205102.459 | 17.6639 | 232205102.459 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 13 | K
14 | KOMATSU HM 400 - 14 | 23 | 1000000 | 23000000 | 446.0112 | 5129128.7313 | 19.3918 | 28129128.7313 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 14 | K
15 | KOMATSU HM 400 - 15 | 8 | 1000000 | 8000000 | 161.4848 | 1857075.7576 | 20.1856 | 9857075.7576 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 15 | K
16 | KOMATSU HM 400 - 17 | 58 | 1000000 | 58000000 | 1204.1787 | 13848055.3191 | 20.7617 | 71848055.3191 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 17 | K
17 | KOMATSU HM 400 - 18 | 48 | 1000000 | 48000000 | 814.7143 | 9369214.2857 | 16.9732 | 57369214.2857 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 18 | K
18 | KOMATSU HM 400 - 19 | 8 | 1000000 | 8000000 | 134.9474 | 1551894.7368 | 16.8684 | 9551894.7368 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 19 | K
19 | KOMATSU HM 400 - 20 | 52 | 950000 | 49400000 | 923.3514 | 10618540.5405 | 17.7568 | 60018540.5405 | kbm | PC 400 LC SE-8 | KOMATSU HM 400 - 20 | K
20 | KOMATSU HM 400 - 21 | 25 | 950000 | 23750000 | 478.6145 | 5504066.2651 | 19.1446 | 29254066.2651 | kbm | PC 400 LC SE-8 | KOMATSU HM 400 - 21 | K
21 | KOMATSU HM 400 - 23 | 8 | 950000 | 7600000 | 156.8682 | 1803984.4961 | 19.6085 | 9403984.4961 | kbm | PC 400 LC SE-8 | KOMATSU HM 400 - 23 | K
22 | KOMATSU HM 400 - 24 | 8 | 950000 | 7600000 | 142.8923 | 1643261.5385 | 17.8615 | 9243261.5385 | kbm | PC 400 LC SE-8 | KOMATSU HM 400 - 24 | K
23 | KOMATSU HM 400 - 25 | 89 | 950000 | 84550000 | 1367.3306 | 15724302.0408 | 15.3633 | 100274302.0408 | kbm | PC 400 LC SE-8 | KOMATSU HM 400 - 25 | K
TOTAL |  | 978 | 989130.4348 | 968900000 | 21454.4838 | 246726563.5057 | 21.9371 | 1215626563.5057
KURS USD | 14848
FUEL PRICE | 11500

## REPORT unit DEVELOP
COST UNIT DEVELOPT
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | SAKAI - 03 | 246 | 220000 | 54120000 | 1482 | 17043000 | 6.0244 | 71163000 | kbm | SV 525 D | SAKAI - 03 | K
2 | SAKAI - 07 | 149 | 220000 | 32780000 | 754 | 8671000 | 5.0604 | 41451000 | kbm | SV 525 D | SAKAI - 07 | K
TOTAL |  | 395 | 220000 | 86900000 | 2236 | 25714000 | 5.6608 | 112614000
KURS USD | 14848
FUEL PRICE | 11500

## REPORT unit ORE GETTING
COST UNIT ORE GETTING
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 300 - 11 | 145 | 400000 | 58000000 | 4037.2143 | 46427964.2857 | 27.8429 | 104427964.2857 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 11 | K
2 | KOMATSU PC 300 - 14 | 294 | 400000 | 117600000 | 8162.3684 | 93867236.8421 | 27.7632 | 211467236.8421 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 14 | K
3 | KOMATSU PC 300 - 15 | 324 | 400000 | 129600000 | 7162 | 82363000 | 22.1049 | 211963000 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 15 | K
4 | KOBELCO SK 330 - 10 | 279 | 400000 | 111600000 | 5949 | 68413500 | 21.3226 | 180013500 | kbm | SK 330-8 | KOBELCO SK 330 - 10 | K
5 | KOBELCO SK 330 - 11 | 252 | 400000 | 100800000 | 4557.0732 | 52406341.4634 | 18.0836 | 153206341.4634 | kbm | SK 330-8 | KOBELCO SK 330 - 11 | K
6 | KOMATSU PC 200 - 12 | 222 | 275000 | 61050000 | 3149.6856 | 36221384.2795 | 14.1878 | 97271384.2795 | kbm | PC 200-8 MO | KOMATSU PC 200 - 12 | K
7 | KOMATSU PC 200 - 14 | 314 | 275000 | 86350000 | 4911 | 56476500 | 15.6401 | 142826500 | kbm | PC 200-8 MO | KOMATSU PC 200 - 14 | K
8 | KOMATSU PC 200 - 16 | 231 | 275000 | 63525000 | 3874 | 44551000 | 16.7706 | 108076000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 16 | K
9 | KOBELCO SK 200 - 07 | 132 | 275000 | 36300000 | 680 | 7820000 | 5.1515 | 44120000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 07 | K
10 | KOBELCO SK 200 - 08 | 59 | 275000 | 16225000 | 621 | 7141500 | 10.5254 | 23366500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 08 | K
11 | KOBELCO SK 200 - 10 | 196 | 275000 | 53900000 | 2915 | 33522500 | 14.8724 | 87422500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 10 | K
12 | KOBELCO SK 200 - 11 | 226 | 275000 | 62150000 | 2619 | 30118500 | 11.5885 | 92268500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 11 | K
13 | KOBELCO SK 200 - 13 | 293 | 275000 | 80575000 | 4071 | 46816500 | 13.8942 | 127391500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 13 | K
14 | KOBELCO SK 200 - 15 | 173 | 275000 | 47575000 | 2263.0905 | 26025540.724 | 13.0814 | 73600540.724 | kbm | SK 200-8 SX | KOBELCO SK 200 - 15 | K
15 | KOBELCO SK 200 - 16 | 232 | 275000 | 63800000 | 2792 | 32108000 | 12.0345 | 95908000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 16 | K
16 | KOBELCO SK 200 - 18 | 267 | 275000 | 73425000 | 2911 | 33476500 | 10.9026 | 106901500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 18 | K
17 | KOBELCO SK 200 - 20 | 183 | 275000 | 50325000 | 2539 | 29198500 | 13.8743 | 79523500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 20 | K
18 | KOMATSU DOZER D85SS - 06 | 116 | 425000 | 49300000 | 2044.9765 | 23517230.0469 | 17.6291 | 72817230.0469 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 06 | K
19 | KOMATSU DOZER D85SS - 14 | 95 | 425000 | 40375000 | 2321.5899 | 26698283.4101 | 24.4378 | 67073283.4101 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 14 | K
20 | KOMATSU DOZER D85SS - 17 | 23 | 425000 | 9775000 | 525.7749 | 6046411.4391 | 22.8598 | 15821411.4391 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 17 | K
21 | KOMATSU DOZER D85SS - 20 | 174 | 425000 | 73950000 | 4107.792 | 47239608 | 23.608 | 121189608 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 20 | K
TOTAL |  | 4230 | 333333.3333 | 1386200000 | 72213.5653 | 830456000.4909 | 17.0718 | 2216656000.4909
KURS USD | 14848
FUEL PRICE | 11500

## REPORT unit DT HAUL
COST UNIT HAULING
NO | UNIT | TONNAGE |  | RENT |  | FUEL CONSUMPTION |  | RATIO |  |  | GRAND TOTAL COST |  | DESC. | TYPE
|  | Weight Bridge |  | Rate | Total | Fuel | Total
|  | Tonnage | Retase | ($/hour) |  | (liter) |  | (liter/ton) | (ton/ret) | (liter/ret)
1 | DT HINO G 310 | 2910.01 | 62 | 500000 | 105000000 | 2849 | 32763500 | 0.97903 | 46.9356 | 45.9516 | 137763500 | 453682199.04 | ore hauling kbm | 700 Provia/12 | DT HINO G 310
2 | DT HINO G 311 | 4233.63 | 92 | 500000 | 105000000 | 4002 | 46023000 | 0.94529 | 46.0177 | 43.5 | 151023000 | 660039851.52 | ore hauling kbm | 700 Provia/12 | DT HINO G 311
3 | DT HINO G 312 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | ore hauling kbm | 700 Provia/12 | DT HINO G 312
4 | DT HINO G 313 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | ore hauling kbm | 700 Provia/12 | DT HINO G 313
5 | DT HINO G 314 | 4078.13 | 86 | 500000 | 105000000 | 4482 | 51543000 | 1.099 | 47.4201 | 52.1163 | 156543000 | 635796779.52 | ore hauling kbm | 700 Provia/12 | DT HINO G 314
6 | DT HINO G 315 | 2731.28 | 60 | 500000 | 105000000 | 3259 | 37478500 | 1.1932 | 45.5213 | 54.3167 | 142478500 | 425817477.12 | ore hauling kbm | 700 Provia/12 | DT HINO G 315
7 | DT HINO G 316 | 473.45 | 10 | 500000 | 105000000 | 258 | 2967000 | 0.54494 | 47.345 | 25.8 | 107967000 | 73812748.8 | ore hauling kbm | 700 Provia/12 | DT HINO G 316
8 | DT HINO G 317 | 4107.54 | 87 | 500000 | 105000000 | 3985 | 45827500 | 0.97017 | 47.2131 | 45.8046 | 150827500 | 640381916.16 | ore hauling kbm | 700 Provia/12 | DT HINO G 317
9 | DT HINO G 318 | 3378.72 | 73 | 500000 | 105000000 | 3284 | 37766000 | 0.97197 | 46.2838 | 44.9863 | 142766000 | 526755962.88 | ore hauling kbm | 700 Provia/12 | DT HINO G 318
10 | DT HINO G 319 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | ore hauling kbm | 700 Provia/12 | DT HINO G 319
11 | DT HINO G 320 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | ore hauling kbm | 700 Provia/12 | DT HINO G 320
12 | DT HINO G 321 | 4252.1 | 92 | 500000 | 105000000 | 4037 | 46425500 | 0.94941 | 46.2185 | 43.8804 | 151425500 | 662919398.4 | ore hauling kbm | 700 Provia/12 | DT HINO G 321
13 | DT HINO G 322 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | ore hauling kbm | 700 Provia/12 | DT HINO G 322
14 | DT HINO G 323 | 3406.2 | 72 | 500000 | 105000000 | 3272 | 37628000 | 0.9606 | 47.3083 | 45.4444 | 142628000 | 531040204.8 | ore hauling kbm | 700 Provia/12 | DT HINO G 323
15 | DT HINO G 324 | 3442.17 | 74 | 500000 | 105000000 | 3477 | 39985500 | 1.0101 | 46.5158 | 46.9865 | 144985500 | 536648071.68 | ore hauling kbm | 700 Provia/12 | DT HINO G 324
16 | DT HINO G 325 | 3541.74 | 78 | 500000 | 105000000 | 3386 | 38939000 | 0.95603 | 45.4069 | 43.4103 | 143939000 | 552171432.96 | ore hauling kbm | 700 Provia/12 | DT HINO G 325
17 | DT HINO G 326 | 2719.12 | 60 | 500000 | 105000000 | 2968 | 34132000 | 1.0915 | 45.3187 | 49.4667 | 139132000 | 423921684.48 | ore hauling kbm | 700 Provia/12 | DT HINO G 326
18 | DT HINO G 327 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | ore hauling kbm | 700 Provia/12 | DT HINO G 327
19 | DT HINO G 328 | 839.36 | 18 | 500000 | 105000000 | 588 | 6762000 | 0.70053 | 46.6311 | 32.6667 | 111762000 | 130859581.44 | ore hauling kbm | 700 Provia/12 | DT HINO G 328
20 | DT HINO G 329 | 3331.62 | 73 | 500000 | 105000000 | 3158 | 36317000 | 0.94789 | 45.6386 | 43.2603 | 141317000 | 519412884.48 | ore hauling kbm | 700 Provia/12 | DT HINO G 329
21 | DT HINO G 330 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | ore hauling kbm | 700 Provia/12 | DT HINO G 330
22 | DT HINO G 331 | 3728.57 | 79 | 500000 | 105000000 | 3619 | 41618500 | 0.97061 | 47.1971 | 45.8101 | 146618500 | 581298977.28 | ore hauling kbm | 700 Provia/12 | DT HINO G 331
23 | DT HINO G 332 | 3372.29 | 74 | 500000 | 105000000 | 3448 | 39652000 | 1.0225 | 45.5715 | 46.5946 | 144652000 | 525753500.16 | ore hauling kbm | 700 Provia/12 | DT HINO G 332
24 | DT HINO G 333 | 3296.18 | 71 | 500000 | 105000000 | 3091 | 35546500 | 0.93775 | 46.4251 | 43.5352 | 140546500 | 513887646.72 | ore hauling kbm | 700 Provia/12 | DT HINO G 333
25 | DT HINO G 334 | 3257.74 | 69 | 500000 | 105000000 | 3136 | 36064000 | 0.96263 | 47.2136 | 45.4493 | 141064000 | 507894696.96 | ore hauling kbm | 700 Provia/12 | DT HINO G 334
26 | DT HINO G 335 | 4572.44 | 98 | 500000 | 105000000 | 4804 | 55246000 | 1.0506 | 46.6576 | 49.0204 | 160246000 | 712861685.76 | ore hauling kbm | 700 Provia/12 | DT HINO G 335
27 | DT HINO G 336 | 3800.21 | 82 | 500000 | 105000000 | 3760 | 43240000 | 0.98942 | 46.344 | 45.8537 | 148240000 | 592467939.84 | ore hauling kbm | 700 Provia/12 | DT HINO G 336
28 | DT HINO G 337 | 2791.7 | 60 | 500000 | 105000000 | 2630 | 30245000 | 0.94208 | 46.5283 | 43.8333 | 135245000 | 435237196.8 | ore hauling kbm | 700 Provia/12 | DT HINO G 337
29 | DT HINO G 338 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | ore hauling kbm | 700 Provia/12 | DT HINO G 338
30 | DT HINO G 339 | 2813.55 | 61 | 500000 | 105000000 | 2938 | 33787000 | 1.0442 | 46.1238 | 48.1639 | 138787000 | 438643699.2 | ore hauling kbm | 700 Provia/12 | DT HINO G 339
31 | DT HINO G 340 | 3614.16 | 77 | 500000 | 105000000 | 3624 | 41676000 | 1.0027 | 46.9371 | 47.0649 | 146676000 | 563462000.64 | ore hauling kbm | 700 Provia/12 | DT HINO G 340
32 | DT HINO G 341 | 2717.08 | 59 | 500000 | 105000000 | 2768 | 31832000 | 1.0187 | 46.0522 | 46.9153 | 136832000 | 423603640.32 | ore hauling kbm | 700 Provia/12 | DT HINO G 341
33 | DT HINO G 342 | 2990.47 | 65 | 500000 | 105000000 | 2926 | 33649000 | 0.97844 | 46.0072 | 45.0154 | 138649000 | 466226234.88 | ore hauling kbm | 700 Provia/12 | DT HINO G 342
34 | DT HINO G 343 | 3437.39 | 73 | 500000 | 105000000 | 2994 | 34431000 | 0.87101 | 47.0875 | 41.0137 | 139431000 | 535902850.56 | ore hauling kbm | 700 Provia/12 | DT HINO G 343
35 | DT HINO G 344 | 266.45 | 6 | 500000 | 105000000 | 511 | 5876500 | 1.9178 | 44.4083 | 85.1667 | 110876500 | 41540620.8 | ore hauling kbm | 700 Provia/12 | DT HINO G 344
36 | DT HINO G 345 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | ore hauling kbm | 700 Provia/12 | DT HINO G 345
37 | DT HINO G 346 | 3361.58 | 72 | 500000 | 105000000 | 3223 | 37064500 | 0.95878 | 46.6886 | 44.7639 | 142064500 | 524083768.32 | ore hauling kbm | 700 Provia/12 | DT HINO G 346
38 | DT HINO G 347 | 5005.04 | 107 | 500000 | 105000000 | 4926 | 56649000 | 0.98421 | 46.7761 | 46.0374 | 161649000 | 780305756.16 | ore hauling kbm | 700 Provia/12 | DT HINO G 347
39 | DT HINO G 348 | 2669.72 | 58 | 500000 | 105000000 | 2555 | 29382500 | 0.95703 | 46.0297 | 44.0517 | 134382500 | 416220026.88 | ore hauling kbm | 700 Provia/12 | DT HINO G 348
40 | DT HINO G 349 | 3974.95 | 85 | 500000 | 105000000 | 3949 | 45413500 | 0.99347 | 46.7641 | 46.4588 | 150413500 | 619710604.8 | ore hauling kbm | 700 Provia/12 | DT HINO G 349
41 | DT HINO G 350 | 3441.09 | 74 | 500000 | 105000000 | 3508 | 40342000 | 1.0194 | 46.5012 | 47.4054 | 145342000 | 536479695.36 | ore hauling kbm | 700 Provia/12 | DT HINO G 350
42 | DT HINO G 351 | 2863.29 | 61 | 500000 | 105000000 | 2830 | 32545000 | 0.98837 | 46.9392 | 46.3934 | 137545000 | 446398364.16 | ore hauling kbm | 700 Provia/12 | DT HINO G 351
43 | DT HINO G 352 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | ore hauling kbm | 700 Provia/12 | DT HINO G 352
44 | DT HINO G 353 | 449.91 | 10 | 500000 | 105000000 | 606 | 6969000 | 1.3469 | 44.991 | 60.6 | 111969000 | 70142768.64 | ore hauling kbm | 700 Provia/12 | DT HINO G 353
45 | DT HINO G 354 | 4974.96 | 107 | 500000 | 105000000 | 4767 | 54820500 | 0.9582 | 46.495 | 44.5514 | 159820500 | 775616163.84 | ore hauling kbm | 700 Provia/12 | DT HINO G 354
46 | DT HINO G 355 | 4189.63 | 91 | 500000 | 105000000 | 4206 | 48369000 | 1.0039 | 46.0399 | 46.2198 | 153369000 | 653180075.52 | ore hauling kbm | 700 Provia/12 | DT HINO G 355
47 | DT HINO G 356 | 2206.01 | 47 | 500000 | 105000000 | 2152 | 24748000 | 0.97552 | 46.9364 | 45.7872 | 129748000 | 343925783.04 | ore hauling kbm | 700 Provia/12 | DT HINO G 356
48 | DT HINO G 357 | 4154.84 | 88 | 500000 | 105000000 | 3809 | 43803500 | 0.91676 | 47.2141 | 43.2841 | 148803500 | 647756175.36 | ore hauling kbm | 700 Provia/12 | DT HINO G 357
49 | DT HINO G 358 | 3436.29 | 75 | 500000 | 105000000 | 3222 | 37053000 | 0.93764 | 45.8172 | 42.96 | 142053000 | 535731356.16 | ore hauling kbm | 700 Provia/12 | DT HINO G 358
50 | DT HINO G 359 | 4887.63 | 104 | 500000 | 105000000 | 4647 | 53440500 | 0.95077 | 46.9964 | 44.6827 | 158440500 | 762001067.52 | ore hauling kbm | 700 Provia/12 | DT HINO G 359
51 | DT HINO G 360 | 3924.6 | 83 | 500000 | 105000000 | 3707 | 42630500 | 0.94455 | 47.2843 | 44.6627 | 147630500 | 611860838.4 | ore hauling kbm | 700 Provia/12 | DT HINO G 360
52 | DT HINO G 361 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | ore hauling kbm | 700 Provia/12 | DT HINO G 361
53 | DT HINO G 362 | 4741.1 | 102 | 500000 | 105000000 | 4527 | 52060500 | 0.95484 | 46.4814 | 44.3824 | 157060500 | 739156454.4 | ore hauling kbm | 700 Provia/12 | DT HINO G 362
54 | DT HINO G 363 | 3675.36 | 79 | 500000 | 105000000 | 3391 | 38996500 | 0.92263 | 46.5235 | 42.9241 | 143996500 | 573003325.44 | ore hauling kbm | 700 Provia/12 | DT HINO G 363
55 | DT HINO G 364 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | ore hauling kbm | 700 Provia/12 | DT HINO G 364
56 | DT HINO G 365 | 2032.06 | 44 | 500000 | 105000000 | 2180 | 25070000 | 1.0728 | 46.1832 | 49.5455 | 130070000 | 316806282.24 | ore hauling kbm | 700 Provia/12 | DT HINO G 365
57 | DT HINO G 366 | 2292.65 | 50 | 500000 | 105000000 | 2309 | 26553500 | 1.0071 | 45.853 | 46.18 | 131553500 | 357433305.6 | ore hauling kbm | 700 Provia/12 | DT HINO G 366
58 | DT HINO G 367 | 2394.82 | 53 | 500000 | 105000000 | 2477 | 28485500 | 1.0343 | 45.1853 | 46.7358 | 133485500 | 373362017.28 | ore hauling kbm | 700 Provia/12 | DT HINO G 367
59 | DT HINO G 368 | 2084.84 | 45 | 500000 | 105000000 | 2084 | 23966000 | 0.9996 | 46.3298 | 46.3111 | 128966000 | 325034895.36 | ore hauling kbm | 700 Provia/12 | DT HINO G 368
60 | DT HINO G 369 | 1818.72 | 40 | 500000 | 105000000 | 2006 | 23069000 | 1.103 | 45.468 | 50.15 | 128069000 | 283545722.88 | ore hauling kbm | 700 Provia/12 | DT HINO G 369
61 | DT HINO G 370 | 4759.23 | 102 | 500000 | 105000000 | 4579 | 52658500 | 0.96213 | 46.6591 | 44.8922 | 157658500 | 741982993.92 | ore hauling kbm | 700 Provia/12 | DT HINO G 370
62 | DT HINO G 371 | 4474.13 | 98 | 500000 | 105000000 | 4225 | 48587500 | 0.94432 | 45.6544 | 43.1122 | 153587500 | 697534763.52 | ore hauling kbm | 700 Provia/12 | DT HINO G 371
63 | DT HINO G 372 | 55.15 | 1 | 500000 | 105000000 | 101 | 1161500 | 1.8314 | 55.15 | 101 | 106161500 | 8598105.6 | ore hauling kbm | 700 Provia/12 | DT HINO G 372
64 | DT HINO G 373 | 4767.15 | 102 | 500000 | 105000000 | 4603 | 52934500 | 0.96557 | 46.7368 | 45.1275 | 157934500 | 743217753.6 | ore hauling kbm | 700 Provia/12 | DT HINO G 373
65 | DT HINO G 374 | 4952.16 | 106 | 500000 | 105000000 | 4541 | 52221500 | 0.91697 | 46.7185 | 42.8396 | 157221500 | 772061552.64 | ore hauling kbm | 700 Provia/12 | DT HINO G 374
66 | DT HINO G 375 | 4891.51 | 106 | 500000 | 105000000 | 4863 | 55924500 | 0.99417 | 46.1463 | 45.8774 | 160924500 | 762605975.04 | ore hauling kbm | 700 Provia/12 | DT HINO G 375
67 | DT HINO G 376 | 5320.22 | 114 | 500000 | 105000000 | 5285 | 60777500 | 0.99338 | 46.6686 | 46.3596 | 165777500 | 829443578.88 | ore hauling kbm | 700 Provia/12 | DT HINO G 376
68 | DT HINO G 377 | 4329.69 | 94 | 500000 | 105000000 | 4170 | 47955000 | 0.96312 | 46.0605 | 44.3617 | 152955000 | 675015989.76 | ore hauling kbm | 700 Provia/12 | DT HINO G 377
69 | DT HINO G 378 | 2313.77 | 49 | 500000 | 105000000 | 2130 | 24495000 | 0.92058 | 47.2198 | 43.4694 | 129495000 | 360725998.08 | ore hauling kbm | 700 Provia/12 | DT HINO G 378
70 | DT HINO G 380 | 2255.3 | 48 | 500000 | 105000000 | 2133 | 24529500 | 0.94577 | 46.9854 | 44.4375 | 129529500 | 351610291.2 | ore hauling kbm | 700 Provia/12 | DT HINO G 380
71 | DT HINO G 381 | 2084.85 | 44 | 500000 | 105000000 | 1890 | 21735000 | 0.90654 | 47.383 | 42.9545 | 126735000 | 325036454.4 | ore hauling kbm | 700 Provia/12 | DT HINO G 381
72 | DT HINO G 382 | 1989.66 | 44 | 500000 | 105000000 | 2054 | 23621000 | 1.0323 | 45.2195 | 46.6818 | 128621000 | 310195952.64 | ore hauling kbm | 700 Provia/12 | DT HINO G 382
73 | DT HINO G 383 | 2124.61 | 46 | 500000 | 105000000 | 1953 | 22459500 | 0.91923 | 46.1872 | 42.4565 | 127459500 | 331235197.44 | ore hauling kbm | 700 Provia/12 | DT HINO G 383
74 | DT HINO G 385 | 2426.91 | 52 | 500000 | 105000000 | 2446 | 28129000 | 1.0079 | 46.6713 | 47.0385 | 133129000 | 378364976.64 | ore hauling kbm | 700 Provia/12 | DT HINO G 385
75 | DT HINO G 386 | 2584.3 | 55 | 500000 | 105000000 | 2359 | 27128500 | 0.91282 | 46.9873 | 42.8909 | 132128500 | 402902707.2 | ore hauling kbm | 700 Provia/12 | DT HINO G 386
76 | DT HINO G 387 | 3082.76 | 63 | 500000 | 105000000 | 2981 | 34281500 | 0.96699 | 48.9327 | 47.3175 | 139281500 | 480614615.04 | ore hauling kbm | 700 Provia/12 | DT HINO G 387
77 | DT HINO G 388 | 2360.92 | 51 | 500000 | 105000000 | 2309 | 26553500 | 0.97801 | 46.2925 | 45.2745 | 131553500 | 368076871.68 | ore hauling kbm | 700 Provia/12 | DT HINO G 388
78 | DT HINO G 389 | 2067.9 | 43 | 500000 | 105000000 | 1844 | 21206000 | 0.89173 | 48.0907 | 42.8837 | 126206000 | 322393881.6 | ore hauling kbm | 700 Provia/12 | DT HINO G 389
79 | DT HINO G 390 | 2388.02 | 52 | 500000 | 105000000 | 2501 | 28761500 | 1.0473 | 45.9235 | 48.0962 | 133761500 | 372301870.08 | ore hauling kbm | 700 Provia/12 | DT HINO G 390
80 | DT HINO G 391 | 2172.84 | 47 | 500000 | 105000000 | 2407 | 27680500 | 1.1078 | 46.2306 | 51.2128 | 132680500 | 338754447.36 | ore hauling kbm | 700 Provia/12 | DT HINO G 391
81 | DT HINO G 392 | 2286.7 | 49 | 500000 | 105000000 | 2467 | 28370500 | 1.0788 | 46.6673 | 50.3469 | 133370500 | 356505676.8 | ore hauling kbm | 700 Provia/12 | DT HINO G 392
82 | DT HINO G 393 | 2475.2 | 54 | 500000 | 105000000 | 2641 | 30371500 | 1.067 | 45.837 | 48.9074 | 135371500 | 385893580.8 | ore hauling kbm | 700 Provia/12 | DT HINO G 393
83 | DT HINO G 394 | 1956.03 | 42 | 500000 | 105000000 | 1797 | 20665500 | 0.9187 | 46.5721 | 42.7857 | 125665500 | 304952901.12 | ore hauling kbm | 700 Provia/12 | DT HINO G 394
TOTAL |  | 220801.4 | 4748 |  | 7455000000 | 216614 | 2491061000 | 0.98104 | 46.5041 | 45.6222 | 9946061000 | 34423821465.6
HINO 700
KURS USD | 14848
FUEL PRICE | 11500
Min Charge | 210 | Hour

## REPORT unit LV & support
COST UNIT SUPPORT
NO | UNIT | RENT PER MONTH | FUEL CONSUMPTION |  | RATIO | GRAND TOTAL COST | DESC. | TYPE
|  |  | Fuel | Total
|  | (Rp/month) | (liter) |  | (liter/km)
1 | LV HILUX HITAM - 05 | 8000000 |  | 0 |  | 8000000 |  | LV | LV HILUX HITAM - 05
2 | LV PAJERO PUTIH - 06 | 8000000 |  | 0 |  | 8000000 |  | LV | LV PAJERO PUTIH - 06
3 | LV TRITON HITAM - 08 | 8000000 |  | 0 |  | 8000000 |  | LV | LV TRITON HITAM - 08
4 | LV PAJERO PUTIH - 09 | 8000000 |  | 0 |  | 8000000 |  | LV | LV PAJERO PUTIH - 09
5 | LV HILUX SILVER - 10 | 8000000 |  | 0 |  | 8000000 |  | LV | LV HILUX SILVER - 10
6 | LV TRITON HITAM - 10 | 8000000 |  | 0 |  | 8000000 |  | LV | LV TRITON HITAM - 10
7 | LV TRITON PUTIH - 11 | 8000000 |  | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 11
8 | LV HILUX HITAM - 11 | 8000000 |  | 0 |  | 8000000 |  | LV | LV HILUX HITAM - 11
9 | LV TRITON PUTIH - 12 | 8000000 |  | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 12
10 | LV HILUX SILVER - 17 | 8000000 |  | 0 |  | 8000000 |  | LV | LV HILUX SILVER - 17
11 | LV HILUX HITAM - 18 | 8000000 |  | 0 |  | 8000000 |  | LV | LV HILUX HITAM - 18
12 | LV HILUX SILVER - 19 | 8000000 |  | 0 |  | 8000000 |  | LV | LV HILUX SILVER - 19
13 | LV PAJERO SILVER - 21 | 8000000 |  | 0 |  | 8000000 |  | LV | LV PAJERO SILVER - 21
14 | LV HILUX PUTIH - 23 | 8000000 |  | 0 |  | 8000000 |  | LV | LV HILUX PUTIH - 23
15 | LV LC-SILVER - 24 | 0 |  | 0 |  | 0 |  | #N/A | LV LC-SILVER - 24
16 | LV TRITON PUTIH - 27 | 8000000 |  | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 27
17 | LV LC-HIJAU - 29 | 8000000 |  | 0 |  | 8000000 |  | LV | LV LC-HIJAU - 29
18 | LV TRITON PUTIH (SAFETY) - 30 | 8000000 |  | 0 |  | 8000000 |  | LV | LV TRITON PUTIH (SAFETY) - 30
19 | LV TRITON PUTIH - 32 | 8000000 |  | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 32
20 | MANHAUL - 02 | 210000 |  | 0 |  | 210000 |  | FM 260 Ti | MANHAUL - 02
21 | BUS APP - 03 | 12000000 |  | 0 |  | 12000000 |  | LT | BUS APP - 03
22 | FUEL TRUCK - 03 | 210000 |  | 0 |  | 210000 |  | FM 260 Ti | FUEL TRUCK - 03
23 | FUEL TRUCK - 05 | 210000 |  | 0 |  | 210000 |  | FM 260 Ti | FUEL TRUCK - 05
24 | FUEL TRUCK - 06 | 210000 |  | 0 |  | 210000 |  | FM 260 Ti | FUEL TRUCK - 06
25 | TRUCK WELDER - LT-04 | 12000000 |  | 0 |  | 12000000 |  | LT | TRUCK WELDER - LT-04
26 | TRUCK TYRE - LT-08 | 12000000 |  | 0 |  | 12000000 |  | LT | TRUCK TYRE - LT-08
27 | TRUCK MAINTENANCE - LT-09 | 12000000 |  | 0 |  | 12000000 |  | LT | TRUCK MAINTENANCE - LT-09
28 | TRUCK TYRE - LT-10 | 12000000 |  | 0 |  | 12000000 |  | LT | TRUCK TYRE - LT-10
29 | MEKANIK CAMP | 0 |  | 0 |  | 0 |  | 0 | MEKANIK CAMP
30 | Kompresor Tyre | 0 |  | 0 |  | 0 |  | 0 | Kompresor Tyre
TOTAL |  | 204840000 | 0 | 0 | 0 | 204840000
KURS USD | 14848
FUEL PRICE | 11500

## HOUR METER (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
D | NO | ID UNIT | DAYLY REPORT HM | [30 empty] | TOTAL HM | TOTAL FUEL 1- 31
N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WEEK 1 | : | 0 | DAYLY REPORT HM 22: Di setujui oleh :; DAYLY REPORT HM 29: Di buat oleh :
WEEK 2 | : | 0
WEEK 3 | : | 0
WEEK 4 | : | 0 | bar: DAYLY REPORT HM 5
WEEK 5 | : | 0 | DAYLY REPORT HM 22: Internal Kontrol; DAYLY REPORT HM 29: MPE Team
0
BENAR

## FUEL UNIT (hidden)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| D | NO | ID UNIT | DAYLY REPORT FUEL | [30 empty] | TOTAL FUEL | TOTAL HM 1- 31
| N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
SM-BW 211-02 | TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
SM-BW 211-03 | TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
| TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
SM-D85ESS-08 | TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
| TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
| TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
| TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
| TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
| TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
| TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
| ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
| ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
| ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
| ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
| ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
| ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
| ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
| DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
| DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
| DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
| DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
| DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
| TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
| TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DAYLY REPORT FUEL 30: TOTAL FUEL | 0
| WEEK 1 | : | 0 | DAYLY REPORT FUEL 22: Di setujui oleh :; DAYLY REPORT FUEL 29: Di buat oleh :
| WEEK 2 | : | 0
| WEEK 3 | : | 0
| WEEK 4 | : | 0
| WEEK 5 | : | 0 | DAYLY REPORT FUEL 22: Internal Kontrol; DAYLY REPORT FUEL 29: MPE Team
0
BENAR

## list rate unit
RATE
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | unit | type
NO | UNIT | Ltr/Hr | Rent/Hr | Column1 | Column2 | Description | Column4 | Column5 | Column6 | Column7 |  | KOMATSU PC 500 - 01 | PC 500 LCE-10R
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  | KOMATSU PC 500 - 02 | PC 500 LCE-10R
|  |  | Unit Only (Internal) | Incl. Operator | Incl. Operator & Fuel | [6 empty] | KOMATSU PC 500 - 03 | PC 500 LCE-10R
1 | PC 195 LC-8 | 20 | 16.5432 | 19.5084 | 35.3704 | Excavator | 239875.7064 | 282871.4905 | 512871.4905 | 275000 | 200 | KOMATSU PC 500 - 04 | PC 500 LCE-10R
2 | PC 200-8 MO | 22 | 23.2254 | 26.1906 | 43.6389 | Excavator | 336767.7028 | 379763.4868 | 632763.4868 | 275000 | 200 | KOMATSU PC 400 - 01 | PC 400 LC SE-8
3 | PC 300 SE-8 | 30 | 41.2152 | 44.1804 | 69.5598 | Excavator | 597620.6927 | 640616.4768 | 1008616.4768 | 400000 | 300 | KOMATSU PC 400 - 03 | PC 400 LC SE-8
4 | PC 400 LC SE-8 | 38 | 58.29 | 61.6 | 87.81 | Excavator | 845205 | 893200 | 1273245 | 950000 | 400 | KOMATSU PC 400 - 04 | PC 400 LC SE-8
5 | PC 500 LCE-10R | 45 | 63.54 | 66.85 | 98.05 | Excavator | 921330 | 969325 | 1421725 | 1000000 |  | KOMATSU PC 400 - 05 | PC 400 LC SE-8
6 | SK 200-8 SX | 20 | 17.6502 | 20.6154 | 36.4775 | Excavator | 255927.8486 | 298923.6327 | 528923.6327 | 275000 | 200 | KOMATSU PC 400 - 06 | PC 400 LC SE-8
7 | SK 330-8 | 28 | 34.235 | 37.2002 | 59.4071 | Excavator | 496407.8395 | 539403.6235 | 861403.6235 | 400000 |  | KOMATSU PC 300 - 10 | PC 300 SE-8
8 | HM 400-3R | 30 | 98.2279 | 101.5379 | 127.7104 | Artic | 1424304.3668 | 1472300.1508 | 1851800.1508 | 1424304.3668 |  | KOMATSU PC 300 - 11 | PC 300 SE-8
9 | D 85 ESS-2 | 30 | 42.331 | 45.2962 | 69.0893 | Bulldozer | 613799.3709 | 656795.155 | 1001795.155 | 425000 |  | KOMATSU PC 300 - 12 | PC 300 SE-8
10 | D 65 P-12 | 33 | 42.7792 | 45.7445 | 71.9169 | Bulldozer | 620298.906 | 663294.6901 | 1042794.6901 | 425000 |  | KOMATSU PC 300 - 14 | PC 300 SE-8
11 | GD 511 A-1 | 15 | 32.851 | 35.8163 | 47.7128 | Grader | 476340.0889 | 519335.8729 | 691835.8729 | 350000 |  | KOMATSU PC 300 - 15 | PC 300 SE-8
12 | SV 525 D | 11 | 13.1981 | 16.1633 | 24.0943 | Compactor | 191372.0947 | 234367.8788 | 349367.8788 | 220000 |  | KOMATSU PC 300 - 16 | PC 300 SE-8
13 | BW 211 D-40 | 11 | 9.9397 | 12.9049 | 20.8359 | Compactor | 144125.031 | 187120.8151 | 302120.8151 | 220000 |  | KOMATSU PC 300 - 17 | PC 300 SE-8
14 | XG 6121 | 11 | 8.6243 | 11.5895 | 19.5206 | Compactor | 125052.5178 | 168048.3018 | 283048.3018 |  |  | KOBELCO SK 330 - 10 | SK 330-8
15 | XG 955-III | 20 | 12.8699 | 15.8352 | 31.6972 | Whell Loader | 186614.0656 | 229609.8497 | 459609.8497 |  |  | KOBELCO SK 330 - 11 | SK 330-8
16 | WA 380-3 | 20 | 34.0145 | 36.9797 | 52.8418 | Whell Loader | 493209.9817 | 536205.7657 | 766205.7657 |  |  | KOMATSU PC 200 - 11 | PC 200-8 MO
17 | FM 260 Ti | 15 | 17.3403 | 18.9483 | 30.0517 | Dump Truck | 251435.0252 | 274750.1408 | 435750.1408 | 210000 |  | KOMATSU PC 200 - 12 | PC 200-8 MO
18 | 700 Provia | 20 | 31.1718 | 32.9521 | 48.8142 | Dump Truck | 451990.7019 | 477805.8175 | 707805.8175 | 460000 |  | KOMATSU PC 200 - 14 | PC 200-8 MO
19 | 700 Provia/12 | 28 | 32.42 | 34.21 | 53.52 | Dump Truck | 470090 | 496045 | 776040 | 500000 |  | KOMATSU PC 200 - 15 | PC 200-8 MO
20 | LV | 10 |  |  |  |  | 8000000 |  |  | 8000000 |  | KOMATSU PC 200 - 16 | PC 200-8 MO
21 | GENSET | 4 |  |  |  |  | 3000000 |  |  | 3000000 |  | KOMATSU PC 200 - 22 | PC 200-8 MO
22 | LT | 10 |  |  |  |  | 12000000 |  |  | 12000000 |  | KOMATSU PC 200 - 23 | PC 200-8 MO
RATE MOBILISASI | [11 empty] | KOMATSU PC 200 - 25 | PC 200-8 MO
[9 empty] | source data ( owning & operating cost) |  |  | KOMATSU PC 195 - 01 | PC 195 LC-8
NO | UNIT | $ / KM | [9 empty] | KOBELCO SK 200 - 07 | SK 200-8 SX
1 | PC 400 | 24 | [9 empty] | KOBELCO SK 200 - 08 | SK 200-8 SX
2 | PC 300 | 16 | [9 empty] | KOBELCO SK 200 - 10 | SK 200-8 SX
3 | PC 200 | 8 | [9 empty] | KOBELCO SK 200 - 11 | SK 200-8 SX
4 | BULLDOZER | 16 | [9 empty] | KOBELCO SK 200 - 13 | SK 200-8 SX
5 | COMPACTOR | 8 | [9 empty] | KOBELCO SK 200 - 15 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 16 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 18 | SK 200-8 SX
| 14652.34 | [10 empty] | KOBELCO SK 200 - 19 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 20 | SK 200-8 SX
[12 empty] | KOMATSU HM 400 - 01 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 02 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 04 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 05 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 06 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 07 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 08 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 09 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 10 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 11 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 12 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 13 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 14 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 15 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 16 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 17 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 18 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 19 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 20 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 21 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 22 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 23 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 24 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 25 | HM 400-3R
[12 empty] | KOMATSU DOZER D65 - 05 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 10 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 11 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 12 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 13 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 15 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 16 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 18 | D 65 P-12
[12 empty] | KOMATSU DOZER D85SS - 11 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 14 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 17 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 18 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 20 | D 85 ESS-2
[12 empty] | GRADER GD535 - 03 | GD 511 A-1
[12 empty] | LOADER WA380 - 02 | WA 380-3
[12 empty] | SAKAI - 02 | SV 525 D
[12 empty] | SAKAI - 03 | SV 525 D
[12 empty] | SAKAI - 07 | SV 525 D
[12 empty] | LV HILUX HITAM - 05 | LV
[12 empty] | LV PAJERO PUTIH - 06 | LV
[12 empty] | LV TRITON HITAM - 08 | LV
[12 empty] | LV PAJERO PUTIH - 09 | LV
[12 empty] | LV HILUX SILVER - 10 | LV
[12 empty] | LV TRITON HITAM - 10 | LV
[12 empty] | LV TRITON PUTIH - 11 | LV
[12 empty] | LV HILUX HITAM - 11 | LV
[12 empty] | LV TRITON PUTIH - 12 | LV
[12 empty] | LV PAJERO HITAM - 15 | LV
[12 empty] | LV HILUX SILVER - 17 | LV
[12 empty] | LV HILUX HITAM - 18 | LV
[12 empty] | LV HILUX SILVER - 19 | LV
[12 empty] | LV PAJERO SILVER - 21 | LV
[12 empty] | LV HILUX PUTIH - 23 | LV
[12 empty] | LV TRITON PUTIH - 27 | LV
[12 empty] | LV LC-HIJAU - 29 | LV
[12 empty] | LV TRITON PUTIH (SAFETY) - 30 | LV
[12 empty] | LV TRITON PUTIH - 31 | LV
[12 empty] | LV TRITON PUTIH - 32 | LV
[12 empty] | MANHAUL - 02 | FM 260 Ti
[12 empty] | BUS APP - 03 | LT
[12 empty] | FUEL TRUCK - 03 | FM 260 Ti
[12 empty] | FUEL TRUCK - 05 | FM 260 Ti
[12 empty] | FUEL TRUCK - 06 | FM 260 Ti
[12 empty] | TRUCK WELDER - LT-04 | LT
[12 empty] | TRUCK TYRE - LT-08 | LT
[12 empty] | TRUCK MAINTENANCE - LT-09 | LT
[12 empty] | TRUCK TYRE - LT-10 | LT
MEKANIK CAMP
[12 empty] | LV HILUX HITAM - 04 | LV
Kompresor Tyre
[12 empty] | KOMATSU DOZER D85SS - 06 | D 85 ESS-2