## SUMMARY
MINING COST (APRIL)
| SUMMARY KBM BLOK B & C | April 2023 |  |  | CV ADIL PRIMA PERKASA
|  | PLAN | ACTUAL | ACH % | DAYS WORK |  | 30 | days
| OVERBURDEN REMOVAL | 168615.9552 | 111460.3 | 66.1% | WORKING HOUR |  | 270 | hours
| ORE MINING | 335342.1344 | 202342.57 | 60.34% | PHYSICHAL AVAILIBILITY |  | 85% | PA
| QUARRY MINING | 33723.191 | 22346.49 | 66.26%
| STRIPING RATIO | 0.50282 | 0.55085 | 91.28% | Fuel Price / liter |  | 11500
| FUEL RATIO OVERALL (L/Ton) | 1.74 | 1.8479 | 94.16% | (fuel not include in contract)
| PC 500 (bcm/hour) |  |  |  | Total Fuel Consumption | PLAN | 583514.7075 | Liter
| PRODUCTION excavator | 355 | 182.7962 | 51.49% |  | ACTUAL | 373910 | Liter
[6 empty] | ACH % | 156.1%
| COST RENT + FUEL |  |  |  | COST ITEM / TON ORE
| COST OB REMOVAL | 5863845675.093 |  |  | COST OB / TON | 31.88% | 28979.7924 | 1.9518
| COST QUARRY HAULING | 913239430.0853 |  |  | COST QUARRY / TON | 4.965% | 4513.3332 | 0.30397
| COST DEVELOP ACT. | 50126000 |  |  | COST DEV / TON | 0.2725% | 247.7284 | 0.016684
| COST ORE GETTING | 1626803827.5208 |  |  | COST ORE GETTING / TON | 8.845% | 8039.8496 | 0.54148
| COST ORE HAULING | 9642996500 |  |  | COST ORE HAULING / TON | 52.43% | 47656.7857 | 3.2096
| COST UNIT SUPPORT | 295340000 |  |  | COST SUPPORT / TON | 1.606% | 1459.6039 | 0.098303
[6 empty] | 100% | 90897.0931 | 6.1218
| TOTAL COST | 18392351432.6991 |  |  | COST / TON ORE |  | 90897.0931
| INCOME | 31546016033.28 |  |  | ( USD / Ton ) |  | 6.1218
[5 empty] | KURS/$ |  | 14848
| RESULT | 13153664600.5809 |  |  | PRICE / TON ORE |  | 10.5
OKE…..

## SUMMARY 2 (hidden)
MINING COST (FEBRUARY)
| SUMMARY KBM BLOK B & C | February 2023 |  | CV. ADIL PRIMA PERKASA
| WASTE REMOVAL |  | 170387.16 | DAYS WORK |  | 28
| ORE MINING |  | 202342.57 | WORKING HOUR |  | 252
| QUARRY MINING |  | 33006.63 | MECANICAL AVAILABILITY |  | 85%
| STRIPING RATIO |  | 0.84207
|  |  |  | Fuel Price / liter | Rp | 11500
| PC 500 (bcm/hour) |  |  | (fuel include in contract)
| PRODUCTION excavator |  | 1298.1691 | Total Fuel Consumption | Liter | 373910
COST RENT + FUEL
| COST OB REMOVAL | Rp | 5863845675.093 | COST OB / TON | 31.88% | 28979.7924 | 1.9518
| COST QUARRY HAULING | Rp | 913239430.0853 | COST QUARRY / TON | 4.965% | 4513.3332 | 0.30397
| COST DEVELOP ACT. | Rp | 50126000 | COST DEV / TON | 0.2725% | 247.7284 | 0.016684
| COST ORE GETTING | Rp | 1626803827.5208 | COST ORE GETTING / TON | 8.845% | 8039.8496 | 0.54148
| COST ORE HAULING | Rp | 9642996500 | COST ORE HAULING / TON | 52.43% | 47656.7857 | 3.2096
| COST UNIT SUPPORT | Rp | 295340000 | COST SUPPORT / TON | 1.606% | 1459.6039 | 0.098303
[5 empty] | 100% | 90897.0931 | 6.1218
| TOTAL COST | Rp | 18392351432.6991 | COST / TON ORE |  | 90897.0931
|  |  |  | ( USD / Ton ) |  | 6.1218
| INCOME | Rp | 31546016033.28 | KURS/$ |  | 14848
|  |  |  | PRICE / TON ORE |  | 10.5
| RESULT | Rp | 13153664600.5809
OKE…..

## SUMMARY MTD
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| last year (2022) | january | february | march | april | may | june | july | august | september | october | november | december | TOTAL 2023
OVERBURDEN REMOVAL | 2593394.68 | 1 january: 162229.23; 2 february: 170387.16; 3 march: 141007.28; 4 april: 111460.3 | 585083.97
ORE MINING | 2365922.32 | 1 january: 242547.79; 2 february: 231630.67; 3 march: 220801.4; 4 april: 202342.57 | 897322.43
QUARRY MINING | 485042.22 | 1 january: 18017.98; 2 february: 33006.63; 3 march: 34352.26; 4 april: 22346.49 | 107723.36
STRIPING RATIO | 1.0961 | 1 january: 0.66885; 2 february: 0.7356; 3 march: 0.63862; 4 april: 0.55085 | 0.65203
ACH % OVERBURDEN |  | 1 january: 74.25%; 2 february: 83.77%; 3 march: 70.71%; 4 april: 66.1% | 73.71%
ACH % ORE MINING |  | 1 january: 97.76%; 2 february: 102%; 3 march: 72.41%; 4 april: 60.34% | 83.13%
ACH % QUARRY |  | 1 january: 41.23%; 2 february: 81.13%; 3 march: 86.13%; 4 april: 66.26% | 68.69%
PRODUCTION excavator | 996.2529 | 1 january: 910.6566; 2 february: 1244.3993; 3 march: 213.9575; 4 april: 182.7962 | 637.9524
COST OB REMOVAL | 117351549119.5926 | 1 january: 7778110546.1814; 2 february: 7751770028.8051; 3 march: 7633760648.9457; 4 april: 5863845675.093 | 29027486899.0251
COST QUARRY HAULING | 15778967244.1131 | 1 january: 618619864.2204; 2 february: 1075055326.3787; 3 march: 1215626563.5057; 4 april: 913239430.0853 | 3822541184.1901
COST DEVELOP ACT. | 279499500 | 1 january: 0; 2 february: 141737500; 3 march: 112614000; 4 april: 50126000 | 304477500
COST ORE GETTING | 36943314302.0272 | 1 january: 2360847500; 2 february: 2163072201.0775; 3 march: 2216656000.4909; 4 april: 1626803827.5208 | 8367379529.0893
COST ORE HAULING | 97545270500 | 1 january: 8362268500; 2 february: 8066319000; 3 march: 9946061000; 4 april: 9642996500 | 36017645000
COST UNIT SUPPORT | 4177854000 | 1 january: 323262000; 2 february: 331087000; 3 march: 204840000; 4 april: 295340000 | 1154529000
TOTAL COST | 272076454665.7328 | 1 january: 19443108410.4018; 2 february: 19529041056.2612; 3 march: 21329558212.9423; 4 april: 18392351432.6991 | 78694059112.3044
INCOME | 368856753377.28 | 1 january: 37814170652.16; 2 february: 36112147975.68; 3 march: 34423821465.6; 4 april: 31546016033.28 | 139896156126.72
PROFIT | 96780298711.5471 | 1 january: 18371062241.7582; 2 february: 16583106919.4187; 3 march: 13094263252.6577; 4 april: 13153664600.5809 | 61202097014.4156
PERCENT COST | 73.76% | 1 january: 51.42%; 2 february: 54.08%; 3 march: 61.96%; 4 april: 58.3% | 56.25%
PERCENT PROFIT | 26.24% | 1 january: 48.58%; 2 february: 45.92%; 3 march: 38.04%; 4 april: 41.7% | 43.75%
FUEL RATIO (L/Ton) | 2.4824 | 1 january: 1.7187; 2 february: 1.9425; 3 march: 2.0214; 4 april: 1.8479 | 1.8801
ACH % FUEL RATIO |  | 1 january: 121%; 2 february: 108.6%; 3 march: 95.48%; 4 april: 94.16% | 104.8%
DAYS WORK | 367 | 1 january: 31; 2 february: 28; 3 march: 31; 4 april: 30 | 120
WORKING HOUR | 3303 | 1 january: 279; 2 february: 252; 3 march: 279; 4 april: 270 | 1080
MECANICAL AVAILABILITY | 85% | 1 january: 85%; 2 february: 85%; 3 march: 85%; 4 april: 85% | 85%
Total Fuel Consumption | 5873252.2234 | 1 january: 416876; 2 february: 449940; 3 march: 446332; 4 april: 373910 | 1687058
ACH % FUEL CONSUMPTION |  | 1 january: 124%; 2 february: 106.3%; 3 march: 131.9%; 4 april: 156.1% | 129.6%
COST / TON ORE | 1535031.7437 | 1 january: 80161.9689; 2 february: 84311.1193; 3 march: 96600.6475; 4 april: 90897.0931 | 351970.8289
( USD / Ton ) | 104.7921 | 1 january: 5.3988; 2 february: 5.6783; 3 march: 6.506; 4 april: 6.1218 | 23.7049
NOTE
ACH % OVERBURDEN
ACH % ORE MINING | 3 hari tidak ada kegiatan, karena grade pengiriman drop
ACH % QUARRY
ACH % FUEL RATIO | terjadi penurunan dikarenakan produksi ore menurun
ACH % FUEL CONSUMPTION

## REPORT unit OB
COST UNIT OVERBURDEN
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 500 - 01 | 202 | 1000000 | 202000000 | 6059 | 69678500 | 29.995 | 271678500 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 01 | K
2 | KOMATSU PC 500 - 02 | 204 | 1000000 | 204000000 | 6014 | 69161000 | 29.4804 | 273161000 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 02 | K
3 | KOMATSU PC 500 - 03 | 211 | 1000000 | 211000000 | 6440.7991 | 74069189.4977 | 30.5251 | 285069189.4977 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 03 | K
4 | KOMATSU PC 500 - 04 | 115 | 1000000 | 115000000 | 3752.9909 | 43159394.9772 | 32.6347 | 158159394.9772 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 04 | K
5 | KOMATSU PC 400 - 04 | 41 | 950000 | 38950000 | 992.8881 | 11418213.2867 | 24.2168 | 50368213.2867 | kbm | PC 400 LC SE-8 | KOMATSU PC 400 - 04 | K
6 | KOMATSU PC 400 - 05 | 60 | 950000 | 57000000 | 1243.5616 | 14300958.9041 | 20.726 | 71300958.9041 | kbm | PC 400 LC SE-8 | KOMATSU PC 400 - 05 | K
7 | KOMATSU HM 400 - 11 | 88 | 1424304.3668 | 125338784.2774 | 1176.2979 | 13527425.5319 | 13.367 | 138866209.8093 | kbm | HM 400-3R | KOMATSU HM 400 - 11 | K
8 | KOMATSU HM 400 - 12 | 170 | 1424304.3668 | 242131742.354 | 2910.5789 | 33471657.8947 | 17.1211 | 275603400.2488 | kbm | HM 400-3R | KOMATSU HM 400 - 12 | K
9 | KOMATSU HM 400 - 13 | 65 | 1424304.3668 | 92579783.8412 | 1020.7796 | 11738965.0538 | 15.7043 | 104318748.895 | kbm | HM 400-3R | KOMATSU HM 400 - 13 | K
10 | KOMATSU HM 400 - 14 | 168 | 1424304.3668 | 239283133.6205 | 2487.3555 | 28604587.6777 | 14.8057 | 267887721.2982 | kbm | HM 400-3R | KOMATSU HM 400 - 14 | K
11 | KOMATSU HM 400 - 15 | 82 | 1424304.3668 | 116792958.0767 | 1150.6452 | 13232419.3548 | 14.0323 | 130025377.4315 | kbm | HM 400-3R | KOMATSU HM 400 - 15 | K
12 | KOMATSU HM 400 - 16 | 154 | 1424304.3668 | 219342872.4854 | 2403 | 27634500 | 15.6039 | 246977372.4854 | kbm | HM 400-3R | KOMATSU HM 400 - 16 | K
13 | KOMATSU HM 400 - 17 | 119 | 1424304.3668 | 169492219.6478 | 1708.2536 | 19644916.6667 | 14.3551 | 189137136.3145 | kbm | HM 400-3R | KOMATSU HM 400 - 17 | K
14 | KOMATSU HM 400 - 18 | 149 | 1424304.3668 | 212221350.6515 | 2008.7112 | 23100179.1444 | 13.4813 | 235321529.7959 | kbm | HM 400-3R | KOMATSU HM 400 - 18 | K
15 | KOMATSU HM 400 - 19 | 119 | 1424304.3668 | 169492219.6478 | 1528.7443 | 17580559.6591 | 12.8466 | 187072779.3069 | kbm | HM 400-3R | KOMATSU HM 400 - 19 | K
16 | KOMATSU HM 400 - 20 | 192 | 1424304.3668 | 273466438.4234 | 3134 | 36041000 | 16.3229 | 309507438.4234 | kbm | HM 400-3R | KOMATSU HM 400 - 20 | K
17 | KOMATSU HM 400 - 21 | 184 | 1424304.3668 | 262072003.4891 | 2659.551 | 30584836.7347 | 14.4541 | 292656840.2238 | kbm | HM 400-3R | KOMATSU HM 400 - 21 | K
18 | KOMATSU HM 400 - 22 | 190 | 1424304.3668 | 270617829.6898 | 2653 | 30509500 | 13.9632 | 301127329.6898 | kbm | HM 400-3R | KOMATSU HM 400 - 22 | K
19 | KOMATSU HM 400 - 23 | 170 | 1424304.3668 | 242131742.354 | 2704.3784 | 31100351.3514 | 15.9081 | 273232093.7054 | kbm | HM 400-3R | KOMATSU HM 400 - 23 | K
20 | KOMATSU HM 400 - 24 | 156 | 1424304.3668 | 222191481.219 | 1846 | 21229000 | 11.8333 | 243420481.219 | kbm | HM 400-3R | KOMATSU HM 400 - 24 | K
21 | KOMATSU HM 400 - 25 | 177 | 1424304.3668 | 252101872.9216 | 2211.6729 | 25434238.3178 | 12.4953 | 277536111.2393 | kbm | HM 400-3R | KOMATSU HM 400 - 25 | K
22 | KOMATSU DOZER D65 - 10 | 158 | 425000 | 67150000 | 3706 | 42619000 | 23.4557 | 109769000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 10 | K
23 | KOMATSU DOZER D65 - 13 | 205 | 425000 | 87125000 | 5856 | 67344000 | 28.5659 | 154469000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 13 | K
24 | KOMATSU DOZER D65 - 15 | 210 | 425000 | 89250000 | 5020 | 57730000 | 23.9048 | 146980000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 15 | K
25 | KOMATSU DOZER D65 - 16 | 240 | 425000 | 102000000 | 6406 | 73669000 | 26.6917 | 175669000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 16 | K
26 | KOMATSU DOZER D65 - 18 | 207 | 425000 | 87975000 | 5337 | 61375500 | 25.7826 | 149350500 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 18 | K
27 | KOMATSU DOZER D85SS - 06 | 93 | 425000 | 39525000 | 1827 | 21010500 | 19.6452 | 60535500 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 06 | K
28 | KOMATSU DOZER D85SS - 14 | 140 | 425000 | 59500000 | 2864 | 32936000 | 20.4571 | 92436000 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 14 | K
29 | KOMATSU DOZER D85SS - 17 | 212 | 425000 | 90100000 | 5331 | 61306500 | 25.1462 | 151406500 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 17 | K
30 | KOMATSU DOZER D85SS - 18 | 202 | 425000 | 85850000 | 3059 | 35178500 | 15.1436 | 121028500 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 18 | K
31 | KOMATSU DOZER D85SS - 20 | 174 | 425000 | 73950000 | 3984.6825 | 45823848.3412 | 22.9005 | 119773848.3412 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 20 | K
TOTAL |  | 4857 | 1016598.8872 | 4719631432.6991 | 99496.8906 | 1144214242.3939 | 20.4853 | 5863845675.093
KURS USD | 14848
FUEL PRICE | 11500

## REPORT unit QUARRY
COST UNIT QUARRY
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 500 - 03 | 8 | 1000000 | 8000000 | 244.2009 | 2808310.5023 | 30.5251 | 10808310.5023 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 03 | K
2 | KOMATSU PC 500 - 04 | 104 | 1000000 | 104000000 | 3394.0091 | 39031105.0228 | 32.6347 | 143031105.0228 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 04 | K
3 | KOMATSU PC 400 - 04 | 102 | 1000000 | 102000000 | 2470.1119 | 28406286.7133 | 24.2168 | 130406286.7133 | kbm | PC 500 LCE-10R | KOMATSU PC 400 - 04 | K
4 | KOMATSU PC 400 - 05 | 13 | 1000000 | 13000000 | 269.4384 | 3098541.0959 | 20.726 | 16098541.0959 | kbm | PC 500 LCE-10R | KOMATSU PC 400 - 05 | K
5 | KOMATSU PC 300 - 15 | 4 | 1000000 | 4000000 | 103.1586 | 1186324.1379 | 25.7897 | 5186324.1379 | kbm | PC 500 LCE-10R | KOMATSU PC 300 - 15 | K
6 | KOMATSU PC 200 - 22 | 51 | 1000000 | 51000000 | 517 | 5945500 | 10.1373 | 56945500 | kbm | PC 500 LCE-10R | KOMATSU PC 200 - 22 | K
7 | KOMATSU HM 400 - 11 | 100 | 1000000 | 100000000 | 1336.7021 | 15372074.4681 | 13.367 | 115372074.4681 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 11 | K
8 | KOMATSU HM 400 - 12 | 20 | 1000000 | 20000000 | 342.4211 | 3937842.1053 | 17.1211 | 23937842.1053 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 12 | K
9 | KOMATSU HM 400 - 13 | 121 | 1000000 | 121000000 | 1900.2204 | 21852534.9462 | 15.7043 | 142852534.9462 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 13 | K
10 | KOMATSU HM 400 - 14 | 43 | 1000000 | 43000000 | 636.6445 | 7321412.3223 | 14.8057 | 50321412.3223 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 14 | K
11 | KOMATSU HM 400 - 15 | 11 | 1000000 | 11000000 | 154.3548 | 1775080.6452 | 14.0323 | 12775080.6452 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 15 | K
12 | KOMATSU HM 400 - 17 | 19 | 1000000 | 19000000 | 272.7464 | 3136583.3333 | 14.3551 | 22136583.3333 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 17 | K
13 | KOMATSU HM 400 - 18 | 38 | 1000000 | 38000000 | 512.2888 | 5891320.8556 | 13.4813 | 43891320.8556 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 18 | K
14 | KOMATSU HM 400 - 19 | 57 | 1000000 | 57000000 | 732.2557 | 8420940.3409 | 12.8466 | 65420940.3409 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 19 | K
15 | KOMATSU HM 400 - 21 | 12 | 1000000 | 12000000 | 173.449 | 1994663.2653 | 14.4541 | 13994663.2653 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 21 | K
16 | KOMATSU HM 400 - 23 | 15 | 1000000 | 15000000 | 238.6216 | 2744148.6486 | 15.9081 | 17744148.6486 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 23 | K
17 | KOMATSU HM 400 - 25 | 37 | 1000000 | 37000000 | 462.3271 | 5316761.6822 | 12.4953 | 42316761.6822 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 25 | K
TOTAL |  | 755 | 1000000 | 755000000 | 13759.9504 | 158239430.0853 | 18.2251 | 913239430.0853
KURS USD | 14848
FUEL PRICE | 11500

## REPORT unit DEVELOP
COST UNIT DEVELOPT
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | SAKAI - 03 | 65 | 220000 | 14300000 | 124 | 1426000 | 1.9077 | 15726000 | kbm | SV 525 D | SAKAI - 03 | K
2 | SAKAI - 07 | 125 | 220000 | 27500000 | 600 | 6900000 | 4.8 | 34400000 | kbm | SV 525 D | SAKAI - 07 | K
TOTAL |  | 190 | 220000 | 41800000 | 724 | 8326000 | 3.8105 | 50126000
KURS USD | 14848
FUEL PRICE | 11500

## REPORT unit ORE GETTING
COST UNIT ORE GETTING
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 300 - 07 | 137 | 400000 | 54800000 | 3949 | 45413500 | 28.8248 | 100213500 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 07 | K
2 | KOMATSU PC 300 - 11 | 205 | 400000 | 82000000 | 5359 | 61628500 | 26.1415 | 143628500 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 11 | K
3 | KOMATSU PC 300 - 14 | 28 | 400000 | 11200000 | 932 | 10718000 | 33.2857 | 21918000 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 14 | K
4 | KOMATSU PC 300 - 15 | 286 | 400000 | 114400000 | 7375.8414 | 84822175.8621 | 25.7897 | 199222175.8621 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 15 | K
5 | KOBELCO SK 330 - 10 | 154 | 400000 | 61600000 | 2687 | 30900500 | 17.4481 | 92500500 | kbm | SK 330-8 | KOBELCO SK 330 - 10 | K
6 | KOBELCO SK 330 - 11 | 176 | 400000 | 70400000 | 2214 | 25461000 | 12.5795 | 95861000 | kbm | SK 330-8 | KOBELCO SK 330 - 11 | K
7 | KOBELCO SK 330 - 12 | 22 | 400000 | 8800000 | 162 | 1863000 | 7.3636 | 10663000 | kbm | SK 330-8 | KOBELCO SK 330 - 12 | K
8 | KOMATSU PC 200 - 12 | 232 | 275000 | 63800000 | 3638 | 41837000 | 15.681 | 105637000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 12 | K
9 | KOMATSU PC 200 - 14 | 260 | 275000 | 71500000 | 4381 | 50381500 | 16.85 | 121881500 | kbm | PC 200-8 MO | KOMATSU PC 200 - 14 | K
10 | KOMATSU PC 200 - 16 | 194 | 275000 | 53350000 | 3294 | 37881000 | 16.9794 | 91231000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 16 | K
11 | KOBELCO SK 200 - 07 | 68 | 275000 | 18700000 | 269 | 3093500 | 3.9559 | 21793500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 07 | K
12 | KOBELCO SK 200 - 08 | 82 | 275000 | 22550000 | 449 | 5163500 | 5.4756 | 27713500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 08 | K
13 | KOBELCO SK 200 - 10 | 245 | 275000 | 67375000 | 2730 | 31395000 | 11.1429 | 98770000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 10 | K
14 | KOBELCO SK 200 - 11 | 202 | 275000 | 55550000 | 2889 | 33223500 | 14.302 | 88773500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 11 | K
15 | KOBELCO SK 200 - 13 | 145 | 275000 | 39875000 | 1966 | 22609000 | 13.5586 | 62484000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 13 | K
16 | KOBELCO SK 200 - 15 | 190 | 275000 | 52250000 | 2797 | 32165500 | 14.7211 | 84415500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 15 | K
17 | KOBELCO SK 200 - 16 | 247 | 275000 | 67925000 | 3359 | 38628500 | 13.5992 | 106553500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 16 | K
18 | KOBELCO SK 200 - 18 | 193 | 275000 | 53075000 | 2432 | 27968000 | 12.601 | 81043000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 18 | K
19 | KOBELCO SK 200 - 20 | 118 | 275000 | 32450000 | 1268 | 14582000 | 10.7458 | 47032000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 20 | K
20 | KOMATSU DOZER D85SS - 20 | 37 | 425000 | 15725000 | 847.3175 | 9744151.6588 | 22.9005 | 25469151.6588 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 20 | K
TOTAL |  | 3221 | 326250 | 1017325000 | 52998.1589 | 609478827.5208 | 16.4539 | 1626803827.5208
KURS USD | 14848
FUEL PRICE | 11500

## REPORT unit DT HAUL
COST UNIT HAULING
NO | UNIT | TONNAGE |  | RENT |  | FUEL CONSUMPTION |  | RATIO |  |  | GRAND TOTAL COST |  | DESC. | TYPE
|  | Weight Bridge |  | Rate | Total | Fuel | Total
|  | Tonnage | Retase | ($/hour) |  | (liter) |  | (liter/ton) | (ton/ret) | (liter/ret)
1 | DT HINO G 310 | 3119.89 | 68 | 500000 | 105000000 | 3039 | 34948500 | 0.97407 | 45.8807 | 44.6912 | 139948500 | 486403330.56 | ore hauling kbm | 700 Provia/12 | DT HINO G 310
2 | DT HINO G 311 | 3981.73 | 85 | 500000 | 105000000 | 3715 | 42722500 | 0.93301 | 46.8439 | 43.7059 | 147722500 | 620767633.92 | ore hauling kbm | 700 Provia/12 | DT HINO G 311
3 | DT HINO G 314 | 3401.7 | 74 | 500000 | 105000000 | 3541 | 40721500 | 1.041 | 45.9689 | 47.8514 | 145721500 | 530338636.8 | ore hauling kbm | 700 Provia/12 | DT HINO G 314
4 | DT HINO G 315 | 1298.42 | 27 | 500000 | 105000000 | 1565 | 17997500 | 1.2053 | 48.0896 | 57.963 | 122997500 | 202428871.68 | ore hauling kbm | 700 Provia/12 | DT HINO G 315
5 | DT HINO G 317 | 2183.19 | 48 | 500000 | 105000000 | 2157 | 24805500 | 0.988 | 45.4831 | 44.9375 | 129805500 | 340368053.76 | ore hauling kbm | 700 Provia/12 | DT HINO G 317
6 | DT HINO G 318 | 1804.5 | 39 | 500000 | 105000000 | 1680 | 19320000 | 0.93101 | 46.2692 | 43.0769 | 124320000 | 281328768 | ore hauling kbm | 700 Provia/12 | DT HINO G 318
7 | DT HINO G 321 | 147.23 | 3 | 500000 | 105000000 | 363 | 4174500 | 2.4655 | 49.0767 | 121 | 109174500 | 22953745.92 | ore hauling kbm | 700 Provia/12 | DT HINO G 321
8 | DT HINO G 323 | 2765.6 | 60 | 500000 | 105000000 | 2931 | 33706500 | 1.0598 | 46.0933 | 48.85 | 138706500 | 431168102.4 | ore hauling kbm | 700 Provia/12 | DT HINO G 323
9 | DT HINO G 324 | 1945.67 | 43 | 500000 | 105000000 | 1957 | 22505500 | 1.0058 | 45.2481 | 45.5116 | 127505500 | 303337735.68 | ore hauling kbm | 700 Provia/12 | DT HINO G 324
10 | DT HINO G 325 | 2324.79 | 50 | 500000 | 105000000 | 2161 | 24851500 | 0.92955 | 46.4958 | 43.22 | 129851500 | 362444060.16 | ore hauling kbm | 700 Provia/12 | DT HINO G 325
11 | DT HINO G 326 | 2834.91 | 63 | 500000 | 105000000 | 3135 | 36052500 | 1.1059 | 44.9986 | 49.7619 | 141052500 | 441973808.64 | ore hauling kbm | 700 Provia/12 | DT HINO G 326
12 | DT HINO G 329 | 2214.26 | 48 | 500000 | 105000000 | 2114 | 24311000 | 0.95472 | 46.1304 | 44.0417 | 129311000 | 345211991.04 | ore hauling kbm | 700 Provia/12 | DT HINO G 329
13 | DT HINO G 331 | 3693.68 | 78 | 500000 | 105000000 | 3920 | 45080000 | 1.0613 | 47.3549 | 50.2564 | 150080000 | 575859486.72 | ore hauling kbm | 700 Provia/12 | DT HINO G 331
14 | DT HINO G 332 | 1364.94 | 30 | 500000 | 105000000 | 1518 | 17457000 | 1.1121 | 45.498 | 50.6 | 122457000 | 212799605.76 | ore hauling kbm | 700 Provia/12 | DT HINO G 332
15 | DT HINO G 333 | 3106.13 | 66 | 500000 | 105000000 | 3104 | 35696000 | 0.99931 | 47.0626 | 47.0303 | 140696000 | 484258091.52 | ore hauling kbm | 700 Provia/12 | DT HINO G 333
16 | DT HINO G 334 | 1662.66 | 37 | 500000 | 105000000 | 1687 | 19400500 | 1.0146 | 44.9368 | 45.5946 | 124400500 | 259215344.64 | ore hauling kbm | 700 Provia/12 | DT HINO G 334
17 | DT HINO G 335 | 2642.19 | 56 | 500000 | 105000000 | 2489 | 28623500 | 0.94202 | 47.182 | 44.4464 | 133623500 | 411927989.76 | ore hauling kbm | 700 Provia/12 | DT HINO G 335
18 | DT HINO G 336 | 2133.43 | 46 | 500000 | 105000000 | 2181 | 25081500 | 1.0223 | 46.3789 | 47.413 | 130081500 | 332610270.72 | ore hauling kbm | 700 Provia/12 | DT HINO G 336
19 | DT HINO G 337 | 876.53 | 19 | 500000 | 105000000 | 1015 | 11672500 | 1.158 | 46.1332 | 53.4211 | 116672500 | 136654533.12 | ore hauling kbm | 700 Provia/12 | DT HINO G 337
20 | DT HINO G 339 | 1910.83 | 41 | 500000 | 105000000 | 2242 | 25783000 | 1.1733 | 46.6056 | 54.6829 | 130783000 | 297906040.32 | ore hauling kbm | 700 Provia/12 | DT HINO G 339
21 | DT HINO G 340 | 2714.02 | 59 | 500000 | 105000000 | 2638 | 30337000 | 0.97199 | 46.0003 | 44.7119 | 135337000 | 423126574.08 | ore hauling kbm | 700 Provia/12 | DT HINO G 340
22 | DT HINO G 341 | 2375.54 | 51 | 500000 | 105000000 | 2183 | 25104500 | 0.91895 | 46.5792 | 42.8039 | 130104500 | 370356188.16 | ore hauling kbm | 700 Provia/12 | DT HINO G 341
23 | DT HINO G 342 | 665.86 | 14 | 500000 | 105000000 | 610 | 7015000 | 0.91611 | 47.5614 | 43.5714 | 112015000 | 103810237.44 | ore hauling kbm | 700 Provia/12 | DT HINO G 342
24 | DT HINO G 343 | 4658.87 | 100 | 500000 | 105000000 | 4405 | 50657500 | 0.94551 | 46.5887 | 44.05 | 155657500 | 726336468.48 | ore hauling kbm | 700 Provia/12 | DT HINO G 343
25 | DT HINO G 344 | 3439.18 | 75 | 500000 | 105000000 | 3557 | 40905500 | 1.0343 | 45.8557 | 47.4267 | 145905500 | 536181918.72 | ore hauling kbm | 700 Provia/12 | DT HINO G 344
26 | DT HINO G 346 | 3608.94 | 77 | 500000 | 105000000 | 3639 | 41848500 | 1.0083 | 46.8694 | 47.2597 | 146848500 | 562648181.76 | ore hauling kbm | 700 Provia/12 | DT HINO G 346
27 | DT HINO G 347 | 1812.21 | 39 | 500000 | 105000000 | 1856 | 21344000 | 1.0242 | 46.4669 | 47.5897 | 126344000 | 282530787.84 | ore hauling kbm | 700 Provia/12 | DT HINO G 347
28 | DT HINO G 348 | 2023.23 | 42 | 500000 | 105000000 | 1820 | 20930000 | 0.89955 | 48.1721 | 43.3333 | 125930000 | 315429649.92 | ore hauling kbm | 700 Provia/12 | DT HINO G 348
29 | DT HINO G 349 | 548.81 | 12 | 500000 | 105000000 | 545 | 6267500 | 0.99306 | 45.7342 | 45.4167 | 111267500 | 85561674.24 | ore hauling kbm | 700 Provia/12 | DT HINO G 349
30 | DT HINO G 350 | 3046.14 | 65 | 500000 | 105000000 | 3064 | 35236000 | 1.0059 | 46.8637 | 47.1385 | 140236000 | 474905410.56 | ore hauling kbm | 700 Provia/12 | DT HINO G 350
31 | DT HINO G 351 | 2406.48 | 52 | 500000 | 105000000 | 2411 | 27726500 | 1.0019 | 46.2785 | 46.3654 | 132726500 | 375179857.92 | ore hauling kbm | 700 Provia/12 | DT HINO G 351
32 | DT HINO G 352 | 2657.13 | 57 | 500000 | 105000000 | 2679 | 30808500 | 1.0082 | 46.6163 | 47 | 135808500 | 414257195.52 | ore hauling kbm | 700 Provia/12 | DT HINO G 352
33 | DT HINO G 353 | 2015.24 | 42 | 500000 | 105000000 | 2096 | 24104000 | 1.0401 | 47.9819 | 49.9048 | 129104000 | 314183976.96 | ore hauling kbm | 700 Provia/12 | DT HINO G 353
34 | DT HINO G 354 | 1384.37 | 29 | 500000 | 105000000 | 1241 | 14271500 | 0.89644 | 47.7369 | 42.7931 | 119271500 | 215828820.48 | ore hauling kbm | 700 Provia/12 | DT HINO G 354
35 | DT HINO G 355 | 2956.59 | 63 | 500000 | 105000000 | 2902 | 33373000 | 0.98154 | 46.93 | 46.0635 | 138373000 | 460944207.36 | ore hauling kbm | 700 Provia/12 | DT HINO G 355
36 | DT HINO G 357 | 3388.88 | 73 | 500000 | 105000000 | 3350 | 38525000 | 0.98853 | 46.423 | 45.8904 | 143525000 | 528339947.52 | ore hauling kbm | 700 Provia/12 | DT HINO G 357
37 | DT HINO G 358 | 592.14 | 13 | 500000 | 105000000 | 617 | 7095500 | 1.042 | 45.5492 | 47.4615 | 112095500 | 92316994.56 | ore hauling kbm | 700 Provia/12 | DT HINO G 358
38 | DT HINO G 359 | 3913.1 | 83 | 500000 | 105000000 | 3694 | 42481000 | 0.94401 | 47.1458 | 44.506 | 147481000 | 610067942.4 | ore hauling kbm | 700 Provia/12 | DT HINO G 359
39 | DT HINO G 360 | 2925.48 | 63 | 500000 | 105000000 | 3017 | 34695500 | 1.0313 | 46.4362 | 47.8889 | 139695500 | 456094033.92 | ore hauling kbm | 700 Provia/12 | DT HINO G 360
40 | DT HINO G 361 | 1291.71 | 28 | 500000 | 105000000 | 1487 | 17100500 | 1.1512 | 46.1325 | 53.1071 | 122100500 | 201382755.84 | ore hauling kbm | 700 Provia/12 | DT HINO G 361
41 | DT HINO G 362 | 3077.18 | 67 | 500000 | 105000000 | 3063 | 35224500 | 0.99539 | 45.9281 | 45.7164 | 140224500 | 479744670.72 | ore hauling kbm | 700 Provia/12 | DT HINO G 362
42 | DT HINO G 363 | 2931.7 | 63 | 500000 | 105000000 | 2659 | 30578500 | 0.90698 | 46.5349 | 42.2063 | 135578500 | 457063756.8 | ore hauling kbm | 700 Provia/12 | DT HINO G 363
43 | DT HINO G 365 | 2719.9 | 59 | 500000 | 105000000 | 2804 | 32246000 | 1.0309 | 46.1 | 47.5254 | 137246000 | 424043289.6 | ore hauling kbm | 700 Provia/12 | DT HINO G 365
44 | DT HINO G 366 | 3234.22 | 71 | 500000 | 105000000 | 3131 | 36006500 | 0.96809 | 45.5524 | 44.0986 | 141006500 | 504227834.88 | ore hauling kbm | 700 Provia/12 | DT HINO G 366
45 | DT HINO G 367 | 3878.28 | 86 | 500000 | 105000000 | 3761 | 43251500 | 0.96976 | 45.0963 | 43.7326 | 148251500 | 604639365.12 | ore hauling kbm | 700 Provia/12 | DT HINO G 367
46 | DT HINO G 368 | 4196.37 | 91 | 500000 | 105000000 | 3746 | 43079000 | 0.89268 | 46.114 | 41.1648 | 148079000 | 654230868.48 | ore hauling kbm | 700 Provia/12 | DT HINO G 368
47 | DT HINO G 369 | 2804.34 | 63 | 500000 | 105000000 | 2900 | 33350000 | 1.0341 | 44.5133 | 46.0317 | 138350000 | 437207823.36 | ore hauling kbm | 700 Provia/12 | DT HINO G 369
48 | DT HINO G 370 | 2647.76 | 57 | 500000 | 105000000 | 2713 | 31199500 | 1.0246 | 46.4519 | 47.5965 | 136199500 | 412796375.04 | ore hauling kbm | 700 Provia/12 | DT HINO G 370
49 | DT HINO G 371 | 3890.62 | 86 | 500000 | 105000000 | 3694 | 42481000 | 0.94946 | 45.2398 | 42.9535 | 147481000 | 606563220.48 | ore hauling kbm | 700 Provia/12 | DT HINO G 371
50 | DT HINO G 372 | 270.29 | 6 | 500000 | 105000000 | 253 | 2909500 | 0.93603 | 45.0483 | 42.1667 | 107909500 | 42139292.16 | ore hauling kbm | 700 Provia/12 | DT HINO G 372
51 | DT HINO G 373 | 4127.37 | 90 | 500000 | 105000000 | 3815 | 43872500 | 0.92432 | 45.8597 | 42.3889 | 148872500 | 643473492.48 | ore hauling kbm | 700 Provia/12 | DT HINO G 373
52 | DT HINO G 374 | 4241.75 | 91 | 500000 | 105000000 | 3986 | 45839000 | 0.93971 | 46.6126 | 43.8022 | 150839000 | 661305792 | ore hauling kbm | 700 Provia/12 | DT HINO G 374
53 | DT HINO G 375 | 3811.2 | 82 | 500000 | 105000000 | 3711 | 42676500 | 0.97371 | 46.478 | 45.2561 | 147676500 | 594181324.8 | ore hauling kbm | 700 Provia/12 | DT HINO G 375
54 | DT HINO G 376 | 4553.03 | 101 | 500000 | 105000000 | 4570 | 52555000 | 1.0037 | 45.0795 | 45.2475 | 157555000 | 709835589.12 | ore hauling kbm | 700 Provia/12 | DT HINO G 376
55 | DT HINO G 377 | 2411.87 | 54 | 500000 | 105000000 | 2392 | 27508000 | 0.99176 | 44.6643 | 44.2963 | 132508000 | 376020180.48 | ore hauling kbm | 700 Provia/12 | DT HINO G 377
56 | DT HINO G 378 | 4419.67 | 96 | 500000 | 105000000 | 4205 | 48357500 | 0.95143 | 46.0382 | 43.8021 | 153357500 | 689044231.68 | ore hauling kbm | 700 Provia/12 | DT HINO G 378
57 | DT HINO G 380 | 3728.4 | 82 | 500000 | 105000000 | 3651 | 41986500 | 0.97924 | 45.4683 | 44.5244 | 146986500 | 581272473.6 | ore hauling kbm | 700 Provia/12 | DT HINO G 380
58 | DT HINO G 381 | 3768.12 | 81 | 500000 | 105000000 | 3677 | 42285500 | 0.97582 | 46.52 | 45.3951 | 147285500 | 587464980.48 | ore hauling kbm | 700 Provia/12 | DT HINO G 381
59 | DT HINO G 382 | 1995.77 | 43 | 500000 | 105000000 | 1693 | 19469500 | 0.84829 | 46.4133 | 39.3721 | 124469500 | 311148526.08 | ore hauling kbm | 700 Provia/12 | DT HINO G 382
60 | DT HINO G 383 | 3449.78 | 76 | 500000 | 105000000 | 3351 | 38536500 | 0.97137 | 45.3918 | 44.0921 | 143536500 | 537834501.12 | ore hauling kbm | 700 Provia/12 | DT HINO G 383
61 | DT HINO G 385 | 4159.13 | 91 | 500000 | 105000000 | 3727 | 42860500 | 0.8961 | 45.7047 | 40.956 | 147860500 | 648425003.52 | ore hauling kbm | 700 Provia/12 | DT HINO G 385
62 | DT HINO G 386 | 4034.1 | 89 | 500000 | 105000000 | 3759 | 43228500 | 0.93181 | 45.327 | 42.236 | 148228500 | 628932326.4 | ore hauling kbm | 700 Provia/12 | DT HINO G 386
63 | DT HINO G 387 | 5308.85 | 108 | 500000 | 105000000 | 4684 | 53866000 | 0.8823 | 49.156 | 43.3704 | 158866000 | 827670950.4 | ore hauling kbm | 700 Provia/12 | DT HINO G 387
64 | DT HINO G 388 | 4130.18 | 91 | 500000 | 105000000 | 3972 | 45678000 | 0.9617 | 45.3866 | 43.6484 | 150678000 | 643911582.72 | ore hauling kbm | 700 Provia/12 | DT HINO G 388
65 | DT HINO G 389 | 3947.48 | 87 | 500000 | 105000000 | 4260 | 48990000 | 1.0792 | 45.3733 | 48.9655 | 153990000 | 615427921.92 | ore hauling kbm | 700 Provia/12 | DT HINO G 389
66 | DT HINO G 390 | 4528.81 | 98 | 500000 | 105000000 | 4099 | 47138500 | 0.90509 | 46.2123 | 41.8265 | 152138500 | 706059594.24 | ore hauling kbm | 700 Provia/12 | DT HINO G 390
67 | DT HINO G 391 | 4735.47 | 102 | 500000 | 105000000 | 6027 | 69310500 | 1.2727 | 46.4262 | 59.0882 | 174310500 | 738278714.88 | ore hauling kbm | 700 Provia/12 | DT HINO G 391
68 | DT HINO G 392 | 4111.87 | 91 | 500000 | 105000000 | 4012 | 46138000 | 0.97571 | 45.1854 | 44.0879 | 151138000 | 641056980.48 | ore hauling kbm | 700 Provia/12 | DT HINO G 392
69 | DT HINO G 393 | 4216.01 | 93 | 500000 | 105000000 | 3818 | 43907000 | 0.9056 | 45.3334 | 41.0538 | 148907000 | 657292823.04 | ore hauling kbm | 700 Provia/12 | DT HINO G 393
70 | DT HINO G 394 | 3176.85 | 70 | 500000 | 105000000 | 2933 | 33729500 | 0.92324 | 45.3836 | 41.9 | 138729500 | 495283622.4 | ore hauling kbm | 700 Provia/12 | DT HINO G 394
TOTAL |  | 202342.57 | 4383 |  | 7350000000 | 199391 | 2292996500 | 0.98541 | 46.1653 | 45.4919 | 9642996500 | 31546016033.28
HINO 700
KURS USD | 14848
FUEL PRICE | 11500
Min Charge | 210 | Hour

## REPORT unit LV & support
COST UNIT SUPPORT
NO | UNIT | RENT PER MONTH | FUEL CONSUMPTION |  | RATIO | GRAND TOTAL COST | DESC. | TYPE
|  |  | Fuel | Total
|  | (Rp/month) | (liter) |  | (liter/km)
1 | LV PAJERO PUTIH - 06 | 8000000 | 106 | 1219000 |  | 9219000 |  | LV | LV PAJERO PUTIH - 06
2 | LV TRITON HITAM - 08 | 8000000 | 287 | 3300500 |  | 11300500 |  | LV | LV TRITON HITAM - 08
3 | LV PAJERO PUTIH - 09 | 8000000 | 246 | 2829000 |  | 10829000 |  | LV | LV PAJERO PUTIH - 09
4 | LV HILUX SILVER - 10 | 8000000 | 256 | 2944000 |  | 10944000 |  | LV | LV HILUX SILVER - 10
5 | LV TRITON HITAM - 10 | 8000000 | 20 | 230000 |  | 8230000 |  | LV | LV TRITON HITAM - 10
6 | LV TRITON PUTIH - 11 | 8000000 | 256 | 2944000 |  | 10944000 |  | LV | LV TRITON PUTIH - 11
7 | LV TRITON PUTIH - 12 | 8000000 | 293 | 3369500 |  | 11369500 |  | LV | LV TRITON PUTIH - 12
8 | LV HILUX SILVER - 17 | 8000000 | 342 | 3933000 |  | 11933000 |  | LV | LV HILUX SILVER - 17
9 | LV HILUX HITAM - 18 | 8000000 | 77 | 885500 |  | 8885500 |  | LV | LV HILUX HITAM - 18
10 | LV HILUX SILVER - 19 | 8000000 | 218 | 2507000 |  | 10507000 |  | LV | LV HILUX SILVER - 19
11 | LV PAJERO SILVER - 21 | 8000000 | 168 | 1932000 |  | 9932000 |  | LV | LV PAJERO SILVER - 21
12 | LV HILUX PUTIH - 23 | 8000000 | 328 | 3772000 |  | 11772000 |  | LV | LV HILUX PUTIH - 23
13 | LV LC-SILVER - 24 | 8000000 | 80 | 920000 |  | 8920000 |  | LV | LV LC-SILVER - 24
14 | LV TRITON PUTIH - 27 | 8000000 | 184 | 2116000 |  | 10116000 |  | LV | LV TRITON PUTIH - 27
15 | LV LC-HIJAU - 29 | 8000000 | 140 | 1610000 |  | 9610000 |  | LV | LV LC-HIJAU - 29
16 | LV TRITON PUTIH (SAFETY) - 30 | 8000000 | 193 | 2219500 |  | 10219500 |  | LV | LV TRITON PUTIH (SAFETY) - 30
17 | LV TRITON PUTIH - 32 | 8000000 | 269 | 3093500 |  | 11093500 |  | LV | LV TRITON PUTIH - 32
18 | MANHAUL - 02 | 210000 | 860 | 9890000 |  | 10100000 |  | FM 260 Ti | MANHAUL - 02
19 | BUS APP - 03 | 12000000 | 130 | 1495000 |  | 13495000 |  | LT | BUS APP - 03
20 | FUEL TRUCK - 05 | 210000 | 1223 | 14064500 |  | 14274500 |  | FM 260 Ti | FUEL TRUCK - 05
21 | FUEL TRUCK - 06 | 210000 | 938 | 10787000 |  | 10997000 |  | FM 260 Ti | FUEL TRUCK - 06
22 | TRUCK WELDER - LT-04 | 12000000 | 52 | 598000 |  | 12598000 |  | LT | TRUCK WELDER - LT-04
23 | TRUCK TYRE - LT-08 | 12000000 | 167 | 1920500 |  | 13920500 |  | LT | TRUCK TYRE - LT-08
24 | TRUCK MAINTENANCE - LT-09 | 12000000 | 205 | 2357500 |  | 14357500 |  | LT | TRUCK MAINTENANCE - LT-09
25 | TRUCK TYRE - LT-10 | 12000000 | 213 | 2449500 |  | 14449500 |  | LT | TRUCK TYRE - LT-10
26 | MEKANIK CAMP | 0 | 212 | 2438000 |  | 2438000 |  | 0 | MEKANIK CAMP
27 | WELDER CAR | 12000000 | 21 | 241500 |  | 12241500 |  | LT | WELDER CAR
28 | Kompresor Tyre | 0 | 56 | 644000 |  | 644000 |  | 0 | Kompresor Tyre
TOTAL |  | 208630000 | 7540 | 86710000 | 0 | 295340000
KURS USD | 14848
FUEL PRICE | 11500

## HOUR METER (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
D | NO | ID UNIT | DAYLY REPORT HM | [30 empty] | TOTAL HM | TOTAL FUEL 1- 31
N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WEEK 1 | : | 0 | DAYLY REPORT HM 22: Di setujui oleh :; DAYLY REPORT HM 29: Di buat oleh :
WEEK 2 | : | 0
WEEK 3 | : | 0
WEEK 4 | : | 0 | bar: DAYLY REPORT HM 5
WEEK 5 | : | 0 | DAYLY REPORT HM 22: Internal Kontrol; DAYLY REPORT HM 29: MPE Team
0
BENAR

## FUEL UNIT (hidden)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| D | NO | ID UNIT | DAYLY REPORT FUEL | [30 empty] | TOTAL FUEL | TOTAL HM 1- 31
| N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
SM-BW 211-02 | TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
SM-BW 211-03 | TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
| TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
SM-D85ESS-08 | TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
| TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
| TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
| TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
| TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
| TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
| TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
| ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
| ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
| ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
| ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
| ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
| ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
| ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
| DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
| DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
| DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
| DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
| DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
| TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
| TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DAYLY REPORT FUEL 30: TOTAL FUEL | 0
| WEEK 1 | : | 0 | DAYLY REPORT FUEL 22: Di setujui oleh :; DAYLY REPORT FUEL 29: Di buat oleh :
| WEEK 2 | : | 0
| WEEK 3 | : | 0
| WEEK 4 | : | 0
| WEEK 5 | : | 0 | DAYLY REPORT FUEL 22: Internal Kontrol; DAYLY REPORT FUEL 29: MPE Team
0
BENAR

## list rate unit
RATE
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | unit | type
NO | UNIT | Ltr/Hr | Rent/Hr | Column1 | Column2 | Description | Column4 | Column5 | Column6 | Column7 |  | KOMATSU PC 500 - 01 | PC 500 LCE-10R
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  | KOMATSU PC 500 - 02 | PC 500 LCE-10R
|  |  | Unit Only (Internal) | Incl. Operator | Incl. Operator & Fuel | [6 empty] | KOMATSU PC 500 - 03 | PC 500 LCE-10R
1 | PC 195 LC-8 | 20 | 16.5432 | 19.5084 | 35.3704 | Excavator | 239875.7064 | 282871.4905 | 512871.4905 | 275000 | 200 | KOMATSU PC 500 - 04 | PC 500 LCE-10R
2 | PC 200-8 MO | 22 | 23.2254 | 26.1906 | 43.6389 | Excavator | 336767.7028 | 379763.4868 | 632763.4868 | 275000 | 200 | KOMATSU PC 400 - 01 | PC 400 LC SE-8
3 | PC 300 SE-8 | 30 | 41.2152 | 44.1804 | 69.5598 | Excavator | 597620.6927 | 640616.4768 | 1008616.4768 | 400000 | 300 | KOMATSU PC 400 - 03 | PC 400 LC SE-8
4 | PC 400 LC SE-8 | 38 | 58.29 | 61.6 | 87.81 | Excavator | 845205 | 893200 | 1273245 | 950000 | 400 | KOMATSU PC 400 - 04 | PC 400 LC SE-8
5 | PC 500 LCE-10R | 45 | 63.54 | 66.85 | 98.05 | Excavator | 921330 | 969325 | 1421725 | 1000000 |  | KOMATSU PC 400 - 05 | PC 400 LC SE-8
6 | SK 200-8 SX | 20 | 17.6502 | 20.6154 | 36.4775 | Excavator | 255927.8486 | 298923.6327 | 528923.6327 | 275000 | 200 | KOMATSU PC 400 - 06 | PC 400 LC SE-8
7 | SK 330-8 | 28 | 34.235 | 37.2002 | 59.4071 | Excavator | 496407.8395 | 539403.6235 | 861403.6235 | 400000 |  | KOMATSU PC 300 - 10 | PC 300 SE-8
8 | HM 400-3R | 30 | 98.2279 | 101.5379 | 127.7104 | Artic | 1424304.3668 | 1472300.1508 | 1851800.1508 | 1424304.3668 |  | KOMATSU PC 300 - 11 | PC 300 SE-8
9 | D 85 ESS-2 | 30 | 42.331 | 45.2962 | 69.0893 | Bulldozer | 613799.3709 | 656795.155 | 1001795.155 | 425000 |  | KOMATSU PC 300 - 12 | PC 300 SE-8
10 | D 65 P-12 | 33 | 42.7792 | 45.7445 | 71.9169 | Bulldozer | 620298.906 | 663294.6901 | 1042794.6901 | 425000 |  | KOMATSU PC 300 - 14 | PC 300 SE-8
11 | GD 511 A-1 | 15 | 32.851 | 35.8163 | 47.7128 | Grader | 476340.0889 | 519335.8729 | 691835.8729 | 350000 |  | KOMATSU PC 300 - 15 | PC 300 SE-8
12 | SV 525 D | 11 | 13.1981 | 16.1633 | 24.0943 | Compactor | 191372.0947 | 234367.8788 | 349367.8788 | 220000 |  | KOMATSU PC 300 - 16 | PC 300 SE-8
13 | BW 211 D-40 | 11 | 9.9397 | 12.9049 | 20.8359 | Compactor | 144125.031 | 187120.8151 | 302120.8151 | 220000 |  | KOMATSU PC 300 - 17 | PC 300 SE-8
14 | XG 6121 | 11 | 8.6243 | 11.5895 | 19.5206 | Compactor | 125052.5178 | 168048.3018 | 283048.3018 |  |  | KOBELCO SK 330 - 10 | SK 330-8
15 | XG 955-III | 20 | 12.8699 | 15.8352 | 31.6972 | Whell Loader | 186614.0656 | 229609.8497 | 459609.8497 |  |  | KOBELCO SK 330 - 11 | SK 330-8
16 | WA 380-3 | 20 | 34.0145 | 36.9797 | 52.8418 | Whell Loader | 493209.9817 | 536205.7657 | 766205.7657 |  |  | KOMATSU PC 200 - 11 | PC 200-8 MO
17 | FM 260 Ti | 15 | 17.3403 | 18.9483 | 30.0517 | Dump Truck | 251435.0252 | 274750.1408 | 435750.1408 | 210000 |  | KOMATSU PC 200 - 12 | PC 200-8 MO
18 | 700 Provia | 20 | 31.1718 | 32.9521 | 48.8142 | Dump Truck | 451990.7019 | 477805.8175 | 707805.8175 | 460000 |  | KOMATSU PC 200 - 14 | PC 200-8 MO
19 | 700 Provia/12 | 28 | 32.42 | 34.21 | 53.52 | Dump Truck | 470090 | 496045 | 776040 | 500000 |  | KOMATSU PC 200 - 15 | PC 200-8 MO
20 | LV | 10 |  |  |  |  | 8000000 |  |  | 8000000 |  | KOMATSU PC 200 - 16 | PC 200-8 MO
21 | GENSET | 4 |  |  |  |  | 3000000 |  |  | 3000000 |  | KOMATSU PC 200 - 22 | PC 200-8 MO
22 | LT | 10 |  |  |  |  | 12000000 |  |  | 12000000 |  | KOMATSU PC 200 - 23 | PC 200-8 MO
RATE MOBILISASI | [11 empty] | KOMATSU PC 200 - 25 | PC 200-8 MO
[9 empty] | source data ( owning & operating cost) |  |  | KOMATSU PC 195 - 01 | PC 195 LC-8
NO | UNIT | $ / KM | [9 empty] | KOBELCO SK 200 - 07 | SK 200-8 SX
1 | PC 400 | 24 | [9 empty] | KOBELCO SK 200 - 08 | SK 200-8 SX
2 | PC 300 | 16 | [9 empty] | KOBELCO SK 200 - 10 | SK 200-8 SX
3 | PC 200 | 8 | [9 empty] | KOBELCO SK 200 - 11 | SK 200-8 SX
4 | BULLDOZER | 16 | [9 empty] | KOBELCO SK 200 - 13 | SK 200-8 SX
5 | COMPACTOR | 8 | [9 empty] | KOBELCO SK 200 - 15 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 16 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 18 | SK 200-8 SX
| 14652.34 | [10 empty] | KOBELCO SK 200 - 19 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 20 | SK 200-8 SX
[12 empty] | KOMATSU HM 400 - 01 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 02 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 04 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 05 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 06 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 07 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 08 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 09 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 10 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 11 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 12 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 13 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 14 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 15 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 16 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 17 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 18 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 19 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 20 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 21 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 22 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 23 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 24 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 25 | HM 400-3R
[12 empty] | KOMATSU DOZER D65 - 05 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 10 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 11 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 12 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 13 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 15 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 16 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 18 | D 65 P-12
[12 empty] | KOMATSU DOZER D85SS - 11 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 14 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 17 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 18 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 20 | D 85 ESS-2
[12 empty] | GRADER GD535 - 03 | GD 511 A-1
[12 empty] | LOADER WA380 - 02 | WA 380-3
[12 empty] | SAKAI - 02 | SV 525 D
[12 empty] | SAKAI - 03 | SV 525 D
[12 empty] | SAKAI - 07 | SV 525 D
[12 empty] | LV HILUX HITAM - 05 | LV
[12 empty] | LV PAJERO PUTIH - 06 | LV
[12 empty] | LV TRITON HITAM - 08 | LV
[12 empty] | LV PAJERO PUTIH - 09 | LV
[12 empty] | LV HILUX SILVER - 10 | LV
[12 empty] | LV TRITON HITAM - 10 | LV
[12 empty] | LV TRITON PUTIH - 11 | LV
[12 empty] | LV HILUX HITAM - 11 | LV
[12 empty] | LV TRITON PUTIH - 12 | LV
[12 empty] | LV PAJERO HITAM - 15 | LV
[12 empty] | LV HILUX SILVER - 17 | LV
[12 empty] | LV HILUX HITAM - 18 | LV
[12 empty] | LV HILUX SILVER - 19 | LV
[12 empty] | LV PAJERO SILVER - 21 | LV
[12 empty] | LV HILUX PUTIH - 23 | LV
[12 empty] | LV TRITON PUTIH - 27 | LV
[12 empty] | LV LC-HIJAU - 29 | LV
[12 empty] | LV TRITON PUTIH (SAFETY) - 30 | LV
[12 empty] | LV TRITON PUTIH - 31 | LV
[12 empty] | LV TRITON PUTIH - 32 | LV
[12 empty] | MANHAUL - 02 | FM 260 Ti
[12 empty] | BUS APP - 03 | LT
[12 empty] | FUEL TRUCK - 03 | FM 260 Ti
[12 empty] | FUEL TRUCK - 05 | FM 260 Ti
[12 empty] | FUEL TRUCK - 06 | FM 260 Ti
[12 empty] | TRUCK WELDER - LT-04 | LT
[12 empty] | TRUCK TYRE - LT-08 | LT
[12 empty] | TRUCK MAINTENANCE - LT-09 | LT
[12 empty] | TRUCK TYRE - LT-10 | LT
MEKANIK CAMP
[12 empty] | LV HILUX HITAM - 04 | LV
Kompresor Tyre
[12 empty] | KOMATSU DOZER D85SS - 06 | D 85 ESS-2
[12 empty] | KOMATSU PC 300 - 07 | PC 300 SE-8
[12 empty] | KOBELCO SK 330 - 12 | SK 330-8
[12 empty] | LV LC-SILVER - 24 | LV
[12 empty] | WELDER CAR | LT