## SUMMARY
MINING COST (MEI)
| SUMMARY KBM BLOK B & C | Mei 2023 |  |  | CV ADIL PRIMA PERKASA
|  | PLAN | ACTUAL | ACH % | DAYS WORK |  | 31 | days
| OVERBURDEN REMOVAL | 175369.4976 | 111460.3 | 63.56% | WORKING HOUR |  | 279 | hours
| ORE MINING | 302902.5158 | 204340.21 | 67.46% | PHYSICHAL AVAILIBILITY |  | 85% | PA
| QUARRY MINING | 21044.3397 | 22346.49 | 106.2%
| STRIPING RATIO | 0.57896 | 0.54546 | 106.1% | Fuel Price / liter |  | 11500
| FUEL RATIO OVERALL (L/Ton) | 2.19 | 1.9933 | 109.9% | (fuel not include in contract)
| ADT HM 400 (bcm/hour) |  |  |  | Total Fuel Consumption | PLAN | 596024.1564 | Liter
| PRODUCTION hauler | 80 | 43.0662 | 53.83% |  | ACTUAL | 407315.8102 | Liter
[6 empty] | ACH % | 146.3%
| COST RENT + FUEL |  |  |  | COST ITEM / TON ORE
| COST OB REMOVAL | 7157900981.7813 |  |  | COST OB / TON | 35.62% | 35029.3316 | 2.3592
| COST QUARRY HAULING | 1072130001.1488 |  |  | COST QUARRY / TON | 5.335% | 5246.7892 | 0.35337
| COST DEVELOP ACT. | 0 |  |  | COST DEV / TON | 0% | 0 | 0
| COST ORE GETTING | 2197725538.0117 |  |  | COST ORE GETTING / TON | 10.94% | 10755.228 | 0.72436
| COST ORE HAULING | 9457370000 |  |  | COST ORE HAULING / TON | 47.06% | 46282.4718 | 3.1171
| COST UNIT SUPPORT | 212630000 |  |  | COST SUPPORT / TON | 1.058% | 1040.5686 | 0.070081
[6 empty] | 100% | 98354.3891 | 6.6241
| TOTAL COST | 20097756520.9418 |  |  | COST / TON ORE |  | 98354.3891
| INCOME | 31857456099.84 |  |  | ( USD / Ton ) |  | 6.6241
[5 empty] | KURS/$ |  | 14848
| RESULT | 11759699578.8982 |  |  | PRICE / TON ORE |  | 10.5
OKE…..

## SUMMARY 2 (hidden)
MINING COST (FEBRUARY)
| SUMMARY KBM BLOK B & C | February 2023 |  | CV. ADIL PRIMA PERKASA
| WASTE REMOVAL |  | 170387.16 | DAYS WORK |  | 28
| ORE MINING |  | 204340.21 | WORKING HOUR |  | 252
| QUARRY MINING |  | 33006.63 | MECANICAL AVAILABILITY |  | 85%
| STRIPING RATIO |  | 0.83384
|  |  |  | Fuel Price / liter | Rp | 11500
| PC 500 (bcm/hour) |  |  | (fuel include in contract)
| PRODUCTION excavator |  | 1014.5201 | Total Fuel Consumption | Liter | 407315.8102
COST RENT + FUEL
| COST OB REMOVAL | Rp | 7157900981.7813 | COST OB / TON | 35.62% | 35029.3316 | 2.3592
| COST QUARRY HAULING | Rp | 1072130001.1488 | COST QUARRY / TON | 5.335% | 5246.7892 | 0.35337
| COST DEVELOP ACT. | Rp | 0 | COST DEV / TON | 0% | 0 | 0
| COST ORE GETTING | Rp | 2197725538.0117 | COST ORE GETTING / TON | 10.94% | 10755.228 | 0.72436
| COST ORE HAULING | Rp | 9457370000 | COST ORE HAULING / TON | 47.06% | 46282.4718 | 3.1171
| COST UNIT SUPPORT | Rp | 212630000 | COST SUPPORT / TON | 1.058% | 1040.5686 | 0.070081
[5 empty] | 100% | 98354.3891 | 6.6241
| TOTAL COST | Rp | 20097756520.9418 | COST / TON ORE |  | 98354.3891
|  |  |  | ( USD / Ton ) |  | 6.6241
| INCOME | Rp | 31857456099.84 | KURS/$ |  | 14848
|  |  |  | PRICE / TON ORE |  | 10.5
| RESULT | Rp | 11759699578.8982
OKE…..

## SUMMARY MTD
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| last year (2022) | january | february | march | april | may | june | july | august | september | october | november | december | TOTAL 2023
OVERBURDEN REMOVAL | 2593394.68 | 1 january: 162229.23; 2 february: 170387.16; 3 march: 141007.28; 4 april: 111460.3; 5 may: 111460.3 | 696544.27
ORE MINING | 2365922.32 | 1 january: 242547.79; 2 february: 231630.67; 3 march: 220801.4; 4 april: 202342.57; 5 may: 204340.21 | 1101662.64
QUARRY MINING | 485042.22 | 1 january: 18017.98; 2 february: 33006.63; 3 march: 34352.26; 4 april: 22346.49; 5 may: 22346.49 | 130069.85
STRIPING RATIO | 1.0961 | 1 january: 0.66885; 2 february: 0.7356; 3 march: 0.63862; 4 april: 0.55085; 5 may: 0.54546 | 0.63227
ACH % OVERBURDEN |  | 1 january: 74.25%; 2 february: 83.77%; 3 march: 70.71%; 4 april: 66.1%; 5 may: 63.56% | 71.68%
ACH % ORE MINING |  | 1 january: 97.76%; 2 february: 102%; 3 march: 72.41%; 4 april: 60.34%; 5 may: 67.46% | 79.99%
ACH % QUARRY |  | 1 january: 41.23%; 2 february: 81.13%; 3 march: 86.13%; 4 april: 66.26%; 5 may: 106.2% | 76.19%
PRODUCTION excavator | 996.2529 | 1 january: 910.6566; 2 february: 1244.3993; 3 march: 213.9575; 4 april: 182.7962; 5 may: 43.0662 | 518.9752
COST OB REMOVAL | 117351549119.5926 | 1 january: 7778110546.1814; 2 february: 7751770028.8051; 3 march: 7633760648.9457; 4 april: 5863845675.093; 5 may: 7157900981.7813 | 36185387880.8064
COST QUARRY HAULING | 15778967244.1131 | 1 january: 618619864.2204; 2 february: 1075055326.3787; 3 march: 1215626563.5057; 4 april: 913239430.0853; 5 may: 1072130001.1488 | 4894671185.3389
COST DEVELOP ACT. | 279499500 | 1 january: 0; 2 february: 141737500; 3 march: 112614000; 4 april: 50126000; 5 may: 0 | 304477500
COST ORE GETTING | 36943314302.0272 | 1 january: 2360847500; 2 february: 2163072201.0775; 3 march: 2216656000.4909; 4 april: 1626803827.5208; 5 may: 2197725538.0117 | 10565105067.101
COST ORE HAULING | 97545270500 | 1 january: 8362268500; 2 february: 8066319000; 3 march: 9946061000; 4 april: 9642996500; 5 may: 9457370000 | 45475015000
COST UNIT SUPPORT | 4177854000 | 1 january: 323262000; 2 february: 331087000; 3 march: 204840000; 4 april: 295340000; 5 may: 212630000 | 1367159000
TOTAL COST | 272076454665.7328 | 1 january: 19443108410.4018; 2 february: 19529041056.2612; 3 march: 21329558212.9423; 4 april: 18392351432.6991; 5 may: 20097756520.9418 | 98791815633.2462
INCOME | 368856753377.28 | 1 january: 37814170652.16; 2 february: 36112147975.68; 3 march: 34423821465.6; 4 april: 31546016033.28; 5 may: 31857456099.84 | 171753612226.56
PROFIT | 96780298711.5471 | 1 january: 18371062241.7582; 2 february: 16583106919.4187; 3 march: 13094263252.6577; 4 april: 13153664600.5809; 5 may: 11759699578.8982 | 72961796593.3138
PERCENT COST | 73.76% | 1 january: 51.42%; 2 february: 54.08%; 3 march: 61.96%; 4 april: 58.3%; 5 may: 63.09% | 57.52%
PERCENT PROFIT | 26.24% | 1 january: 48.58%; 2 february: 45.92%; 3 march: 38.04%; 4 april: 41.7%; 5 may: 36.91% | 42.48%
FUEL RATIO (L/Ton) | 2.4824 | 1 january: 1.7187; 2 february: 1.9425; 3 march: 2.0214; 4 april: 1.8479; 5 may: 1.9933 | 1.9011
ACH % FUEL RATIO |  | 1 january: 121%; 2 february: 108.6%; 3 march: 95.48%; 4 april: 94.16%; 5 may: 109.9% | 105.8%
DAYS WORK | 367 | 1 january: 31; 2 february: 28; 3 march: 31; 4 april: 30; 5 may: 31 | 151
WORKING HOUR | 3303 | 1 january: 279; 2 february: 252; 3 march: 279; 4 april: 270; 5 may: 279 | 1359
MECANICAL AVAILABILITY | 85% | 1 january: 85%; 2 february: 85%; 3 march: 85%; 4 april: 85%; 5 may: 85% | 85%
Total Fuel Consumption | 5873252.2234 | 1 january: 416876; 2 february: 449940; 3 march: 446332; 4 april: 373910; 5 may: 407315.8102 | 2094373.8102
ACH % FUEL CONSUMPTION |  | 1 january: 124%; 2 february: 106.3%; 3 march: 131.9%; 4 april: 156.1%; 5 may: 146.3% | 132.9%
COST / TON ORE | 1535031.7437 | 1 january: 80161.9689; 2 february: 84311.1193; 3 march: 96600.6475; 4 april: 90897.0931; 5 may: 98354.3891 | 450325.218
( USD / Ton ) | 104.7921 | 1 january: 5.3988; 2 february: 5.6783; 3 march: 6.506; 4 april: 6.1218; 5 may: 6.6241 | 30.329
NOTE
ACH % OVERBURDEN
ACH % ORE MINING | 3 hari tidak ada kegiatan, karena grade pengiriman drop
ACH % QUARRY
ACH % FUEL RATIO | terjadi penurunan dikarenakan produksi ore menurun
ACH % FUEL CONSUMPTION

## REPORT unit OB
COST UNIT OVERBURDEN
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 500 - 01 | 238 | 1000000 | 238000000 | 7442.0402 | 85583461.8474 | 31.2691 | 323583461.8474 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 01 | K
2 | KOMATSU PC 500 - 02 | 256 | 1000000 | 256000000 | 6640 | 76360000 | 25.9375 | 332360000 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 02 | K
3 | KOMATSU PC 500 - 03 | 262 | 1000000 | 262000000 | 7223.3015 | 83067966.9118 | 27.5699 | 345067966.9118 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 03 | K
4 | KOMATSU PC 500 - 04 | 225 | 1000000 | 225000000 | 7151.2357 | 82239211.0266 | 31.7833 | 307239211.0266 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 04 | K
5 | KOMATSU HM 400 - 11 | 123 | 1424304.3668 | 175189437.115 | 2339.3354 | 26902357.5949 | 19.019 | 202091794.7099 | kbm | HM 400-3R | KOMATSU HM 400 - 11 | K
6 | KOMATSU HM 400 - 12 | 241 | 1424304.3668 | 343257352.396 | 4109 | 47253500 | 17.0498 | 390510852.396 | kbm | HM 400-3R | KOMATSU HM 400 - 12 | K
7 | KOMATSU HM 400 - 13 | 162 | 1424304.3668 | 230737307.4197 | 2846.3226 | 32732709.6774 | 17.5699 | 263470017.0971 | kbm | HM 400-3R | KOMATSU HM 400 - 13 | K
8 | KOMATSU HM 400 - 14 | 201 | 1424304.3668 | 286285177.7245 | 4102.1394 | 47174603.3654 | 20.4087 | 333459781.0899 | kbm | HM 400-3R | KOMATSU HM 400 - 14 | K
9 | KOMATSU HM 400 - 15 | 177 | 1424304.3668 | 252101872.9216 | 3422 | 39353000 | 19.3333 | 291454872.9216 | kbm | HM 400-3R | KOMATSU HM 400 - 15 | K
10 | KOMATSU HM 400 - 16 | 97 | 1424304.3668 | 138157523.5785 | 2019.7556 | 23227188.8889 | 20.8222 | 161384712.4674 | kbm | HM 400-3R | KOMATSU HM 400 - 16 | K
11 | KOMATSU HM 400 - 17 | 163 | 1424304.3668 | 232161611.7865 | 2907 | 33430500 | 17.8344 | 265592111.7865 | kbm | HM 400-3R | KOMATSU HM 400 - 17 | K
12 | KOMATSU HM 400 - 18 | 238 | 1424304.3668 | 338984439.2956 | 4754.3108 | 54674573.7052 | 19.9761 | 393659013.0008 | kbm | HM 400-3R | KOMATSU HM 400 - 18 | K
13 | KOMATSU HM 400 - 19 | 182 | 1424304.3668 | 259223394.7555 | 3621.1724 | 41643482.7586 | 19.8966 | 300866877.5141 | kbm | HM 400-3R | KOMATSU HM 400 - 19 | K
14 | KOMATSU HM 400 - 20 | 156 | 1424304.3668 | 222191481.219 | 3016 | 34684000 | 19.3333 | 256875481.219 | kbm | HM 400-3R | KOMATSU HM 400 - 20 | K
15 | KOMATSU HM 400 - 21 | 111 | 1424304.3668 | 158097784.7135 | 1597.557 | 18371905.0633 | 14.3924 | 176469689.7768 | kbm | HM 400-3R | KOMATSU HM 400 - 21 | K
16 | KOMATSU HM 400 - 22 | 157 | 1424304.3668 | 223615785.5858 | 3290.5479 | 37841301.3699 | 20.9589 | 261457086.9556 | kbm | HM 400-3R | KOMATSU HM 400 - 22 | K
17 | KOMATSU HM 400 - 23 | 237 | 1424304.3668 | 337560134.9289 | 4765.675 | 54805262.5 | 20.1083 | 392365397.4289 | kbm | HM 400-3R | KOMATSU HM 400 - 23 | K
18 | KOMATSU HM 400 - 24 | 247 | 1424304.3668 | 351803178.5967 | 4511 | 51876500 | 18.2632 | 403679678.5967 | kbm | HM 400-3R | KOMATSU HM 400 - 24 | K
19 | KOMATSU HM 400 - 25 | 211 | 1424304.3668 | 300528221.3924 | 3692.5 | 42463750 | 17.5 | 342991971.3924 | kbm | HM 400-3R | KOMATSU HM 400 - 25 | K
20 | KOMATSU DOZER D65 - 10 | 259 | 425000 | 110075000 | 6106 | 70219000 | 23.5753 | 180294000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 10 | K
21 | KOMATSU DOZER D65 - 13 | 177 | 425000 | 75225000 | 4414 | 50761000 | 24.9379 | 125986000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 13 | K
22 | KOMATSU DOZER D65 - 15 | 307 | 425000 | 130475000 | 6371 | 73266500 | 20.7524 | 203741500 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 15 | K
23 | KOMATSU DOZER D65 - 16 | 304 | 425000 | 129200000 | 6346 | 72979000 | 20.875 | 202179000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 16 | K
24 | KOMATSU DOZER D65 - 18 | 267 | 425000 | 113475000 | 6575 | 75612500 | 24.6255 | 189087500 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 18 | K
25 | KOMATSU DOZER D85SS - 06 | 83 | 425000 | 35275000 | 1486.9362 | 17099765.9574 | 17.9149 | 52374765.9574 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 06 | K
26 | KOMATSU DOZER D85SS - 14 | 166 | 425000 | 70550000 | 2623.7806 | 30173476.7932 | 15.8059 | 100723476.7932 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 14 | K
27 | KOMATSU DOZER D85SS - 17 | 228 | 425000 | 96900000 | 4248.3453 | 48855971.223 | 18.6331 | 145755971.223 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 17 | K
28 | KOMATSU DOZER D85SS - 18 | 181 | 425000 | 76925000 | 2990.498 | 34390726.9076 | 16.5221 | 111315726.9076 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 18 | K
29 | KOMATSU DOZER D85SS - 20 | 158 | 425000 | 67150000 | 3018.5272 | 34713062.7615 | 19.1046 | 101863062.7615 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 20 | K
TOTAL |  | 5814 | 1021191.9139 | 5736144703.4291 | 123630.9807 | 1421756278.3522 | 21.2644 | 7157900981.7813
KURS USD | 14848
FUEL PRICE | 11500

## REPORT unit QUARRY
COST UNIT QUARRY
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 500 - 01 | 11 | 1000000 | 11000000 | 343.9598 | 3955538.1526 | 31.2691 | 14955538.1526 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 01 | K
2 | KOMATSU PC 500 - 03 | 10 | 1000000 | 10000000 | 275.6985 | 3170533.0882 | 27.5699 | 13170533.0882 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 03 | K
3 | KOMATSU PC 500 - 04 | 38 | 1000000 | 38000000 | 1207.7643 | 13889288.9734 | 31.7833 | 51889288.9734 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 04 | K
4 | KOMATSU PC 400 - 04 | 243 | 1000000 | 243000000 | 7155 | 82282500 | 29.4444 | 325282500 | kbm | PC 500 LCE-10R | KOMATSU PC 400 - 04 | K
5 | KOMATSU PC 400 - 05 | 88 | 1000000 | 88000000 | 2595 | 29842500 | 29.4886 | 117842500 | kbm | PC 500 LCE-10R | KOMATSU PC 400 - 05 | K
6 | KOMATSU PC 300 - 15 | 10 | 1000000 | 10000000 | 267.1111 | 3071777.7778 | 26.7111 | 13071777.7778 | kbm | PC 500 LCE-10R | KOMATSU PC 300 - 15 | K
7 | KOBELCO SK 330 - 11 | 10 | 1000000 | 10000000 | 160.8421 | 1849684.2105 | 16.0842 | 11849684.2105 | kbm | PC 500 LCE-10R | KOBELCO SK 330 - 11 | K
8 | KOMATSU PC 200 - 22 | 119 | 1000000 | 119000000 | 1377 | 15835500 | 11.5714 | 134835500 | kbm | PC 500 LCE-10R | KOMATSU PC 200 - 22 | K
9 | KOMATSU HM 400 - 11 | 35 | 1000000 | 35000000 | 665.6646 | 7655142.4051 | 19.019 | 42655142.4051 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 11 | K
10 | KOMATSU HM 400 - 13 | 24 | 1000000 | 24000000 | 421.6774 | 4849290.3226 | 17.5699 | 28849290.3226 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 13 | K
11 | KOMATSU HM 400 - 14 | 7 | 1000000 | 7000000 | 142.8606 | 1642896.6346 | 20.4087 | 8642896.6346 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 14 | K
12 | KOMATSU HM 400 - 15 | 33 | 1000000 | 33000000 | 638 | 7337000 | 19.3333 | 40337000 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 15 | K
13 | KOMATSU HM 400 - 16 | 38 | 1000000 | 38000000 | 791.2444 | 9099311.1111 | 20.8222 | 47099311.1111 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 16 | K
14 | KOMATSU HM 400 - 18 | 13 | 1000000 | 13000000 | 259.6892 | 2986426.2948 | 19.9761 | 15986426.2948 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 18 | K
15 | KOMATSU HM 400 - 19 | 21 | 1000000 | 21000000 | 417.8276 | 4805017.2414 | 19.8966 | 25805017.2414 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 19 | K
16 | KOMATSU HM 400 - 20 | 27 | 1000000 | 27000000 | 522 | 6003000 | 19.3333 | 33003000 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 20 | K
17 | KOMATSU HM 400 - 21 | 126 | 1000000 | 126000000 | 1813.443 | 20854594.9367 | 14.3924 | 146854594.9367 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 21 | K
18 | KOMATSU HM 400 - 22 | 62 | 1000000 | 62000000 | 1299.4521 | 14943698.6301 | 20.9589 | 76943698.6301 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 22 | K
19 | KOMATSU HM 400 - 23 | 3 | 1000000 | 3000000 | 60.325 | 693737.5 | 20.1083 | 3693737.5 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 23 | K
20 | KOMATSU HM 400 - 25 | 15 | 1000000 | 15000000 | 262.5 | 3018750 | 17.5 | 18018750 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 25 | K
TOTAL |  | 853 | 1000000 | 853000000 | 19054.7827 | 219130001.1488 | 22.3385 | 1072130001.1488
KURS USD | 14848
FUEL PRICE | 11500

## REPORT unit DEVELOP
COST UNIT DEVELOPT
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | SAKAI - 03 |  | 220000 | 0 |  | 0 | 0 | 0 | kbm | SV 525 D | SAKAI - 03 | K
2 | SAKAI - 07 |  | 220000 | 0 |  | 0 | 0 | 0 | kbm | SV 525 D | SAKAI - 07 | K
TOTAL |  | 0 | 220000 | 0 | 0 | 0 | 0 | 0
KURS USD | 14848
FUEL PRICE | 11500

## REPORT unit ORE GETTING
COST UNIT ORE GETTING
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 300 - 07 | 286 | 400000 | 114400000 | 7628 | 87722000 | 26.6713 | 202122000 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 07 | K
2 | KOMATSU PC 300 - 11 | 144 | 400000 | 57600000 | 4006 | 46069000 | 27.8194 | 103669000 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 11 | K
3 | KOMATSU PC 300 - 14 | 17 | 400000 | 6800000 | 947 | 10890500 | 55.7059 | 17690500 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 14 | K
4 | KOMATSU PC 300 - 15 | 305 | 400000 | 122000000 | 8146.8889 | 93689222.2222 | 26.7111 | 215689222.2222 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 15 | K
5 | KOBELCO SK 330 - 10 | 224 | 400000 | 89600000 | 4496 | 51704000 | 20.0714 | 141304000 | kbm | SK 330-8 | KOBELCO SK 330 - 10 | K
6 | KOBELCO SK 330 - 11 | 275 | 400000 | 110000000 | 4423.1579 | 50866315.7895 | 16.0842 | 160866315.7895 | kbm | SK 330-8 | KOBELCO SK 330 - 11 | K
7 | KOBELCO SK 330 - 12 | 281 | 400000 | 112400000 | 4999 | 57488500 | 17.79 | 169888500 | kbm | SK 330-8 | KOBELCO SK 330 - 12 | K
8 | KOMATSU PC 200 - 12 | 277 | 275000 | 76175000 | 4846 | 55729000 | 17.4946 | 131904000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 12 | K
9 | KOMATSU PC 200 - 14 | 287 | 275000 | 78925000 | 4668 | 53682000 | 16.2648 | 132607000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 14 | K
10 | KOMATSU PC 200 - 16 | 266 | 275000 | 73150000 | 3753 | 43159500 | 14.109 | 116309500 | kbm | PC 200-8 MO | KOMATSU PC 200 - 16 | K
11 | KOMATSU PC 200 - 21 | 154 | 275000 | 42350000 | 2037 | 23425500 | 13.2273 | 65775500 | kbm | PC 200-8 MO | KOMATSU PC 200 - 21 | K
12 | KOBELCO SK 200 - 07 | 66 | 275000 | 18150000 | 194 | 2231000 | 2.9394 | 20381000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 07 | K
13 | KOBELCO SK 200 - 08 | 105 | 275000 | 28875000 | 1418 | 16307000 | 13.5048 | 45182000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 08 | K
14 | KOBELCO SK 200 - 10 | 234 | 275000 | 64350000 | 3757 | 43205500 | 16.0556 | 107555500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 10 | K
15 | KOBELCO SK 200 - 11 | 231 | 275000 | 63525000 | 3242 | 37283000 | 14.0346 | 100808000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 11 | K
16 | KOBELCO SK 200 - 13 | 206 | 275000 | 56650000 | 2785 | 32027500 | 13.5194 | 88677500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 13 | K
17 | KOBELCO SK 200 - 15 | 264 | 275000 | 72600000 | 3346 | 38479000 | 12.6742 | 111079000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 15 | K
18 | KOBELCO SK 200 - 16 | 305 | 275000 | 83875000 | 3728 | 42872000 | 12.223 | 126747000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 16 | K
19 | KOBELCO SK 200 - 18 | 264 | 275000 | 72600000 | 3425 | 39387500 | 12.9735 | 111987500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 18 | K
20 | KOBELCO SK 200 - 20 | 83 | 275000 | 22825000 | 405 | 4657500 | 4.8795 | 27482500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 20 | K
21 | KOMATSU DOZER D85SS - 06 | 105 | 425000 | 44625000 | 1881.0638 | 21632234.0426 | 17.9149 | 66257234.0426 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 06 | K
22 | KOMATSU DOZER D85SS - 14 | 71 | 425000 | 30175000 | 1122.2194 | 12905523.2068 | 15.8059 | 43080523.2068 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 14 | K
23 | KOMATSU DOZER D85SS - 17 | 50 | 425000 | 21250000 | 931.6547 | 10714028.777 | 18.6331 | 31964028.777 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 17 | K
24 | KOMATSU DOZER D85SS - 18 | 68 | 425000 | 28900000 | 1123.502 | 12920273.0924 | 16.5221 | 41820273.0924 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 18 | K
25 | KOMATSU DOZER D85SS - 20 | 81 | 425000 | 34425000 | 1547.4728 | 17795937.2385 | 19.1046 | 52220937.2385 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 20 | K
TOTAL |  | 4274 | 318750 | 1366850000 | 72250.0468 | 830875538.0117 | 16.9046 | 2197725538.0117
KURS USD | 14848
FUEL PRICE | 11500

## REPORT unit DT HAUL
COST UNIT HAULING
NO | UNIT | TONNAGE |  | RENT |  | FUEL CONSUMPTION |  | RATIO |  |  | GRAND TOTAL COST |  | DESC. | TYPE
|  | Weight Bridge |  | Rate | Total | Fuel | Total
|  | Tonnage | Retase | ($/hour) |  | (liter) |  | (liter/ton) | (ton/ret) | (liter/ret)
1 | DT HINO G 310 | 1981.3 | 42 | 500000 | 105000000 | 2006 | 23069000 | 1.0125 | 47.1738 | 47.7619 | 128069000 | 308892595.2 | ore hauling kbm | 700 Provia/12 | DT HINO G 310
2 | DT HINO G 311 | 1348.2 | 29 | 500000 | 105000000 | 1135 | 13052500 | 0.84186 | 46.4897 | 39.1379 | 118052500 | 210189772.8 | ore hauling kbm | 700 Provia/12 | DT HINO G 311
3 | DT HINO G 314 | 2096.01 | 44 | 500000 | 105000000 | 2214 | 25461000 | 1.0563 | 47.6366 | 50.3182 | 130461000 | 326776343.04 | ore hauling kbm | 700 Provia/12 | DT HINO G 314
4 | DT HINO G 315 | 1192.09 | 25 | 500000 | 105000000 | 1130 | 12995000 | 0.94792 | 47.6836 | 45.2 | 117995000 | 185851599.36 | ore hauling kbm | 700 Provia/12 | DT HINO G 315
5 | DT HINO G 316 | 1896.2 | 41 | 500000 | 105000000 | 1350 | 15525000 | 0.71195 | 46.2488 | 32.9268 | 120525000 | 295625164.8 | ore hauling kbm | 700 Provia/12 | DT HINO G 316
6 | DT HINO G 317 | 1484.98 | 33 | 500000 | 105000000 | 903 | 10384500 | 0.60809 | 44.9994 | 27.3636 | 115384500 | 231514321.92 | ore hauling kbm | 700 Provia/12 | DT HINO G 317
7 | DT HINO G 318 | 2219.45 | 48 | 500000 | 105000000 | 1758 | 20217000 | 0.79209 | 46.2385 | 36.625 | 125217000 | 346021132.8 | ore hauling kbm | 700 Provia/12 | DT HINO G 318
8 | DT HINO G 321 | 2227.12 | 48 | 500000 | 105000000 | 2268 | 26082000 | 1.0184 | 46.3983 | 47.25 | 131082000 | 347216916.48 | ore hauling kbm | 700 Provia/12 | DT HINO G 321
9 | DT HINO G 323 | 2078.54 | 45 | 500000 | 105000000 | 2232 | 25668000 | 1.0738 | 46.1898 | 49.6 | 130668000 | 324052700.16 | ore hauling kbm | 700 Provia/12 | DT HINO G 323
10 | DT HINO G 324 | 949.05 | 19 | 500000 | 105000000 | 1035 | 11902500 | 1.0906 | 49.95 | 54.4737 | 116902500 | 147960691.2 | ore hauling kbm | 700 Provia/12 | DT HINO G 324
11 | DT HINO G 325 | 1350.36 | 28 | 500000 | 105000000 | 1236 | 14214000 | 0.91531 | 48.2271 | 44.1429 | 119214000 | 210526525.44 | ore hauling kbm | 700 Provia/12 | DT HINO G 325
12 | DT HINO G 326 | 1175.23 | 25 | 500000 | 105000000 | 1356 | 15594000 | 1.1538 | 47.0092 | 54.24 | 120594000 | 183223057.92 | ore hauling kbm | 700 Provia/12 | DT HINO G 326
13 | DT HINO G 329 | 2110.25 | 45 | 500000 | 105000000 | 1761 | 20251500 | 0.8345 | 46.8944 | 39.1333 | 125251500 | 328996416 | ore hauling kbm | 700 Provia/12 | DT HINO G 329
14 | DT HINO G 331 | 860.93 | 18 | 500000 | 105000000 | 925 | 10637500 | 1.0744 | 47.8294 | 51.3889 | 115637500 | 134222430.72 | ore hauling kbm | 700 Provia/12 | DT HINO G 331
15 | DT HINO G 332 | 704.72 | 15 | 500000 | 105000000 | 926 | 10649000 | 1.314 | 46.9813 | 61.7333 | 115649000 | 109868666.88 | ore hauling kbm | 700 Provia/12 | DT HINO G 332
16 | DT HINO G 333 | 1455.83 | 30 | 500000 | 105000000 | 1493 | 17169500 | 1.0255 | 48.5277 | 49.7667 | 122169500 | 226969720.32 | ore hauling kbm | 700 Provia/12 | DT HINO G 333
17 | DT HINO G 334 | 786.07 | 17 | 500000 | 105000000 | 921 | 10591500 | 1.1717 | 46.2394 | 54.1765 | 115591500 | 122551457.28 | ore hauling kbm | 700 Provia/12 | DT HINO G 334
18 | DT HINO G 335 | 522.27 | 11 | 500000 | 105000000 | 596 | 6854000 | 1.1412 | 47.4791 | 54.1818 | 111854000 | 81423982.08 | ore hauling kbm | 700 Provia/12 | DT HINO G 335
19 | DT HINO G 336 | 2452.67 | 53 | 500000 | 105000000 | 1975 | 22712500 | 0.80524 | 46.2768 | 37.2642 | 127712500 | 382381063.68 | ore hauling kbm | 700 Provia/12 | DT HINO G 336
20 | DT HINO G 337 | 929.84 | 19 | 500000 | 105000000 | 969 | 11143500 | 1.0421 | 48.9389 | 51 | 116143500 | 144965775.36 | ore hauling kbm | 700 Provia/12 | DT HINO G 337
21 | DT HINO G 339 | 2926.68 | 63 | 500000 | 105000000 | 2435 | 28002500 | 0.832 | 46.4552 | 38.6508 | 133002500 | 456281118.72 | ore hauling kbm | 700 Provia/12 | DT HINO G 339
22 | DT HINO G 340 | 476.68 | 10 | 500000 | 105000000 | 640 | 7360000 | 1.3426 | 47.668 | 64 | 112360000 | 74316318.72 | ore hauling kbm | 700 Provia/12 | DT HINO G 340
23 | DT HINO G 341 | 1635.11 | 35 | 500000 | 105000000 | 1798 | 20677000 | 1.0996 | 46.7174 | 51.3714 | 125677000 | 254920189.44 | ore hauling kbm | 700 Provia/12 | DT HINO G 341
24 | DT HINO G 343 | 1706.48 | 36 | 500000 | 105000000 | 1811 | 20826500 | 1.0612 | 47.4022 | 50.3056 | 125826500 | 266047057.92 | ore hauling kbm | 700 Provia/12 | DT HINO G 343
25 | DT HINO G 344 | 3275.62 | 70 | 500000 | 105000000 | 2719 | 31268500 | 0.83007 | 46.7946 | 38.8429 | 136268500 | 510682260.48 | ore hauling kbm | 700 Provia/12 | DT HINO G 344
26 | DT HINO G 346 | 2292.56 | 48 | 500000 | 105000000 | 2198 | 25277000 | 0.95875 | 47.7617 | 45.7917 | 130277000 | 357419274.24 | ore hauling kbm | 700 Provia/12 | DT HINO G 346
27 | DT HINO G 347 | 1867.08 | 39 | 500000 | 105000000 | 2115 | 24322500 | 1.1328 | 47.8738 | 54.2308 | 129322500 | 291085240.32 | ore hauling kbm | 700 Provia/12 | DT HINO G 347
28 | DT HINO G 348 | 2119.57 | 44 | 500000 | 105000000 | 2104 | 24196000 | 0.99265 | 48.172 | 47.8182 | 129196000 | 330449441.28 | ore hauling kbm | 700 Provia/12 | DT HINO G 348
29 | DT HINO G 349 | 1542.28 | 34 | 500000 | 105000000 | 1226 | 14099000 | 0.79493 | 45.3612 | 36.0588 | 119099000 | 240447621.12 | ore hauling kbm | 700 Provia/12 | DT HINO G 349
30 | DT HINO G 350 | 1968.58 | 41 | 500000 | 105000000 | 2045 | 23517500 | 1.0388 | 48.0141 | 49.878 | 128517500 | 306909496.32 | ore hauling kbm | 700 Provia/12 | DT HINO G 350
31 | DT HINO G 351 | 3538.5 | 76 | 500000 | 105000000 | 2975 | 34212500 | 0.84075 | 46.5592 | 39.1447 | 139212500 | 551666304 | ore hauling kbm | 700 Provia/12 | DT HINO G 351
32 | DT HINO G 352 | 2219.9 | 48 | 500000 | 105000000 | 1914 | 22011000 | 0.8622 | 46.2479 | 39.875 | 127011000 | 346091289.6 | ore hauling kbm | 700 Provia/12 | DT HINO G 352
33 | DT HINO G 353 | 3774.99 | 81 | 500000 | 105000000 | 3369 | 38743500 | 0.89245 | 46.6048 | 41.5926 | 143743500 | 588536040.96 | ore hauling kbm | 700 Provia/12 | DT HINO G 353
34 | DT HINO G 354 | 3968.84 | 85 | 500000 | 105000000 | 3455 | 39732500 | 0.87053 | 46.6922 | 40.6471 | 144732500 | 618758031.36 | ore hauling kbm | 700 Provia/12 | DT HINO G 354
35 | DT HINO G 355 | 3216.26 | 70 | 500000 | 105000000 | 2757 | 31705500 | 0.85721 | 45.9466 | 39.3857 | 136705500 | 501427799.04 | ore hauling kbm | 700 Provia/12 | DT HINO G 355
36 | DT HINO G 357 | 3076.66 | 66 | 500000 | 105000000 | 2463 | 28324500 | 0.80054 | 46.6161 | 37.3182 | 133324500 | 479663600.64 | ore hauling kbm | 700 Provia/12 | DT HINO G 357
37 | DT HINO G 358 | 2210.93 | 48 | 500000 | 105000000 | 2324 | 26726000 | 1.0511 | 46.061 | 48.4167 | 131726000 | 344692830.72 | ore hauling kbm | 700 Provia/12 | DT HINO G 358
38 | DT HINO G 359 | 4435.57 | 93 | 500000 | 105000000 | 4253 | 48909500 | 0.95884 | 47.6943 | 45.7312 | 153909500 | 691523105.28 | ore hauling kbm | 700 Provia/12 | DT HINO G 359
39 | DT HINO G 360 | 3165.44 | 67 | 500000 | 105000000 | 3165 | 36397500 | 0.99986 | 47.2454 | 47.2388 | 141397500 | 493504757.76 | ore hauling kbm | 700 Provia/12 | DT HINO G 360
40 | DT HINO G 361 | 3961.9 | 85 | 500000 | 105000000 | 3943 | 45344500 | 0.99523 | 46.6106 | 46.3882 | 150344500 | 617676057.6 | ore hauling kbm | 700 Provia/12 | DT HINO G 361
41 | DT HINO G 362 | 2167.62 | 48 | 500000 | 105000000 | 2104 | 24196000 | 0.97065 | 45.1588 | 43.8333 | 129196000 | 337940628.48 | ore hauling kbm | 700 Provia/12 | DT HINO G 362
42 | DT HINO G 363 | 3663.13 | 78 | 500000 | 105000000 | 3366 | 38709000 | 0.91889 | 46.9632 | 43.1538 | 143709000 | 571096619.52 | ore hauling kbm | 700 Provia/12 | DT HINO G 363
43 | DT HINO G 365 | 2062.88 | 43 | 500000 | 105000000 | 1964 | 22586000 | 0.95207 | 47.974 | 45.6744 | 127586000 | 321611243.52 | ore hauling kbm | 700 Provia/12 | DT HINO G 365
44 | DT HINO G 366 | 4055 | 89 | 500000 | 105000000 | 3937 | 45275500 | 0.9709 | 45.5618 | 44.236 | 150275500 | 632190720 | ore hauling kbm | 700 Provia/12 | DT HINO G 366
45 | DT HINO G 367 | 4853.29 | 106 | 500000 | 105000000 | 4673 | 53739500 | 0.96285 | 45.7858 | 44.0849 | 158739500 | 756647324.16 | ore hauling kbm | 700 Provia/12 | DT HINO G 367
46 | DT HINO G 368 | 3650.47 | 78 | 500000 | 105000000 | 3505 | 40307500 | 0.96015 | 46.8009 | 44.9359 | 145307500 | 569122874.88 | ore hauling kbm | 700 Provia/12 | DT HINO G 368
47 | DT HINO G 369 | 3090.06 | 66 | 500000 | 105000000 | 2994 | 34431000 | 0.96891 | 46.8191 | 45.3636 | 139431000 | 481752714.24 | ore hauling kbm | 700 Provia/12 | DT HINO G 369
48 | DT HINO G 370 | 4151.57 | 90 | 500000 | 105000000 | 4093 | 47069500 | 0.98589 | 46.1286 | 45.4778 | 152069500 | 647246369.28 | ore hauling kbm | 700 Provia/12 | DT HINO G 370
49 | DT HINO G 371 | 3956.29 | 87 | 500000 | 105000000 | 3585 | 41227500 | 0.90615 | 45.4746 | 41.2069 | 146227500 | 616801436.16 | ore hauling kbm | 700 Provia/12 | DT HINO G 371
50 | DT HINO G 373 | 4611.94 | 100 | 500000 | 105000000 | 4278 | 49197000 | 0.92759 | 46.1194 | 42.78 | 154197000 | 719019893.76 | ore hauling kbm | 700 Provia/12 | DT HINO G 373
51 | DT HINO G 374 | 4995.57 | 106 | 500000 | 105000000 | 4624 | 53176000 | 0.92562 | 47.128 | 43.6226 | 158176000 | 778829345.28 | ore hauling kbm | 700 Provia/12 | DT HINO G 374
52 | DT HINO G 375 | 4075.31 | 88 | 500000 | 105000000 | 4098 | 47127000 | 1.0056 | 46.3103 | 46.5682 | 152127000 | 635357130.24 | ore hauling kbm | 700 Provia/12 | DT HINO G 375
53 | DT HINO G 376 | 4597.97 | 100 | 500000 | 105000000 | 4517 | 51945500 | 0.98239 | 45.9797 | 45.17 | 156945500 | 716841914.88 | ore hauling kbm | 700 Provia/12 | DT HINO G 376
54 | DT HINO G 377 | 4566.53 | 99 | 500000 | 105000000 | 4319 | 49668500 | 0.94579 | 46.1266 | 43.6263 | 154668500 | 711940293.12 | ore hauling kbm | 700 Provia/12 | DT HINO G 377
55 | DT HINO G 378 | 4287.87 | 92 | 500000 | 105000000 | 4140 | 47610000 | 0.96551 | 46.6073 | 45 | 152610000 | 668496084.48 | ore hauling kbm | 700 Provia/12 | DT HINO G 378
56 | DT HINO G 380 | 3770.49 | 82 | 500000 | 105000000 | 3802 | 43723000 | 1.0084 | 45.9816 | 46.3659 | 148723000 | 587834472.96 | ore hauling kbm | 700 Provia/12 | DT HINO G 380
57 | DT HINO G 381 | 3371.89 | 72 | 500000 | 105000000 | 3119 | 35868500 | 0.925 | 46.8318 | 43.3194 | 140868500 | 525691138.56 | ore hauling kbm | 700 Provia/12 | DT HINO G 381
58 | DT HINO G 382 | 3138.5 | 68 | 500000 | 105000000 | 3189 | 36673500 | 1.0161 | 46.1544 | 46.8971 | 141673500 | 489304704 | ore hauling kbm | 700 Provia/12 | DT HINO G 382
59 | DT HINO G 383 | 4478.31 | 97 | 500000 | 105000000 | 3918 | 45057000 | 0.87488 | 46.1681 | 40.3918 | 150057000 | 698186442.24 | ore hauling kbm | 700 Provia/12 | DT HINO G 383
60 | DT HINO G 385 | 5357.06 | 116 | 500000 | 105000000 | 4671 | 53716500 | 0.87193 | 46.1816 | 40.2672 | 158716500 | 835187082.24 | ore hauling kbm | 700 Provia/12 | DT HINO G 385
61 | DT HINO G 386 | 5146.65 | 113 | 500000 | 105000000 | 4740 | 54510000 | 0.92099 | 45.5456 | 41.9469 | 159510000 | 802383321.6 | ore hauling kbm | 700 Provia/12 | DT HINO G 386
62 | DT HINO G 387 | 5209.82 | 109 | 500000 | 105000000 | 4572 | 52578000 | 0.87757 | 47.7965 | 41.945 | 157578000 | 812231777.28 | ore hauling kbm | 700 Provia/12 | DT HINO G 387
63 | DT HINO G 388 | 4994.19 | 107 | 500000 | 105000000 | 4742 | 54533000 | 0.9495 | 46.6747 | 44.3178 | 159533000 | 778614197.76 | ore hauling kbm | 700 Provia/12 | DT HINO G 388
64 | DT HINO G 389 | 5049.85 | 109 | 500000 | 105000000 | 4847 | 55740500 | 0.95983 | 46.3289 | 44.4679 | 160740500 | 787291814.4 | ore hauling kbm | 700 Provia/12 | DT HINO G 389
65 | DT HINO G 390 | 4478.53 | 98 | 500000 | 105000000 | 3956 | 45494000 | 0.88333 | 45.6993 | 40.3673 | 150494000 | 698220741.12 | ore hauling kbm | 700 Provia/12 | DT HINO G 390
66 | DT HINO G 391 | 5138.11 | 109 | 500000 | 105000000 | 4816 | 55384000 | 0.93731 | 47.1386 | 44.1835 | 160384000 | 801051901.44 | ore hauling kbm | 700 Provia/12 | DT HINO G 391
67 | DT HINO G 392 | 5004.35 | 108 | 500000 | 105000000 | 4907 | 56430500 | 0.98055 | 46.3366 | 45.4352 | 161430500 | 780198182.4 | ore hauling kbm | 700 Provia/12 | DT HINO G 392
68 | DT HINO G 393 | 5330.02 | 117 | 500000 | 105000000 | 5165 | 59397500 | 0.96904 | 45.5557 | 44.1453 | 164397500 | 830971438.08 | ore hauling kbm | 700 Provia/12 | DT HINO G 393
69 | DT HINO G 394 | 1886.2 | 41 | 500000 | 105000000 | 1841 | 21171500 | 0.97604 | 46.0049 | 44.9024 | 126171500 | 294066124.8 | ore hauling kbm | 700 Provia/12 | DT HINO G 394
TOTAL |  | 204340.21 | 4390 |  | 7245000000 | 192380 | 2212370000 | 0.94147 | 46.5467 | 43.8223 | 9457370000 | 31857456099.84
HINO 700
KURS USD | 14848
FUEL PRICE | 11500
Min Charge | 210 | Hour

## REPORT unit LV & support
COST UNIT SUPPORT
NO | UNIT | RENT PER MONTH | FUEL CONSUMPTION |  | RATIO | GRAND TOTAL COST | DESC. | TYPE
|  |  | Fuel | Total
|  | (Rp/month) | (liter) |  | (liter/km)
1 | LV PAJERO PUTIH - 06 | 8000000 |  | 0 |  | 8000000 |  | LV | LV PAJERO PUTIH - 06
2 | LV TRITON HITAM - 08 | 8000000 |  | 0 |  | 8000000 |  | LV | LV TRITON HITAM - 08
3 | LV PAJERO PUTIH - 09 | 8000000 |  | 0 |  | 8000000 |  | LV | LV PAJERO PUTIH - 09
4 | LV HILUX SILVER - 10 | 8000000 |  | 0 |  | 8000000 |  | LV | LV HILUX SILVER - 10
5 | LV TRITON HITAM - 10 | 8000000 |  | 0 |  | 8000000 |  | LV | LV TRITON HITAM - 10
6 | LV TRITON PUTIH - 11 | 8000000 |  | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 11
7 | LV TRITON PUTIH - 12 | 8000000 |  | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 12
8 | LV PAJERO HITAM - 15 | 8000000 |  | 0 |  | 8000000 |  | LV | LV PAJERO HITAM - 15
9 | LV HILUX SILVER - 17 | 8000000 |  | 0 |  | 8000000 |  | LV | LV HILUX SILVER - 17
10 | LV HILUX HITAM - 18 | 8000000 |  | 0 |  | 8000000 |  | LV | LV HILUX HITAM - 18
11 | LV HILUX SILVER - 19 | 8000000 |  | 0 |  | 8000000 |  | LV | LV HILUX SILVER - 19
12 | LV HILUX SILVER - 20 | 0 |  | 0 |  | 0 |  | #N/A | LV HILUX SILVER - 20
13 | LV PAJERO SILVER - 21 | 8000000 |  | 0 |  | 8000000 |  | LV | LV PAJERO SILVER - 21
14 | LV HILUX PUTIH - 23 | 8000000 |  | 0 |  | 8000000 |  | LV | LV HILUX PUTIH - 23
15 | LV LC-SILVER - 24 | 8000000 |  | 0 |  | 8000000 |  | LV | LV LC-SILVER - 24
16 | LV TRITON PUTIH - 27 | 8000000 |  | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 27
17 | LV LC-HIJAU - 29 | 8000000 |  | 0 |  | 8000000 |  | LV | LV LC-HIJAU - 29
18 | LV TRITON PUTIH (SAFETY) - 30 | 8000000 |  | 0 |  | 8000000 |  | LV | LV TRITON PUTIH (SAFETY) - 30
19 | LV TRITON PUTIH - 31 | 8000000 |  | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 31
20 | LV TRITON PUTIH - 32 | 8000000 |  | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 32
21 | MANHAUL - 02 | 210000 |  | 0 |  | 210000 |  | FM 260 Ti | MANHAUL - 02
22 | BUS APP - 03 | 12000000 |  | 0 |  | 12000000 |  | LT | BUS APP - 03
23 | FUEL TRUCK - 05 | 210000 |  | 0 |  | 210000 |  | FM 260 Ti | FUEL TRUCK - 05
24 | FUEL TRUCK - 06 | 210000 |  | 0 |  | 210000 |  | FM 260 Ti | FUEL TRUCK - 06
25 | TRUCK WELDER - LT-04 | 12000000 |  | 0 |  | 12000000 |  | LT | TRUCK WELDER - LT-04
26 | TRUCK TYRE - LT-08 | 12000000 |  | 0 |  | 12000000 |  | LT | TRUCK TYRE - LT-08
27 | TRUCK MAINTENANCE - LT-09 | 12000000 |  | 0 |  | 12000000 |  | LT | TRUCK MAINTENANCE - LT-09
28 | TRUCK TYRE - LT-10 | 12000000 |  | 0 |  | 12000000 |  | LT | TRUCK TYRE - LT-10
29 | MEKANIK CAMP | 0 |  | 0 |  | 0 |  | 0 | MEKANIK CAMP
TOTAL |  | 212630000 | 0 | 0 | 0 | 212630000
KURS USD | 14848
FUEL PRICE | 11500

## HOUR METER (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
D | NO | ID UNIT | DAYLY REPORT HM | [30 empty] | TOTAL HM | TOTAL FUEL 1- 31
N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WEEK 1 | : | 0 | DAYLY REPORT HM 22: Di setujui oleh :; DAYLY REPORT HM 29: Di buat oleh :
WEEK 2 | : | 0
WEEK 3 | : | 0
WEEK 4 | : | 0 | bar: DAYLY REPORT HM 5
WEEK 5 | : | 0 | DAYLY REPORT HM 22: Internal Kontrol; DAYLY REPORT HM 29: MPE Team
0
BENAR

## FUEL UNIT (hidden)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| D | NO | ID UNIT | DAYLY REPORT FUEL | [30 empty] | TOTAL FUEL | TOTAL HM 1- 31
| N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
SM-BW 211-02 | TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
SM-BW 211-03 | TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
| TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
SM-D85ESS-08 | TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
| TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
| TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
| TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
| TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
| TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
| TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
| ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
| ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
| ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
| ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
| ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
| ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
| ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
| DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
| DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
| DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
| DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
| DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
| TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
| TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DAYLY REPORT FUEL 30: TOTAL FUEL | 0
| WEEK 1 | : | 0 | DAYLY REPORT FUEL 22: Di setujui oleh :; DAYLY REPORT FUEL 29: Di buat oleh :
| WEEK 2 | : | 0
| WEEK 3 | : | 0
| WEEK 4 | : | 0
| WEEK 5 | : | 0 | DAYLY REPORT FUEL 22: Internal Kontrol; DAYLY REPORT FUEL 29: MPE Team
0
BENAR

## list rate unit
RATE
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | unit | type
NO | UNIT | Ltr/Hr | Rent/Hr | Column1 | Column2 | Description | Column4 | Column5 | Column6 | Column7 |  | KOMATSU PC 500 - 01 | PC 500 LCE-10R
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  | KOMATSU PC 500 - 02 | PC 500 LCE-10R
|  |  | Unit Only (Internal) | Incl. Operator | Incl. Operator & Fuel | [6 empty] | KOMATSU PC 500 - 03 | PC 500 LCE-10R
1 | PC 195 LC-8 | 20 | 16.5432 | 19.5084 | 35.3704 | Excavator | 239875.7064 | 282871.4905 | 512871.4905 | 275000 | 200 | KOMATSU PC 500 - 04 | PC 500 LCE-10R
2 | PC 200-8 MO | 22 | 23.2254 | 26.1906 | 43.6389 | Excavator | 336767.7028 | 379763.4868 | 632763.4868 | 275000 | 200 | KOMATSU PC 400 - 01 | PC 400 LC SE-8
3 | PC 300 SE-8 | 30 | 41.2152 | 44.1804 | 69.5598 | Excavator | 597620.6927 | 640616.4768 | 1008616.4768 | 400000 | 300 | KOMATSU PC 400 - 03 | PC 400 LC SE-8
4 | PC 400 LC SE-8 | 38 | 58.29 | 61.6 | 87.81 | Excavator | 845205 | 893200 | 1273245 | 950000 | 400 | KOMATSU PC 400 - 04 | PC 400 LC SE-8
5 | PC 500 LCE-10R | 45 | 63.54 | 66.85 | 98.05 | Excavator | 921330 | 969325 | 1421725 | 1000000 |  | KOMATSU PC 400 - 05 | PC 400 LC SE-8
6 | SK 200-8 SX | 20 | 17.6502 | 20.6154 | 36.4775 | Excavator | 255927.8486 | 298923.6327 | 528923.6327 | 275000 | 200 | KOMATSU PC 400 - 06 | PC 400 LC SE-8
7 | SK 330-8 | 28 | 34.235 | 37.2002 | 59.4071 | Excavator | 496407.8395 | 539403.6235 | 861403.6235 | 400000 |  | KOMATSU PC 300 - 10 | PC 300 SE-8
8 | HM 400-3R | 30 | 98.2279 | 101.5379 | 127.7104 | Artic | 1424304.3668 | 1472300.1508 | 1851800.1508 | 1424304.3668 |  | KOMATSU PC 300 - 11 | PC 300 SE-8
9 | D 85 ESS-2 | 30 | 42.331 | 45.2962 | 69.0893 | Bulldozer | 613799.3709 | 656795.155 | 1001795.155 | 425000 |  | KOMATSU PC 300 - 12 | PC 300 SE-8
10 | D 65 P-12 | 33 | 42.7792 | 45.7445 | 71.9169 | Bulldozer | 620298.906 | 663294.6901 | 1042794.6901 | 425000 |  | KOMATSU PC 300 - 14 | PC 300 SE-8
11 | GD 511 A-1 | 15 | 32.851 | 35.8163 | 47.7128 | Grader | 476340.0889 | 519335.8729 | 691835.8729 | 350000 |  | KOMATSU PC 300 - 15 | PC 300 SE-8
12 | SV 525 D | 11 | 13.1981 | 16.1633 | 24.0943 | Compactor | 191372.0947 | 234367.8788 | 349367.8788 | 220000 |  | KOMATSU PC 300 - 16 | PC 300 SE-8
13 | BW 211 D-40 | 11 | 9.9397 | 12.9049 | 20.8359 | Compactor | 144125.031 | 187120.8151 | 302120.8151 | 220000 |  | KOMATSU PC 300 - 17 | PC 300 SE-8
14 | XG 6121 | 11 | 8.6243 | 11.5895 | 19.5206 | Compactor | 125052.5178 | 168048.3018 | 283048.3018 |  |  | KOBELCO SK 330 - 10 | SK 330-8
15 | XG 955-III | 20 | 12.8699 | 15.8352 | 31.6972 | Whell Loader | 186614.0656 | 229609.8497 | 459609.8497 |  |  | KOBELCO SK 330 - 11 | SK 330-8
16 | WA 380-3 | 20 | 34.0145 | 36.9797 | 52.8418 | Whell Loader | 493209.9817 | 536205.7657 | 766205.7657 |  |  | KOMATSU PC 200 - 11 | PC 200-8 MO
17 | FM 260 Ti | 15 | 17.3403 | 18.9483 | 30.0517 | Dump Truck | 251435.0252 | 274750.1408 | 435750.1408 | 210000 |  | KOMATSU PC 200 - 12 | PC 200-8 MO
18 | 700 Provia | 20 | 31.1718 | 32.9521 | 48.8142 | Dump Truck | 451990.7019 | 477805.8175 | 707805.8175 | 460000 |  | KOMATSU PC 200 - 14 | PC 200-8 MO
19 | 700 Provia/12 | 28 | 32.42 | 34.21 | 53.52 | Dump Truck | 470090 | 496045 | 776040 | 500000 |  | KOMATSU PC 200 - 15 | PC 200-8 MO
20 | LV | 10 |  |  |  |  | 8000000 |  |  | 8000000 |  | KOMATSU PC 200 - 16 | PC 200-8 MO
21 | GENSET | 4 |  |  |  |  | 3000000 |  |  | 3000000 |  | KOMATSU PC 200 - 22 | PC 200-8 MO
22 | LT | 10 |  |  |  |  | 12000000 |  |  | 12000000 |  | KOMATSU PC 200 - 23 | PC 200-8 MO
RATE MOBILISASI | [11 empty] | KOMATSU PC 200 - 25 | PC 200-8 MO
[9 empty] | source data ( owning & operating cost) |  |  | KOMATSU PC 195 - 01 | PC 195 LC-8
NO | UNIT | $ / KM | [9 empty] | KOBELCO SK 200 - 07 | SK 200-8 SX
1 | PC 400 | 24 | [9 empty] | KOBELCO SK 200 - 08 | SK 200-8 SX
2 | PC 300 | 16 | [9 empty] | KOBELCO SK 200 - 10 | SK 200-8 SX
3 | PC 200 | 8 | [9 empty] | KOBELCO SK 200 - 11 | SK 200-8 SX
4 | BULLDOZER | 16 | [9 empty] | KOBELCO SK 200 - 13 | SK 200-8 SX
5 | COMPACTOR | 8 | [9 empty] | KOBELCO SK 200 - 15 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 16 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 18 | SK 200-8 SX
| 14652.34 | [10 empty] | KOBELCO SK 200 - 19 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 20 | SK 200-8 SX
[12 empty] | KOMATSU HM 400 - 01 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 02 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 04 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 05 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 06 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 07 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 08 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 09 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 10 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 11 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 12 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 13 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 14 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 15 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 16 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 17 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 18 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 19 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 20 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 21 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 22 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 23 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 24 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 25 | HM 400-3R
[12 empty] | KOMATSU DOZER D65 - 05 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 10 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 11 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 12 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 13 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 15 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 16 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 18 | D 65 P-12
[12 empty] | KOMATSU DOZER D85SS - 11 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 14 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 17 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 18 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 20 | D 85 ESS-2
[12 empty] | GRADER GD535 - 03 | GD 511 A-1
[12 empty] | LOADER WA380 - 02 | WA 380-3
[12 empty] | SAKAI - 02 | SV 525 D
[12 empty] | SAKAI - 03 | SV 525 D
[12 empty] | SAKAI - 07 | SV 525 D
[12 empty] | LV HILUX HITAM - 05 | LV
[12 empty] | LV PAJERO PUTIH - 06 | LV
[12 empty] | LV TRITON HITAM - 08 | LV
[12 empty] | LV PAJERO PUTIH - 09 | LV
[12 empty] | LV HILUX SILVER - 10 | LV
[12 empty] | LV TRITON HITAM - 10 | LV
[12 empty] | LV TRITON PUTIH - 11 | LV
[12 empty] | LV HILUX HITAM - 11 | LV
[12 empty] | LV TRITON PUTIH - 12 | LV
[12 empty] | LV PAJERO HITAM - 15 | LV
[12 empty] | LV HILUX SILVER - 17 | LV
[12 empty] | LV HILUX HITAM - 18 | LV
[12 empty] | LV HILUX SILVER - 19 | LV
[12 empty] | LV PAJERO SILVER - 21 | LV
[12 empty] | LV HILUX PUTIH - 23 | LV
[12 empty] | LV TRITON PUTIH - 27 | LV
[12 empty] | LV LC-HIJAU - 29 | LV
[12 empty] | LV TRITON PUTIH (SAFETY) - 30 | LV
[12 empty] | LV TRITON PUTIH - 31 | LV
[12 empty] | LV TRITON PUTIH - 32 | LV
[12 empty] | MANHAUL - 02 | FM 260 Ti
[12 empty] | BUS APP - 03 | LT
[12 empty] | FUEL TRUCK - 03 | FM 260 Ti
[12 empty] | FUEL TRUCK - 05 | FM 260 Ti
[12 empty] | FUEL TRUCK - 06 | FM 260 Ti
[12 empty] | TRUCK WELDER - LT-04 | LT
[12 empty] | TRUCK TYRE - LT-08 | LT
[12 empty] | TRUCK MAINTENANCE - LT-09 | LT
[12 empty] | TRUCK TYRE - LT-10 | LT
MEKANIK CAMP
[12 empty] | LV HILUX HITAM - 04 | LV
Kompresor Tyre
[12 empty] | KOMATSU DOZER D85SS - 06 | D 85 ESS-2
[12 empty] | KOMATSU PC 300 - 07 | PC 300 SE-8
[12 empty] | KOBELCO SK 330 - 12 | SK 330-8
[12 empty] | LV LC-SILVER - 24 | LV
[12 empty] | WELDER CAR | LT
[12 empty] | KOMATSU PC 200 - 21 | PC 200-8 MO