## SUMMARY
MINING COST (MEI)
| SUMMARY KBM BLOK C & D | MEI 2024 |  |  | CV ADIL PRIMA PERKASA
|  | PLAN | ACTUAL | ACH % | DAYS WORK |  | 31 | days
| OVERBURDEN REMOVAL | 108336.7296 | 124621.9 | 115% | WORKING HOUR |  | 279 | hours
| ORE MINING | 151034.2848 | 85982.45 | 56.93% | PHYSICHAL AVAILIBILITY |  | 92% | PA
| QUARRY MINING | 21667.3459 | 15925.8 | 73.5%
| STRIPING RATIO | 0.7173 | 1.4494 | 49.49% | Fuel Price / liter |  | 11500
| FUEL RATIO OVERALL (L/Ton) | 1.8668 | 2.799 | 66.69% | (fuel not include in contract)
6 hari tidak operasi dikarenakan belum adanya kesiapan material yang dapat dimuat (grade sesuai kontrak)
| ADT HM 400 (bcm/hour) |  |  |  | Total Fuel Consumption | PLAN | 281944.527 | Liter
| PRODUCTION hauler | 63 | 78.035 | 123.9% |  | ACTUAL | 240666.2104 | Liter
[6 empty] | ACH % | 117.2%
| COST RENT + FUEL |  |  |  | COST ITEM / TON ORE
| COST OB REMOVAL | 5129695377.3567 |  |  | COST OB / TON | 40.64% | 59659.7954 | 4.018
| COST QUARRY HAULING | 1186422072.9017 |  |  | COST QUARRY / TON | 9.399% | 13798.4213 | 0.92931
| COST DEVELOP ACT. | 0 |  |  | COST DEV / TON | 0% | 0 | 0
| COST ORE GETTING | 1506917780.5152 |  |  | COST ORE GETTING / TON | 11.94% | 17525.8763 | 1.1804
| COST ORE HAULING | 4540841500 |  |  | COST ORE HAULING / TON | 35.97% | 52811.2597 | 3.5568
| COST UNIT SUPPORT | 258778500 |  |  | COST SUPPORT / TON | 2.05% | 3009.6665 | 0.2027
[6 empty] | 100% | 146805.0193 | 9.8872
| TOTAL COST | 12622655230.7736 |  |  | COST / TON ORE |  | 146805.0193
| INCOME | 13405007884.8 |  |  | ( USD / Ton ) |  | 9.8872
[5 empty] | KURS/$ |  | 14848
| RESULT | 782352654.0264 |  |  | PRICE / TON ORE |  | 10.5
OKE…..

## SUMMARY 2 (hidden)
MINING COST (FEBRUARY)
| SUMMARY KBM BLOK B & C | February 2023 |  | CV. ADIL PRIMA PERKASA
| WASTE REMOVAL |  | 170387.16 | DAYS WORK |  | 28
| ORE MINING |  | 85982.45 | WORKING HOUR |  | 252
| QUARRY MINING |  | 33006.63 | MECANICAL AVAILABILITY |  | 85%
| STRIPING RATIO |  | 1.9817
|  |  |  | Fuel Price / liter | Rp | 11500
| PC 500 (bcm/hour) |  |  | (fuel include in contract)
| PRODUCTION excavator |  | 1973.0667 | Total Fuel Consumption | Liter | 240666.2104
COST RENT + FUEL
| COST OB REMOVAL | Rp | 5129695377.3567 | COST OB / TON | 40.64% | 59659.7954 | 4.018
| COST QUARRY HAULING | Rp | 1186422072.9017 | COST QUARRY / TON | 9.399% | 13798.4213 | 0.92931
| COST DEVELOP ACT. | Rp | 0 | COST DEV / TON | 0% | 0 | 0
| COST ORE GETTING | Rp | 1506917780.5152 | COST ORE GETTING / TON | 11.94% | 17525.8763 | 1.1804
| COST ORE HAULING | Rp | 4540841500 | COST ORE HAULING / TON | 35.97% | 52811.2597 | 3.5568
| COST UNIT SUPPORT | Rp | 258778500 | COST SUPPORT / TON | 2.05% | 3009.6665 | 0.2027
[5 empty] | 100% | 146805.0193 | 9.8872
| TOTAL COST | Rp | 12622655230.7736 | COST / TON ORE |  | 146805.0193
|  |  |  | ( USD / Ton ) |  | 9.8872
| INCOME | Rp | 13405007884.8 | KURS/$ |  | 14848
|  |  |  | PRICE / TON ORE |  | 10.5
| RESULT | Rp | 782352654.0264
OKE…..

## SUMMARY MTD
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| 2022 | last year (2023) | january | february | march | april | may | june | july | august | september | october | november | december | TOTAL 2024
OVERBURDEN REMOVAL | 2593394.68 | 1762644.37 | 1 january: 96004.7; 2 february: 64356.6; 3 march: 103019.8; 4 april: 91039.4; 5 may: 124621.9 | 479042.4
ORE MINING | 2365922.32 | 2351389.83 | 1 january: 139218.55; 2 february: 135612.65; 3 march: 139849.34; 4 april: 37314.72; 5 may: 85982.45 | 537977.71
QUARRY MINING | 485042.22 | 231202.35 | 1 january: 20164.9; 2 february: 33195.1; 3 march: 25675.5; 4 april: 22698.1; 5 may: 15925.8 | 117659.4
STRIPING RATIO | 1.0961 | 0.74962 | 1 january: 0.6896; 2 february: 0.47456; 3 march: 0.73665; 4 april: 2.4398; 5 may: 1.4494 | 0.89045
ACH % OVERBURDEN |  | 78.27% | 1 january: 61.24%; 2 february: 45.74%; 3 march: 104%; 4 april: 100.8%; 5 may: 115% | 85.37%
ACH % ORE MINING |  | 76.81% | 1 january: 70.05%; 2 february: 74.6%; 3 march: 92.17%; 4 april: 24.73%; 5 may: 56.93% | 63.69%
ACH % QUARRY |  | 63.74% | 1 january: 64.31%; 2 february: 118%; 3 march: 129.6%; 4 april: 125.7%; 5 may: 73.5% | 102.2%
PRODUCTION excavator | 996.2529 | 247.7372 | 1 january: 80.9483; 2 february: 33.6118; 3 march: 70.804; 4 april: 74.5613; 5 may: 78.035 | 67.5921
COST OB REMOVAL | 117351549119.5926 | 89114970157.4923 | 1 january: 6960925765.638; 2 february: 5222995676.1753; 3 march: 5827686516.5355; 4 april: 4200363392.4252; 5 may: 5129695377.3567 | 27341666728.1308
COST QUARRY HAULING | 15778967244.1131 | 11003332333.604 | 1 january: 307546487.4077; 2 february: 1007714291.9115; 3 march: 1652176858.1483; 4 april: 1531554207.0122; 5 may: 1186422072.9017 | 5685413917.3814
COST DEVELOP ACT. | 279499500 | 1511876000 | 1 january: 29087910.5828; 2 february: 7937511.7301; 3 march: 4814495.4411; 4 april: 0; 5 may: 0 | 41839917.754
COST ORE GETTING | 36943314302.0272 | 29478347836.0073 | 1 january: 1659006090.9509; 2 february: 1909600441.3111; 3 march: 1805188806.0276; 4 april: 877810447.9217; 5 may: 1506917780.5152 | 7758523566.7264
COST ORE HAULING | 97545270500 | 100875347500 | 1 january: 8167942000; 2 february: 8818596000; 3 march: 6809658000; 4 april: 3762316000; 5 may: 4540841500 | 32099353500
COST UNIT SUPPORT | 4177854000 | 3796676000 | 1 january: 274029000; 2 february: 252883000; 3 march: 230297000; 4 april: 206696000; 5 may: 258778500 | 1222683500
TOTAL COST | 272076454665.7328 | 235780549827.1036 | 1 january: 17398537254.5794; 2 february: 17219726921.128; 3 march: 16329821676.1526; 4 april: 10578740047.3591; 5 may: 12622655230.7736 | 74149481129.9926
INCOME | 368856753377.28 | 366591080056.3199 | 1 january: 21704728819.2; 2 february: 21142554585.6; 3 march: 21803071503.36; 4 april: 5817514106.88; 5 may: 13405007884.8 | 83872876899.84
PROFIT | 96780298711.5471 | 130810530229.2163 | 1 january: 4306191564.6206; 2 february: 3922827664.472; 3 march: 5473249827.2074; 4 april: -4761225940.4791; 5 may: 782352654.0264 | 9723395769.8474
PERCENT COST | 73.76% | 64.32% | 1 january: 80.16%; 2 february: 81.45%; 3 march: 74.9%; 4 april: 181.8%; 5 may: 94.16% | 88.41%
PERCENT PROFIT | 26.24% | 35.68% | 1 january: 19.84%; 2 february: 18.55%; 3 march: 25.1%; 4 april: -81.84%; 5 may: 5.836% | 11.59%
FUEL RATIO (L/Ton) | 2.4824 | 2.1979 | 1 january: 1.9117; 2 february: 2.1518; 3 march: 2.2992; 4 april: 4.352; 5 may: 2.799 | 2.384
ACH % FUEL RATIO |  | 101.4% | 1 january: 137.6%; 2 february: 121.1%; 3 march: 120.4%; 4 april: 38.93%; 5 may: 66.69% | 96.93%
DAYS WORK | 367 | 365 | 1 january: 31; 2 february: 29; 3 march: 31; 4 april: 30; 5 may: 31 | 152
WORKING HOUR | 3303 | 3294 | 1 january: 279; 2 february: 261; 3 march: 279; 4 april: 270; 5 may: 279 | 1368
MECANICAL AVAILABILITY | 85% | 88.5% | 1 january: 92%; 2 february: 92%; 3 march: 92%; 4 april: 92%; 5 may: 92% | 92%
Total Fuel Consumption | 5873252.2234 | 5168095.4772 | 1 january: 266151; 2 february: 291807; 3 march: 321542; 4 april: 162394.1163; 5 may: 240666.2104 | 1282560.3267
ACH % FUEL CONSUMPTION |  | 132.8% | 1 january: 196.4%; 2 february: 162.3%; 3 march: 130.6%; 4 april: 157.4%; 5 may: 117.2% | 152.8%
COST / TON ORE | 127919.312 | 102888.0397 | 1 january: 124972.8377; 2 february: 126977.291; 3 march: 116767.2416; 4 april: 283500.4536; 5 may: 146805.0193 | 159804.5687
( USD / Ton ) | 8.7327 | 6.9294 | 1 january: 8.4168; 2 february: 8.5518; 3 march: 7.8642; 4 april: 19.0935; 5 may: 9.8872 | 10.7627
NOTE
ACH % OVERBURDEN
ACH % ORE MINING | KONDISI MEDAN YANG CUKUP BAIK, SEHINGGA KURANG NYA PENGGUNAAN QUARRY UNTUK MAINTENANCE JALAN
ACH % QUARRY | ADANYA PENGURANGAN UNIT, DAN PENGALIHAN STOCKPILE DARI KM 7 KE PIT, SEHINGGA PERLU PENYESUAIAN METODE KERJA
ACH % FUEL RATIO | FUEL RATIO MENINGKAT DIKARENAKAN PRODUKSI ORE YANG MENURUN
ACH % FUEL CONSUMPTION | KARENA KURANG NYA KEGIATAN SEHINGGA KONSUMSI FUEL MENJADI KURANG

## REPORT unit OB
COST UNIT OVERBURDEN
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 500 - 01 | 195 | 1000000 | 195000000 | 5647.7778 | 64949444.4444 | 28.963 | 259949444.4444 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 01 | K
2 | KOMATSU PC 500 - 02 | 211 | 1000000 | 211000000 | 4790.6591 | 55092579.5455 | 22.7045 | 266092579.5455 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 02 | K
3 | KOMATSU PC 500 - 04 | 61 | 1000000 | 61000000 | 1867.0231 | 21470765.896 | 30.6069 | 82470765.896 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 04 | K
4 | KOMATSU PC 400 - 02 | 14 | 950000 | 13300000 | 526 | 6049000 | 37.5714 | 19349000 | kbm | PC 400 LC SE-8 | KOMATSU PC 400 - 02 | K
5 | KOMATSU PC 300 - 07 | 51 | 400000 | 20400000 | 763 | 8774500 | 14.9608 | 29174500 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 07 | K
6 | KOMATSU PC 300 - 10 | 89 | 400000 | 35600000 | 1951.2576 | 22439462.1212 | 21.9242 | 58039462.1212 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 10 | K
7 | KOMATSU PC 300 - 11 | 30 | 400000 | 12000000 | 583.6364 | 6711818.1818 | 19.4545 | 18711818.1818 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 11 | K
8 | KOMATSU PC 300 - 14 | 37 | 400000 | 14800000 | 967.0376 | 11120931.9249 | 26.1362 | 25920931.9249 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 14 | K
9 | KOMATSU PC 300 - 15 | 41 | 400000 | 16400000 | 945.7828 | 10876502.2624 | 23.0679 | 27276502.2624 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 15 | K
10 | KOBELCO SK 330 - 10 | 14 | 400000 | 5600000 | 240.4316 | 2764963.1579 | 17.1737 | 8364963.1579 | kbm | SK 330-8 | KOBELCO SK 330 - 10 | K
11 | KOBELCO SK 330 - 11 | 15 | 400000 | 6000000 | 205.6434 | 2364898.8971 | 13.7096 | 8364898.8971 | kbm | SK 330-8 | KOBELCO SK 330 - 11 | K
12 | KOBELCO SK 330 - 12 | 7 | 400000 | 2800000 | 124.3604 | 1430144.1441 | 17.7658 | 4230144.1441 | kbm | SK 330-8 | KOBELCO SK 330 - 12 | K
13 | KOMATSU PC 200 - 12 | 7 | 275000 | 1925000 | 103.2982 | 1187928.8991 | 14.7569 | 3112928.8991 | kbm | PC 200-8 MO | KOMATSU PC 200 - 12 | K
14 | KOMATSU PC 200 - 20 | 8 | 275000 | 2200000 | 109.6857 | 1261385.7143 | 13.7107 | 3461385.7143 | kbm | PC 200-8 MO | KOMATSU PC 200 - 20 | K
15 | KOMATSU PC 200 - 22 | 19 | 275000 | 5225000 | 289.3542 | 3327572.9167 | 15.2292 | 8552572.9167 | kbm | PC 200-8 MO | KOMATSU PC 200 - 22 | K
16 | KOBELCO SK 200 - 10 | 32 | 275000 | 8800000 | 448.8122 | 5161340.1015 | 14.0254 | 13961340.1015 | kbm | SK 200-8 SX | KOBELCO SK 200 - 10 | K
17 | KOBELCO SK 200 - 11 | 21 | 275000 | 5775000 | 206.3478 | 2373000 | 9.8261 | 8148000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 11 | K
18 | KOBELCO SK 200 - 13 | 21 | 275000 | 5775000 | 245.9471 | 2828391.1765 | 11.7118 | 8603391.1765 | kbm | SK 200-8 SX | KOBELCO SK 200 - 13 | K
19 | KOBELCO SK 200 - 20 | 29 | 275000 | 7975000 | 427.9869 | 4921849.6732 | 14.7582 | 12896849.6732 | kbm | SK 200-8 SX | KOBELCO SK 200 - 20 | K
20 | KOMATSU HM 400 - 11 | 99 | 1424304.3668 | 141006132.3121 | 1625.8 | 18696700 | 16.4222 | 159702832.3121 | kbm | HM 400-3R | KOMATSU HM 400 - 11 | K
21 | KOMATSU HM 400 - 12 | 29 | 1424304.3668 | 41304826.6369 | 675.2857 | 7765785.7143 | 23.2857 | 49070612.3511 | kbm | HM 400-3R | KOMATSU HM 400 - 12 | K
22 | KOMATSU HM 400 - 13 | 155 | 1424304.3668 | 220767176.8522 | 2638.5429 | 30343242.8571 | 17.0229 | 251110419.7093 | kbm | HM 400-3R | KOMATSU HM 400 - 13 | K
23 | KOMATSU HM 400 - 14 | 131 | 1424304.3668 | 186583872.0493 | 2096 | 24104000 | 16 | 210687872.0493 | kbm | HM 400-3R | KOMATSU HM 400 - 14 | K
24 | KOMATSU HM 400 - 15 | 121 | 1424304.3668 | 172340828.3814 | 2008.1027 | 23093181.5068 | 16.5959 | 195434009.8882 | kbm | HM 400-3R | KOMATSU HM 400 - 15 | K
25 | KOMATSU HM 400 - 16 | 175 | 1424304.3668 | 249253264.188 | 3344.337 | 38459875.6906 | 19.1105 | 287713139.8786 | kbm | HM 400-3R | KOMATSU HM 400 - 16 | K
26 | KOMATSU HM 400 - 17 | 163 | 1424304.3668 | 232161611.7865 | 2270.4123 | 26109741.7062 | 13.9289 | 258271353.4927 | kbm | HM 400-3R | KOMATSU HM 400 - 17 | K
27 | KOMATSU HM 400 - 18 | 159 | 1424304.3668 | 226464394.3194 | 2847.3793 | 32744862.069 | 17.908 | 259209256.3883 | kbm | HM 400-3R | KOMATSU HM 400 - 18 | K
28 | KOMATSU HM 400 - 19 | 133 | 1424304.3668 | 189432480.7829 | 2237.4862 | 25731091.1602 | 16.8232 | 215163571.9431 | kbm | HM 400-3R | KOMATSU HM 400 - 19 | K
29 | KOMATSU HM 400 - 20 | 36 | 1424304.3668 | 51274957.2044 | 500.5565 | 5756400 | 13.9043 | 57031357.2044 | kbm | HM 400-3R | KOMATSU HM 400 - 20 | K
30 | KOMATSU HM 400 - 21 | 171 | 1424304.3668 | 243556046.7208 | 3524.8674 | 40535975.1381 | 20.6133 | 284092021.8589 | kbm | HM 400-3R | KOMATSU HM 400 - 21 | K
31 | KOMATSU HM 400 - 22 | 92 | 1424304.3668 | 131036001.7445 | 1557.8031 | 17914735.7513 | 16.9326 | 148950737.4958 | kbm | HM 400-3R | KOMATSU HM 400 - 22 | K
32 | KOMATSU HM 400 - 23 | 133 | 1424304.3668 | 189432480.7829 | 2767.1189 | 31821867.5676 | 20.8054 | 221254348.3504 | kbm | HM 400-3R | KOMATSU HM 400 - 23 | K
33 | KOMATSU HM 400 - 24 | 156 | 1424304.3668 | 222191481.219 | 2380.1143 | 27371314.2857 | 15.2571 | 249562795.5047 | kbm | HM 400-3R | KOMATSU HM 400 - 24 | K
34 | KOMATSU HM 400 - 25 | 151 | 1424304.3668 | 215069959.3851 | 2471.676 | 28424273.743 | 16.3687 | 243494233.1281 | kbm | HM 400-3R | KOMATSU HM 400 - 25 | K
35 | KOMATSU DOZER D65 - 10 | 164 | 425000 | 69700000 | 4005.7471 | 46066091.954 | 24.4253 | 115766091.954 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 10 | K
36 | KOMATSU DOZER D65 - 13 | 78 | 425000 | 33150000 | 1102 | 12673000 | 14.1282 | 45823000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 13 | K
37 | KOMATSU DOZER D65 - 15 | 225 | 425000 | 95625000 | 3726 | 42849000 | 16.56 | 138474000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 15 | K
38 | KOMATSU DOZER D65 - 16 | 270 | 425000 | 114750000 | 5049 | 58063500 | 18.7 | 172813500 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 16 | K
39 | KOMATSU DOZER D65 - 18 | 228 | 425000 | 96900000 | 4457 | 51255500 | 19.5482 | 148155500 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 18 | K
40 | KOMATSU DOZER D85SS - 06 | 110 | 425000 | 46750000 | 1498.6667 | 17234666.6667 | 13.6242 | 63984666.6667 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 06 | K
41 | KOMATSU DOZER D85SS - 10 | 105 | 425000 | 44625000 | 1537.3585 | 17679622.6415 | 14.6415 | 62304622.6415 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 10 | K
42 | KOMATSU DOZER D85SS - 18 | 174 | 425000 | 73950000 | 1770.7535 | 20363665.1163 | 10.1767 | 94313665.1163 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 18 | K
43 | KOMATSU DOZER D85SS - 20 | 219 | 425000 | 93075000 | 4535.326 | 52156248.8987 | 20.7093 | 145231248.8987 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 20 | K
44 | GRADER GD535 - 10 | 219 | 350000 | 76650000 | 2830.5991 | 32551889.8678 | 12.9251 | 109201889.8678 | kbm | GD 511 A-1 | GRADER GD535 - 10 | K
45 | SAKAI - 02 | 24 | 220000 | 5280000 | 147.4682 | 1695884.3931 | 6.1445 | 6975884.3931 | kbm | SV 525 D | SAKAI - 02 | K
46 | SAKAI - 07 | 214 | 220000 | 47080000 | 1279.1802 | 14710572.0721 | 5.9775 | 61790572.0721 | kbm | SV 525 D | SAKAI - 07 | K
47 | LOADER - 02 | 9 | 766205.7657 | 6895851.8917 | 46.5081 | 534843.2432 | 5.1676 | 7430695.135 | kbm | WA 380-3 | LOADER - 02 | K
TOTAL |  | 4845 | 762144.0695 | 4147881366.2569 | 85375.1314 | 981814011.0999 | 17.6213 | 5129695377.3567
KURS USD | 14848
FUEL PRICE | 11500

## REPORT unit QUARRY
COST UNIT QUARRY
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 500 - 01 | 21 | 1000000 | 21000000 | 608.2222 | 6994555.5556 | 28.963 | 27994555.5556 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 01 | K
2 | KOMATSU PC 500 - 02 | 9 | 1000000 | 9000000 | 204.3409 | 2349920.4545 | 22.7045 | 11349920.4545 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 02 | K
3 | KOMATSU PC 500 - 04 | 112 | 1000000 | 112000000 | 3427.9769 | 39421734.104 | 30.6069 | 151421734.104 | kbm | PC 500 LCE-10R | KOMATSU PC 500 - 04 | K
4 | KOMATSU PC 300 - 10 | 29 | 400000 | 11600000 | 635.803 | 7311734.8485 | 21.9242 | 18911734.8485 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 10 | K
5 | KOMATSU PC 300 - 14 | 46 | 400000 | 18400000 | 1202.2629 | 13826023.4742 | 26.1362 | 32226023.4742 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 14 | K
6 | KOMATSU PC 300 - 15 | 7 | 400000 | 2800000 | 161.4751 | 1856963.8009 | 23.0679 | 4656963.8009 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 15 | K
7 | KOBELCO SK 330 - 12 | 19 | 400000 | 7600000 | 337.5495 | 3881819.8198 | 17.7658 | 11481819.8198 | kbm | SK 330-8 | KOBELCO SK 330 - 12 | K
8 | KOMATSU PC 200 - 20 | 8 | 275000 | 2200000 | 109.6857 | 1261385.7143 | 13.7107 | 3461385.7143 | kbm | PC 200-8 MO | KOMATSU PC 200 - 20 | K
9 | KOBELCO SK 200 - 13 | 3 | 275000 | 825000 | 35.1353 | 404055.8824 | 11.7118 | 1229055.8824 | kbm | SK 200-8 SX | KOBELCO SK 200 - 13 | K
10 | KOMATSU HM 400 - 11 | 32 | 1424304.3668 | 45577739.7372 | 525.5111 | 6043377.7778 | 16.4222 | 51621117.515 | kbm | HM 400-3R | KOMATSU HM 400 - 11 | K
11 | KOMATSU HM 400 - 12 | 6 | 1424304.3668 | 8545826.2007 | 139.7143 | 1606714.2857 | 23.2857 | 10152540.4864 | kbm | HM 400-3R | KOMATSU HM 400 - 12 | K
12 | KOMATSU HM 400 - 13 | 20 | 1424304.3668 | 28486087.3358 | 340.4571 | 3915257.1429 | 17.0229 | 32401344.4786 | kbm | HM 400-3R | KOMATSU HM 400 - 13 | K
13 | KOMATSU HM 400 - 14 | 21 | 1424304.3668 | 29910391.7026 | 336 | 3864000 | 16 | 33774391.7026 | kbm | HM 400-3R | KOMATSU HM 400 - 14 | K
14 | KOMATSU HM 400 - 15 | 25 | 1424304.3668 | 35607609.1697 | 414.8973 | 4771318.4932 | 16.5959 | 40378927.6629 | kbm | HM 400-3R | KOMATSU HM 400 - 15 | K
15 | KOMATSU HM 400 - 16 | 6 | 1424304.3668 | 8545826.2007 | 114.663 | 1318624.3094 | 19.1105 | 9864450.5101 | kbm | HM 400-3R | KOMATSU HM 400 - 16 | K
16 | KOMATSU HM 400 - 17 | 48 | 1424304.3668 | 68366609.6058 | 668.5877 | 7688758.2938 | 13.9289 | 76055367.8997 | kbm | HM 400-3R | KOMATSU HM 400 - 17 | K
17 | KOMATSU HM 400 - 18 | 15 | 1424304.3668 | 21364565.5018 | 268.6207 | 3089137.931 | 17.908 | 24453703.4329 | kbm | HM 400-3R | KOMATSU HM 400 - 18 | K
18 | KOMATSU HM 400 - 19 | 48 | 1424304.3668 | 68366609.6058 | 807.5138 | 9286408.8398 | 16.8232 | 77653018.4456 | kbm | HM 400-3R | KOMATSU HM 400 - 19 | K
19 | KOMATSU HM 400 - 20 | 53 | 1424304.3668 | 75488131.4398 | 736.9304 | 8474700 | 13.9043 | 83962831.4398 | kbm | HM 400-3R | KOMATSU HM 400 - 20 | K
20 | KOMATSU HM 400 - 21 | 10 | 1424304.3668 | 14243043.6679 | 206.1326 | 2370524.8619 | 20.6133 | 16613568.5298 | kbm | HM 400-3R | KOMATSU HM 400 - 21 | K
21 | KOMATSU HM 400 - 22 | 101 | 1424304.3668 | 143854741.0456 | 1710.1969 | 19667264.2487 | 16.9326 | 163522005.2943 | kbm | HM 400-3R | KOMATSU HM 400 - 22 | K
22 | KOMATSU HM 400 - 23 | 52 | 1424304.3668 | 74063827.073 | 1081.8811 | 12441632.4324 | 20.8054 | 86505459.5054 | kbm | HM 400-3R | KOMATSU HM 400 - 23 | K
23 | KOMATSU HM 400 - 24 | 19 | 1424304.3668 | 27061782.969 | 289.8857 | 3333685.7143 | 15.2571 | 30395468.6833 | kbm | HM 400-3R | KOMATSU HM 400 - 24 | K
24 | KOMATSU HM 400 - 25 | 28 | 1424304.3668 | 39880522.2701 | 458.324 | 5270726.257 | 16.3687 | 45151248.5271 | kbm | HM 400-3R | KOMATSU HM 400 - 25 | K
25 | KOMATSU DOZER D65 - 10 | 10 | 425000 | 4250000 | 244.2529 | 2808908.046 | 24.4253 | 7058908.046 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 10 | K
26 | KOMATSU DOZER D85SS - 06 | 55 | 425000 | 23375000 | 749.3333 | 8617333.3333 | 13.6242 | 31992333.3333 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 06 | K
27 | KOMATSU DOZER D85SS - 10 | 54 | 425000 | 22950000 | 790.6415 | 9092377.3585 | 14.6415 | 32042377.3585 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 10 | K
28 | KOMATSU DOZER D85SS - 18 | 28 | 425000 | 11900000 | 284.9488 | 3276911.6279 | 10.1767 | 15176911.6279 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 18 | K
29 | KOMATSU DOZER D85SS - 20 | 8 | 425000 | 3400000 | 165.674 | 1905251.1013 | 20.7093 | 5305251.1013 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 20 | K
30 | GRADER GD535 - 10 | 8 | 350000 | 2800000 | 103.4009 | 1189110.1322 | 12.9251 | 3989110.1322 | kbm | GD 511 A-1 | GRADER GD535 - 10 | K
31 | SAKAI - 02 | 149 | 220000 | 32780000 | 915.5318 | 10528615.6069 | 6.1445 | 43308615.6069 | kbm | SV 525 D | SAKAI - 02 | K
32 | SAKAI - 07 | 8 | 220000 | 1760000 | 47.8198 | 549927.9279 | 5.9775 | 2309927.9279 | kbm | SV 525 D | SAKAI - 07 | K
TOTAL |  | 1058 | 919673.9219 | 978003313.5256 | 18123.3704 | 208418759.3761 | 17.1298 | 1186422072.9017
KURS USD | 14848
FUEL PRICE | 11500

## REPORT unit DEVELOP
COST UNIT DEVELOPT
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 200 - 14 |  | 275000 | 0 |  | 0 | 0 | 0 | kbm | PC 200-8 MO | KOMATSU PC 200 - 14 | K
2 | KOMATSU DOZER D85SS - 17 |  | 425000 | 0 |  | 0 | 0 | 0 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 17 | K
TOTAL |  | 0 | 350000 | 0 | 0 | 0 | 0 | 0
KURS USD | 14848
FUEL PRICE | 11500

## REPORT unit ORE GETTING
COST UNIT ORE GETTING
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 300 - 10 | 14 | 400000 | 5600000 | 306.9394 | 3529803.0303 | 21.9242 | 9129803.0303 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 10 | K
2 | KOMATSU PC 300 - 11 | 14 | 400000 | 5600000 | 272.3636 | 3132181.8182 | 19.4545 | 8732181.8182 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 11 | K
3 | KOMATSU PC 300 - 14 | 130 | 400000 | 52000000 | 3397.6995 | 39073544.6009 | 26.1362 | 91073544.6009 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 14 | K
4 | KOMATSU PC 300 - 15 | 173 | 400000 | 69200000 | 3990.7421 | 45893533.9367 | 23.0679 | 115093533.9367 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 15 | K
5 | KOBELCO SK 330 - 10 | 176 | 400000 | 70400000 | 3022.5684 | 34759536.8421 | 17.1737 | 105159536.8421 | kbm | SK 330-8 | KOBELCO SK 330 - 10 | K
6 | KOBELCO SK 330 - 11 | 257 | 400000 | 102800000 | 3523.3566 | 40518601.1029 | 13.7096 | 143318601.1029 | kbm | SK 330-8 | KOBELCO SK 330 - 11 | K
7 | KOBELCO SK 330 - 12 | 196 | 400000 | 78400000 | 3482.0901 | 40044036.036 | 17.7658 | 118444036.036 | kbm | SK 330-8 | KOBELCO SK 330 - 12 | K
8 | KOMATSU PC 200 - 12 | 211 | 275000 | 58025000 | 3113.7018 | 35807571.1009 | 14.7569 | 93832571.1009 | kbm | PC 200-8 MO | KOMATSU PC 200 - 12 | K
9 | KOMATSU PC 200 - 16 | 245 | 275000 | 67375000 | 3251 | 37386500 | 13.2694 | 104761500 | kbm | PC 200-8 MO | KOMATSU PC 200 - 16 | K
10 | KOMATSU PC 200 - 20 | 264 | 275000 | 72600000 | 3619.6286 | 41625728.5714 | 13.7107 | 114225728.5714 | kbm | PC 200-8 MO | KOMATSU PC 200 - 20 | K
11 | KOMATSU PC 200 - 22 | 221 | 275000 | 60775000 | 3365.6458 | 38704927.0833 | 15.2292 | 99479927.0833 | kbm | PC 200-8 MO | KOMATSU PC 200 - 22 | K
12 | KOBELCO SK 200 - 10 | 165 | 275000 | 45375000 | 2314.1878 | 26613159.8985 | 14.0254 | 71988159.8985 | kbm | SK 200-8 SX | KOBELCO SK 200 - 10 | K
13 | KOBELCO SK 200 - 11 | 186 | 275000 | 51150000 | 1827.6522 | 21018000 | 9.8261 | 72168000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 11 | K
14 | KOBELCO SK 200 - 13 | 146 | 275000 | 40150000 | 1709.9176 | 19664052.9412 | 11.7118 | 59814052.9412 | kbm | SK 200-8 SX | KOBELCO SK 200 - 13 | K
15 | KOBELCO SK 200 - 15 | 266 | 275000 | 73150000 | 2652 | 30498000 | 9.9699 | 103648000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 15 | K
16 | KOBELCO SK 200 - 18 | 76 | 275000 | 20900000 | 866 | 9959000 | 11.3947 | 30859000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 18 | K
17 | KOBELCO SK 200 - 19 | 146 | 275000 | 40150000 | 1935 | 22252500 | 13.2534 | 62402500 | kbm | SK 200-8 SX | KOBELCO SK 200 - 19 | K
18 | KOBELCO SK 200 - 20 | 124 | 275000 | 34100000 | 1830.0131 | 21045150.3268 | 14.7582 | 55145150.3268 | kbm | SK 200-8 SX | KOBELCO SK 200 - 20 | K
19 | KOMATSU HM 400 - 11 | 4 | 1424304.3668 | 5697217.4672 | 65.6889 | 755422.2222 | 16.4222 | 6452639.6894 | kbm | HM 400-3R | KOMATSU HM 400 - 11 | K
20 | KOMATSU HM 400 - 20 | 26 | 1424304.3668 | 37031913.5365 | 361.513 | 4157400 | 13.9043 | 41189313.5365 | kbm | HM 400-3R | KOMATSU HM 400 - 20 | K
TOTAL |  | 3040 | 433680.4367 | 990479131.0037 | 44907.7087 | 516438649.5115 | 14.7723 | 1506917780.5152
KURS USD | 14848
FUEL PRICE | 11500
129328.7087

## REPORT unit DT HAUL
COST UNIT HAULING
NO | UNIT | TONNAGE |  | RENT |  | FUEL CONSUMPTION |  | RATIO |  |  | GRAND TOTAL COST |  | DESC. | TYPE
|  | Weight Bridge |  | Rate | Total | Fuel | Total
|  | Tonnage | Retase | ($/hour) |  | (liter) |  | (liter/ton) | (ton/ret) | (liter/ret)
1 | HONGYANG 500 | 1372.55 | 25 | 500000 | 105000000 | 1323 | 15214500 | 0.9639 | 54.902 | 52.92 | 120214500 | 213986035.2 | ore hauling kbm | HONGYAN/12 | HONGYANG 500
2 | HONGYANG 501 | 3690.71 | 67 | 500000 | 105000000 | 3568 | 41032000 | 0.96675 | 55.0852 | 53.2537 | 146032000 | 575396451.84 | ore hauling kbm | HONGYAN/12 | HONGYANG 501
3 | HONGYANG 502 | 2630.43 | 48 | 500000 | 105000000 | 2225 | 25587500 | 0.84587 | 54.8006 | 46.3542 | 130587500 | 410094558.72 | ore hauling kbm | HONGYAN/12 | HONGYANG 502
4 | HONGYANG 503 | 3152.68 | 56 | 500000 | 105000000 | 3264 | 37536000 | 1.0353 | 56.2979 | 58.2857 | 142536000 | 491515422.72 | ore hauling kbm | HONGYAN/12 | HONGYANG 503
5 | HONGYANG 504 | 2719.92 | 48 | 500000 | 105000000 | 2888 | 33212000 | 1.0618 | 56.665 | 60.1667 | 138212000 | 424046407.68 | ore hauling kbm | HONGYAN/12 | HONGYANG 504
6 | HONGYANG 505 | 2598.61 | 46 | 500000 | 105000000 | 2735 | 31452500 | 1.0525 | 56.4915 | 59.4565 | 136452500 | 405133693.44 | ore hauling kbm | HONGYAN/12 | HONGYANG 505
7 | HONGYANG 506 | 2977.92 | 52 | 500000 | 105000000 | 2905 | 33407500 | 0.97551 | 57.2677 | 55.8654 | 138407500 | 464269639.68 | ore hauling kbm | HONGYAN/12 | HONGYANG 506
8 | HONGYANG 507 | 1932.18 | 35 | 500000 | 105000000 | 2053 | 23609500 | 1.0625 | 55.2051 | 58.6571 | 128609500 | 301234590.72 | ore hauling kbm | HONGYAN/12 | HONGYANG 507
9 | HONGYANG 508 | 3262.19 | 57 | 500000 | 105000000 | 3030 | 34845000 | 0.92882 | 57.2314 | 53.1579 | 139845000 | 508588469.76 | ore hauling kbm | HONGYAN/12 | HONGYANG 508
10 | HONGYANG 509 | 2364.01 | 42 | 500000 | 105000000 | 2427 | 27910500 | 1.0266 | 56.286 | 57.7857 | 132910500 | 368558615.04 | ore hauling kbm | HONGYAN/12 | HONGYANG 509
11 | HONGYANG 510 | 3458.77 | 61 | 500000 | 105000000 | 3365 | 38697500 | 0.97289 | 56.7011 | 55.1639 | 143697500 | 539236078.08 | ore hauling kbm | HONGYAN/12 | HONGYANG 510
12 | HONGYANG 511 | 2637.69 | 47 | 500000 | 105000000 | 2537 | 29175500 | 0.96183 | 56.1211 | 53.9787 | 134175500 | 411226421.76 | ore hauling kbm | HONGYAN/12 | HONGYANG 511
13 | HONGYANG 512 | 2664.64 | 47 | 500000 | 105000000 | 2903 | 33384500 | 1.0895 | 56.6945 | 61.766 | 138384500 | 415428034.56 | ore hauling kbm | HONGYAN/12 | HONGYANG 512
14 | HONGYANG 513 | 237.98 | 4 | 500000 | 105000000 | 537 | 6175500 | 2.2565 | 59.495 | 134.25 | 111175500 | 37102033.92 | ore hauling kbm | HONGYAN/12 | HONGYANG 513
15 | HONGYANG 514 | 2088.59 | 38 | 500000 | 105000000 | 2334 | 26841000 | 1.1175 | 54.9629 | 61.4211 | 131841000 | 325619535.36 | ore hauling kbm | HONGYAN/12 | HONGYANG 514
16 | HONGYANG 517 | 2595.35 | 46 | 500000 | 105000000 | 2434 | 27991000 | 0.93783 | 56.4207 | 52.913 | 132991000 | 404625446.4 | ore hauling kbm | HONGYAN/12 | HONGYANG 517
17 | HONGYANG 518 | 1018.89 | 18 | 500000 | 105000000 | 950 | 10925000 | 0.93239 | 56.605 | 52.7778 | 115925000 | 158849026.56 | ore hauling kbm | HONGYAN/12 | HONGYANG 518
18 | HONGYANG 519 | 2945.76 | 52 | 500000 | 105000000 | 2663 | 30624500 | 0.90401 | 56.6492 | 51.2115 | 135624500 | 459255767.04 | ore hauling kbm | HONGYAN/12 | HONGYANG 519
19 | HONGYANG 520 | 3970.08 | 71 | 500000 | 105000000 | 3965 | 45597500 | 0.99872 | 55.9166 | 55.8451 | 150597500 | 618951352.32 | ore hauling kbm | HONGYAN/12 | HONGYANG 520
20 | HONGYANG 521 | 3724.26 | 66 | 500000 | 105000000 | 3392 | 39008000 | 0.91078 | 56.4282 | 51.3939 | 144008000 | 580627031.04 | ore hauling kbm | HONGYAN/12 | HONGYANG 521
21 | HONGYANG 522 | 2924.72 | 52 | 500000 | 105000000 | 2942 | 33833000 | 1.0059 | 56.2446 | 56.5769 | 138833000 | 455975546.88 | ore hauling kbm | HONGYAN/12 | HONGYANG 522
22 | HONGYANG 523 | 1284.42 | 22 | 500000 | 105000000 | 1208 | 13892000 | 0.9405 | 58.3827 | 54.9091 | 118892000 | 200246215.68 | ore hauling kbm | HONGYAN/12 | HONGYANG 523
23 | HONGYANG 524 | 1683.45 | 29 | 500000 | 105000000 | 1726 | 19849000 | 1.0253 | 58.05 | 59.5172 | 124849000 | 262456588.8 | ore hauling kbm | HONGYAN/12 | HONGYANG 524
24 | HONGYANG 525 | 2848.16 | 50 | 500000 | 105000000 | 3288 | 37812000 | 1.1544 | 56.9632 | 65.76 | 142812000 | 444039536.64 | ore hauling kbm | HONGYAN/12 | HONGYANG 525
25 | HONGYANG 526 | 3187.09 | 56 | 500000 | 105000000 | 2941 | 33821500 | 0.92279 | 56.9123 | 52.5179 | 138821500 | 496880079.36 | ore hauling kbm | HONGYAN/12 | HONGYANG 526
26 | HONGYANG 527 | 2547.53 | 45 | 500000 | 105000000 | 2731 | 31406500 | 1.072 | 56.6118 | 60.6889 | 136406500 | 397170117.12 | ore hauling kbm | HONGYAN/12 | HONGYANG 527
27 | HONGYANG 528 | 2662.32 | 47 | 500000 | 105000000 | 2602 | 29923000 | 0.97734 | 56.6451 | 55.3617 | 134923000 | 415066337.28 | ore hauling kbm | HONGYAN/12 | HONGYANG 528
28 | HONGYANG 529 | 2186.88 | 39 | 500000 | 105000000 | 2207 | 25380500 | 1.0092 | 56.0738 | 56.5897 | 130380500 | 340943339.52 | ore hauling kbm | HONGYAN/12 | HONGYANG 529
29 | HONGYANG 530 | 2266.77 | 42 | 500000 | 105000000 | 1973 | 22689500 | 0.8704 | 53.9707 | 46.9762 | 127689500 | 353398510.08 | ore hauling kbm | HONGYAN/12 | HONGYANG 530
30 | HONGYANG 531 | 1638.84 | 29 | 500000 | 105000000 | 1387 | 15950500 | 0.84633 | 56.5117 | 47.8276 | 120950500 | 255501711.36 | ore hauling kbm | HONGYAN/12 | HONGYANG 531
31 | HONGYANG 532 | 2718.44 | 48 | 500000 | 105000000 | 2401 | 27611500 | 0.88323 | 56.6342 | 50.0208 | 132611500 | 423815669.76 | ore hauling kbm | HONGYAN/12 | HONGYANG 532
32 | HONGYANG 533 | 2851.05 | 50 | 500000 | 105000000 | 2928 | 33672000 | 1.027 | 57.021 | 58.56 | 138672000 | 444490099.2 | ore hauling kbm | HONGYAN/12 | HONGYANG 533
33 | HONGYANG 534 | 2831.92 | 51 | 500000 | 105000000 | 2676 | 30774000 | 0.94494 | 55.5278 | 52.4706 | 135774000 | 441507655.68 | ore hauling kbm | HONGYAN/12 | HONGYANG 534
34 | HONGYANG 535 | 2307.65 | 40 | 500000 | 105000000 | 1913 | 21999500 | 0.82898 | 57.6913 | 47.825 | 126999500 | 359771865.6 | ore hauling kbm | HONGYAN/12 | HONGYANG 535
TOTAL |  | 85982.45 | 1526 |  | 3570000000 | 84421 | 970841500 | 0.98184 | 56.345 | 55.3218 | 4540841500 | 13405007884.8
HINO 700
KURS USD | 14848 |  |  |  |  | 129328.7087
FUEL PRICE | 11500
Min Charge | 210 | Hour

## REPORT unit LV & support
COST UNIT SUPPORT
NO | UNIT | RENT PER MONTH | FUEL CONSUMPTION |  | RATIO | GRAND TOTAL COST | DESC. | TYPE
|  |  | Fuel | Total
|  | (Rp/month) | (liter) |  | (liter/km)
1 | LV TRITON HITAM - 08 | 8000000 | 379 | 4358500 |  | 12358500 |  | LV | LV TRITON HITAM - 08
2 | LV PAJERO PUTIH - 09 | 8000000 | 141 | 1621500 |  | 9621500 |  | LV | LV PAJERO PUTIH - 09
3 | LV HILUX SILVER - 10 | 8000000 | 123 | 1414500 |  | 9414500 |  | LV | LV HILUX SILVER - 10
4 | LV TRITON PUTIH - 11 | 8000000 | 29 | 333500 |  | 8333500 |  | LV | LV TRITON PUTIH - 11
5 | LV HILUX HITAM - 11 | 8000000 | 347 | 3990500 |  | 11990500 |  | LV | LV HILUX HITAM - 11
6 | LV TRITON PUTIH - 12 | 8000000 | 436 | 5014000 |  | 13014000 |  | LV | LV TRITON PUTIH - 12
7 | LV HILUX SILVER - 17 | 8000000 | 400 | 4600000 |  | 12600000 |  | LV | LV HILUX SILVER - 17
8 | LV HILUX HITAM - 18 | 8000000 | 297 | 3415500 |  | 11415500 |  | LV | LV HILUX HITAM - 18
9 | LV HILUX SILVER - 19 | 8000000 | 68 | 782000 |  | 8782000 |  | LV | LV HILUX SILVER - 19
10 | LV HILUX SILVER - 20 | 8000000 | 119 | 1368500 |  | 9368500 |  | LV | LV HILUX SILVER - 20
11 | LV PAJERO SILVER - 21 | 8000000 | 234 | 2691000 |  | 10691000 |  | LV | LV PAJERO SILVER - 21
12 | LV HILUX PUTIH - 23 | 8000000 | 190 | 2185000 |  | 10185000 |  | LV | LV HILUX PUTIH - 23
13 | LV LC-HIJAU - 29 | 8000000 | 301 | 3461500 |  | 11461500 |  | LV | LV LC-HIJAU - 29
14 | LV TRITON PUTIH (SAFETY) - 30 | 8000000 | 392 | 4508000 |  | 12508000 |  | LV | LV TRITON PUTIH (SAFETY) - 30
15 | LV TRITON PUTIH - 32 | 8000000 | 378 | 4347000 |  | 12347000 |  | LV | LV TRITON PUTIH - 32
16 | MANHAUL - 02 | 210000 | 287 | 3300500 |  | 3510500 |  | FM 260 Ti | MANHAUL - 02
17 | FUEL TRUCK - 05 | 210000 | 1473 | 16939500 |  | 17149500 |  | FM 260 Ti | FUEL TRUCK - 05
18 | FUEL TRUCK - 06 | 210000 | 1050 | 12075000 |  | 12285000 |  | FM 260 Ti | FUEL TRUCK - 06
19 | TRUCK WELDER - LT-04 | 12000000 | 48 | 552000 |  | 12552000 |  | LT | TRUCK WELDER - LT-04
20 | TRUCK TYRE - LT-08 | 12000000 | 343 | 3944500 |  | 15944500 |  | LT | TRUCK TYRE - LT-08
21 | TRUCK MAINTENANCE - LT-09 | 12000000 | 338 | 3887000 |  | 15887000 |  | LT | TRUCK MAINTENANCE - LT-09
22 | TRUCK TYRE - LT-10 | 12000000 | 466 | 5359000 |  | 17359000 |  | LT | TRUCK TYRE - LT-10
TOTAL |  | 168630000 | 7839 | 90148500 | 0 | 258778500
KURS USD | 14848
FUEL PRICE | 11500

## HOUR METER (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
D | NO | ID UNIT | DAYLY REPORT HM | [30 empty] | TOTAL HM | TOTAL FUEL 1- 31
N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WEEK 1 | : | 0 | DAYLY REPORT HM 22: Di setujui oleh :; DAYLY REPORT HM 29: Di buat oleh :
WEEK 2 | : | 0
WEEK 3 | : | 0
WEEK 4 | : | 0 | bar: DAYLY REPORT HM 5
WEEK 5 | : | 0 | DAYLY REPORT HM 22: Internal Kontrol; DAYLY REPORT HM 29: MPE Team
0
BENAR

## FUEL UNIT (hidden)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| D | NO | ID UNIT | DAYLY REPORT FUEL | [30 empty] | TOTAL FUEL | TOTAL HM 1- 31
| N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
SM-BW 211-02 | TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
SM-BW 211-03 | TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
| TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
SM-D85ESS-08 | TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
| TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
| TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
| TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
| TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
| TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
| TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
| ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
| ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
| ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
| ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
| ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
| ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
| ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
| DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
| DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
| DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
| DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
| DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
| TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
| TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DAYLY REPORT FUEL 30: TOTAL FUEL | 0
| WEEK 1 | : | 0 | DAYLY REPORT FUEL 22: Di setujui oleh :; DAYLY REPORT FUEL 29: Di buat oleh :
| WEEK 2 | : | 0
| WEEK 3 | : | 0
| WEEK 4 | : | 0
| WEEK 5 | : | 0 | DAYLY REPORT FUEL 22: Internal Kontrol; DAYLY REPORT FUEL 29: MPE Team
0
BENAR

## list rate unit
RATE
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | unit | type
NO | UNIT | Ltr/Hr | Rent/Hr | Column1 | Column2 | Description | Column4 | Column5 | Column6 | Column7 |  | KOMATSU PC 500 - 01 | PC 500 LCE-10R
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  | KOMATSU PC 500 - 02 | PC 500 LCE-10R
|  |  | Unit Only (Internal) | Incl. Operator | Incl. Operator & Fuel | [6 empty] | KOMATSU PC 500 - 03 | PC 500 LCE-10R
1 | PC 195 LC-8 | 20 | 16.5432 | 19.5084 | 35.3704 | Excavator | 239875.7064 | 282871.4905 | 512871.4905 | 275000 | 200 | KOMATSU PC 500 - 04 | PC 500 LCE-10R
2 | PC 200-8 MO | 22 | 23.2254 | 26.1906 | 43.6389 | Excavator | 336767.7028 | 379763.4868 | 632763.4868 | 275000 | 200 | KOMATSU PC 400 - 01 | PC 400 LC SE-8
3 | PC 300 SE-8 | 30 | 41.2152 | 44.1804 | 69.5598 | Excavator | 597620.6927 | 640616.4768 | 1008616.4768 | 400000 | 300 | KOMATSU PC 400 - 03 | PC 400 LC SE-8
4 | PC 400 LC SE-8 | 38 | 58.29 | 61.6 | 87.81 | Excavator | 845205 | 893200 | 1273245 | 950000 | 400 | KOMATSU PC 400 - 04 | PC 400 LC SE-8
5 | PC 500 LCE-10R | 45 | 63.54 | 66.85 | 98.05 | Excavator | 921330 | 969325 | 1421725 | 1000000 |  | KOMATSU PC 400 - 05 | PC 400 LC SE-8
6 | SK 200-8 SX | 20 | 17.6502 | 20.6154 | 36.4775 | Excavator | 255927.8486 | 298923.6327 | 528923.6327 | 275000 | 200 | KOMATSU PC 400 - 06 | PC 400 LC SE-8
7 | SK 330-8 | 28 | 34.235 | 37.2002 | 59.4071 | Excavator | 496407.8395 | 539403.6235 | 861403.6235 | 400000 |  | KOMATSU PC 300 - 10 | PC 300 SE-8
8 | HM 400-3R | 30 | 98.2279 | 101.5379 | 127.7104 | Artic | 1424304.3668 | 1472300.1508 | 1851800.1508 | 1424304.3668 |  | KOMATSU PC 300 - 11 | PC 300 SE-8
9 | D 85 ESS-2 | 30 | 42.331 | 45.2962 | 69.0893 | Bulldozer | 613799.3709 | 656795.155 | 1001795.155 | 425000 |  | KOMATSU PC 300 - 12 | PC 300 SE-8
10 | D 65 P-12 | 33 | 42.7792 | 45.7445 | 71.9169 | Bulldozer | 620298.906 | 663294.6901 | 1042794.6901 | 425000 |  | KOMATSU PC 300 - 14 | PC 300 SE-8
11 | GD 511 A-1 | 15 | 32.851 | 35.8163 | 47.7128 | Grader | 476340.0889 | 519335.8729 | 691835.8729 | 350000 |  | KOMATSU PC 300 - 15 | PC 300 SE-8
12 | SV 525 D | 11 | 13.1981 | 16.1633 | 24.0943 | Compactor | 191372.0947 | 234367.8788 | 349367.8788 | 220000 |  | KOMATSU PC 300 - 16 | PC 300 SE-8
13 | BW 211 D-40 | 11 | 9.9397 | 12.9049 | 20.8359 | Compactor | 144125.031 | 187120.8151 | 302120.8151 | 220000 |  | KOMATSU PC 300 - 17 | PC 300 SE-8
14 | XG 6121 | 11 | 8.6243 | 11.5895 | 19.5206 | Compactor | 125052.5178 | 168048.3018 | 283048.3018 |  |  | KOBELCO SK 330 - 10 | SK 330-8
15 | XG 955-III | 20 | 12.8699 | 15.8352 | 31.6972 | Whell Loader | 186614.0656 | 229609.8497 | 459609.8497 |  |  | KOBELCO SK 330 - 11 | SK 330-8
16 | WA 380-3 | 20 | 34.0145 | 36.9797 | 52.8418 | Whell Loader | 493209.9817 | 536205.7657 | 766205.7657 | 766205.7657 |  | KOMATSU PC 200 - 11 | PC 200-8 MO
17 | FM 260 Ti | 15 | 17.3403 | 18.9483 | 30.0517 | Dump Truck | 251435.0252 | 274750.1408 | 435750.1408 | 210000 |  | KOMATSU PC 200 - 12 | PC 200-8 MO
18 | 700 Provia | 20 | 31.1718 | 32.9521 | 48.8142 | Dump Truck | 451990.7019 | 477805.8175 | 707805.8175 | 460000 |  | KOMATSU PC 200 - 14 | PC 200-8 MO
19 | 700 Provia/12 | 28 | 32.42 | 34.21 | 53.52 | Dump Truck | 470090 | 496045 | 776040 | 500000 |  | KOMATSU PC 200 - 15 | PC 200-8 MO
20 | HONGYAN/12 | 28 | 32.42 | 34.21 | 53.52 | Dump Truck | 470090 | 496045 | 776040 | 500000 |  | KOMATSU DOZER D85SS - 10 | D 85 ESS-2
21 | LV | 10 |  |  |  |  | 8000000 |  |  | 8000000 |  | KOMATSU PC 200 - 16 | PC 200-8 MO
22 | GENSET | 4 |  |  |  |  | 3000000 |  |  | 3000000 |  | KOMATSU PC 200 - 22 | PC 200-8 MO
23 | LT | 10 |  |  |  |  | 12000000 |  |  | 12000000 |  | KOMATSU PC 200 - 23 | PC 200-8 MO
RATE MOBILISASI | [11 empty] | KOMATSU PC 200 - 25 | PC 200-8 MO
[9 empty] | source data ( owning & operating cost) |  |  | KOMATSU PC 195 - 01 | PC 195 LC-8
NO | UNIT | $ / KM | [9 empty] | KOBELCO SK 200 - 07 | SK 200-8 SX
1 | PC 400 | 24 | [9 empty] | KOBELCO SK 200 - 08 | SK 200-8 SX
2 | PC 300 | 16 | [9 empty] | KOBELCO SK 200 - 10 | SK 200-8 SX
3 | PC 200 | 8 | [9 empty] | KOBELCO SK 200 - 11 | SK 200-8 SX
4 | BULLDOZER | 16 | [9 empty] | KOBELCO SK 200 - 13 | SK 200-8 SX
5 | COMPACTOR | 8 | [9 empty] | KOBELCO SK 200 - 15 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 16 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 18 | SK 200-8 SX
| 14652.34 | [10 empty] | KOBELCO SK 200 - 19 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 20 | SK 200-8 SX
[12 empty] | KOMATSU HM 400 - 01 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 02 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 04 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 05 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 06 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 07 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 08 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 09 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 10 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 11 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 12 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 13 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 14 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 15 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 16 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 17 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 18 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 19 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 20 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 21 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 22 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 23 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 24 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 25 | HM 400-3R
[12 empty] | KOMATSU DOZER D65 - 05 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 10 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 11 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 12 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 13 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 15 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 16 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 18 | D 65 P-12
[12 empty] | KOMATSU DOZER D85SS - 11 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 14 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 17 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 18 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 20 | D 85 ESS-2
[12 empty] | GRADER GD535 - 03 | GD 511 A-1
[12 empty] | LOADER WA380 - 02 | WA 380-3
[12 empty] | SAKAI - 02 | SV 525 D
[12 empty] | SAKAI - 03 | SV 525 D
[12 empty] | SAKAI - 07 | SV 525 D
[12 empty] | LV HILUX HITAM - 05 | LV
[12 empty] | LV PAJERO PUTIH - 06 | LV
[12 empty] | LV TRITON HITAM - 08 | LV
[12 empty] | LV PAJERO PUTIH - 09 | LV
[12 empty] | LV HILUX SILVER - 10 | LV
[12 empty] | LV TRITON HITAM - 10 | LV
[12 empty] | LV TRITON PUTIH - 11 | LV
[12 empty] | LV HILUX HITAM - 11 | LV
[12 empty] | LV TRITON PUTIH - 12 | LV
[12 empty] | LV PAJERO HITAM - 15 | LV
[12 empty] | LV HILUX SILVER - 17 | LV
[12 empty] | LV HILUX HITAM - 18 | LV
[12 empty] | LV HILUX SILVER - 19 | LV
[12 empty] | LV PAJERO SILVER - 21 | LV
[12 empty] | LV HILUX PUTIH - 23 | LV
[12 empty] | LV TRITON PUTIH - 27 | LV
[12 empty] | LV LC-HIJAU - 29 | LV
[12 empty] | LV TRITON PUTIH (SAFETY) - 30 | LV
[12 empty] | LV TRITON PUTIH - 31 | LV
[12 empty] | LV TRITON PUTIH - 32 | LV
[12 empty] | MANHAUL - 02 | FM 260 Ti
[12 empty] | BUS APP - 03 | LT
[12 empty] | FUEL TRUCK - 03 | FM 260 Ti
[12 empty] | FUEL TRUCK - 05 | FM 260 Ti
[12 empty] | FUEL TRUCK - 06 | FM 260 Ti
[12 empty] | TRUCK WELDER - LT-04 | LT
[12 empty] | TRUCK TYRE - LT-08 | LT
[12 empty] | TRUCK MAINTENANCE - LT-09 | LT
[12 empty] | TRUCK TYRE - LT-10 | LT
MEKANIK CAMP
[12 empty] | LV HILUX HITAM - 04 | LV
Kompresor Tyre
[12 empty] | KOMATSU DOZER D85SS - 06 | D 85 ESS-2
[12 empty] | KOMATSU PC 300 - 07 | PC 300 SE-8
[12 empty] | KOBELCO SK 330 - 12 | SK 330-8
[12 empty] | LV LC-SILVER - 24 | LV
[12 empty] | WELDER CAR | LT
[12 empty] | KOMATSU PC 200 - 21 | PC 200-8 MO
[12 empty] | KOMATSU PC 200 - 04 | PC 200-8 MO
[12 empty] | LV HLUX SILVER - 07 | LV
[12 empty] | LV HILUX SILVER - 20 | LV
[12 empty] | LV TRITON PUTIH - 28 | LV
WELDER CAMP
[12 empty] | KOMATSU PC 400 - 02 | PC 400 LC SE-8
[12 empty] | KOMATSU PC 300 - 02 | PC 300 SE-8
[12 empty] | LOADER - 02 | WA 380-3
[12 empty] | GRADER GD535 - 02 | GD 511 A-1
[12 empty] | KOMATSU PC 200 - 24 | PC 200-8 MO
[12 empty] | KOMATSU PC 200 - 20 | PC 200-8 MO
[12 empty] | LV LC-HIJAU - 22 | LV
[12 empty] | KOBELCO SK 200 - 17 | SK 200-8 SX
[12 empty] | GRADER GD535 - 10 | GD 511 A-1
[12 empty] | SAKAI - 06 | SV 525 D
GENSET CAMP
WATER TRUCK - 02