## SUMMARY
MINING COST (APRIL)
| SUMMARY BDM BLOK 8 NAKULA | April 2023 |  |  | CV. SENTOSA ABADI
|  | PLAN | ACTUAL | ACH % | DAYS WORK |  | 30 | days
| OVERBURDEN REMOVAL | 41511.7824 | 27308.81 | 65.79% | WORKING HOUR |  | 270 | hours
| ORE MINING | 86937.2928 | 56656.32 | 65.17% | PHYSICHAL AVAILIBILITY |  | 85% | PA
| QUARRY MINING | 4981.4139 | 7992.67 | 160.4%
| STRIPING RATIO | 0.57568 | 0.48201 | 119.4% | Fuel Price / liter |  | 0
| FUEL RATIO OVERALL (L/Ton) | 2.2102 | 2.07 | 106.8% | (fuel not include in contract)
| PC 400 (bcm/hour) |  |  |  | Total Fuel Consumption | PLAN | 159376.0548 | Liter
| PRODUCTION excavator | 348.14 | 497.2039 | 142.8% |  | ACTUAL | 117279.338 | Liter
[6 empty] | ACH % | 135.9%
| COST RENT + FUEL |  |  |  | COST ITEM / TON ORE
| COST OB REMOVAL | 1103086793.8723 |  |  | COST OB / TON | 21.95% | 19469.7925 | 1.3113
| COST QUARRY HAULING | 446450000 |  |  | COST QUARRY / TON | 8.883% | 7879.9682 | 0.53071
| COST DEVELOP ACT. | 0 |  |  | COST DEV / TON | 0% | 0 | 0
| COST ORE GETTING | 445795000 |  |  | COST ORE GETTING / TON | 8.87% | 7868.4073 | 0.52993
| COST ORE HAULING | 2994600000 |  |  | COST ORE HAULING / TON | 59.58% | 52855.5332 | 3.5598
| COST UNIT SUPPORT | 36210000 |  |  | COST SUPPORT / TON | 0.7204% | 639.1167 | 0.043044
[6 empty] | 100% | 88712.8178 | 5.9747
| TOTAL COST | 5026141793.8723 |  |  | COST / TON ORE |  | 88712.8178
| INCOME | 6729864314.88 |  |  | ( USD / Ton ) |  | 5.9747
[5 empty] | KURS/$ |  | 14848
| RESULT | 1703722521.0077 |  |  | PRICE / TON ORE |  | 8
OKE…..

## SUMMARY MTD
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| last year (2022) | january | february | march | april | may | june | july | august | september | october | november | december | TOTAL 2022
OVERBURDEN REMOVAL | 25551.1 | 1 january: 23545.18; 2 february: 29931.98; 3 march: 18697.04; 4 april: 18697.04 | 90871.24
ORE MINING | 125448.88 | 1 january: 64719.62; 2 february: 76341.76; 3 march: 71048.76; 4 april: 71048.76 | 283158.9
QUARRY MINING | 12871.52 | 1 january: 746.51; 2 february: 647.58; 3 march: 7573.39; 4 april: 7573.39 | 16540.87
STRIPING RATIO | 0.20368 | 1 january: 0.3638; 2 february: 0.39208; 3 march: 0.26316; 4 april: 0.26316 | 0.32092
ACH % OVERBURDEN |  | 1 january: 84.91%; 2 february: 103.6%; 3 march: 39.13%; 4 april: 39.13% | 66.68%
ACH % ORE MINING |  | 1 january: 118%; 2 february: 106.4%; 3 march: 81.72%; 4 april: 81.72% | 96.97%
ACH % QUARRY |  | 1 january: 8.974%; 2 february: 7.469%; 3 march: 132.1%; 4 april: 132.1% | 70.15%
PRODUCTION excavator | 249.917 | 1 january: 208.413; 2 february: 398.8638; 3 march: 250.4596; 4 april: 497.2039 | 338.7351
COST OB REMOVAL | 980772683.1761 | 1 january: 913930747.1515; 2 february: 963632138.4179; 3 march: 1138721618.3285; 4 april: 1103086793.8723 | 4119371297.7703
COST QUARRY HAULING | 747900000 | 1 january: 334050000; 2 february: 264500000; 3 march: 446450000; 4 april: 446450000 | 1491450000
COST DEVELOP ACT. | 0 | 1 january: 0; 2 february: 0; 3 march: 0; 4 april: 0 | 0
COST ORE GETTING | 1089025000 | 1 january: 434195000; 2 february: 532270000; 3 march: 553530000; 4 april: 445795000 | 1965790000
COST ORE HAULING | 4733400000 | 1 january: 2318400000; 2 february: 2898000000; 3 march: 2608200000; 4 april: 2994600000 | 10819200000
COST UNIT SUPPORT | 80210000 | 1 january: 28210000; 2 february: 28210000; 3 march: 40210000; 4 april: 36210000 | 132840000
TOTAL COST | 7631307683.1761 | 1 january: 4028785747.1515; 2 february: 4686612138.4179; 3 march: 4787111618.3285; 4 april: 5026141793.8723 | 18528651297.7703
INCOME | 19557982187.52 | 1 january: 7687655342.08; 2 february: 9068179619.84; 3 march: 8439455907.84; 4 april: 6729864314.88 | 31925155184.64
PROFIT | 11926674504.3439 | 1 january: 3658869594.9285; 2 february: 4381567481.4221; 3 march: 3652344289.5115; 4 april: 1703722521.0077 | 13396503886.8697
PERCENT COST | 39.02% | 1 january: 52.41%; 2 february: 51.68%; 3 march: 56.72%; 4 april: 74.68% | 58.04%
PERCENT PROFIT | 60.98% | 1 january: 47.59%; 2 february: 48.32%; 3 march: 43.28%; 4 april: 25.32% | 41.96%
FUEL RATIO (L/Ton) | 1.8718 | 1 january: 2.0366; 2 february: 2.0066; 3 march: 2.045; 4 april: 1.6507 | 1.9338
ACH % FUEL RATIO |  | 1 january: 104.1%; 2 february: 96.68%; 3 march: 106.5%; 4 april: 106.8% | 103.5%
DAYS WORK | 61 | 1 january: 31; 2 february: 28; 3 march: 31; 4 april: 30 | 120
WORKING HOUR | 549 | 1 january: 279; 2 february: 252; 3 march: 279; 4 april: 270 | 1080
MECANICAL AVAILABILITY | 85% | 1 january: 85%; 2 february: 85%; 3 march: 85%; 4 april: 0.85 | 85%
Total Fuel Consumption | 234819.598 | 1 january: 131810; 2 february: 153187.8031; 3 march: 145293; 4 april: 117279.338 | 547570.1412
ACH % FUEL CONSUMPTION |  | 1 january: 88.23%; 2 february: 90.92%; 3 march: 130.3%; 4 april: 135.9% | 111.3%
COST / TON ORE | 121718.5763 | 1 january: 62249.8362; 2 february: 61389.8886; 3 march: 67377.8349; 4 april: 88712.8178 | 279730.3775
( USD / Ton ) | 8.1976 | 1 january: 4.1925; 2 february: 4.1346; 3 march: 4.5378; 4 april: 5.9747 | 18.8396

## REPORT unit OB
COST UNIT OVERBURDEN
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 400 - 01 | 87 | 950000 | 82650000 | 2534.9725 | 0 | 29.1376 | 82650000 | kbm | PC 400 LC SE-8 | KOMATSU PC 400 - 01 | K
2 | KOMATSU PC 300 - 12 | 19 | 400000 | 7600000 | 539.3077 | 0 | 28.3846 | 7600000 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 12 | K
3 | KOMATSU PC 300 - 17 | 24 | 400000 | 9600000 | 639.7922 | 0 | 26.658 | 9600000 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 17 | K
4 | KOMATSU PC 200 - 11 | 13 | 275000 | 3575000 | 206.8857 | 0 | 15.9143 | 3575000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 11 | K
5 | KOMATSU PC 200 - 15 | 10 | 275000 | 2750000 | 105.1724 | 0 | 10.5172 | 2750000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 15 | K
6 | KOMATSU HM 400 - 06 | 103 | 1424304.3668 | 146703349.7792 | 1714.6015 | 0 | 16.6466 | 146703349.7792 | kbm | HM 400-3R | KOMATSU HM 400 - 06 | K
7 | KOMATSU HM 400 - 07 | 167 | 1424304.3668 | 237858829.2537 | 2706.0995 | 0 | 16.2042 | 237858829.2537 | kbm | HM 400-3R | KOMATSU HM 400 - 07 | K
8 | KOMATSU HM 400 - 08 | 111 | 1424304.3668 | 158097784.7135 | 1778.3451 | 0 | 16.0211 | 158097784.7135 | kbm | HM 400-3R | KOMATSU HM 400 - 08 | K
9 | KOMATSU HM 400 - 09 | 105 | 1424304.3668 | 149551958.5128 | 1814.878 | 0 | 17.2846 | 149551958.5128 | kbm | HM 400-3R | KOMATSU HM 400 - 09 | K
10 | KOMATSU HM 400 - 10 | 108 | 1424304.3668 | 153824871.6131 | 1645.7143 | 0 | 15.2381 | 153824871.6131 | kbm | HM 400-3R | KOMATSU HM 400 - 10 | K
11 | KOMATSU DOZER D65 - 11 | 98 | 425000 | 41650000 | 2757 | 0 | 28.1327 | 41650000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 11 | K
12 | KOMATSU DOZER D65 - 12 | 155 | 425000 | 65875000 | 3930 | 0 | 25.3548 | 65875000 | kbm | D 65 P-12 | KOMATSU DOZER D65 - 12 | K
13 | KOMATSU DOZER D85SS - 11 | 102 | 425000 | 43350000 | 2176.3953 | 0 | 21.3372 | 43350000 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 11 | K
TOTAL |  | 1102 | 822809.3718 | 1103086793.8723 | 22549.1642 | 0 | 20.462 | 1103086793.8723
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit QUARRY
COST UNIT QUARRY
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 400 - 01 | 12 | 1000000 | 12000000 | 407.9266 | 0 | 33.9939 | 12000000 | kbm | PC 500 LCE-10R | KOMATSU PC 400 - 01 | K
2 | KOMATSU PC 300 - 12 | 74 | 1000000 | 74000000 | 397.3846 | 0 | 5.3701 | 74000000 | kbm | PC 500 LCE-10R | KOMATSU PC 300 - 12 | K
3 | KOMATSU PC 300 - 17 | 31 | 1000000 | 31000000 | 2132.6407 | 0 | 68.7949 | 31000000 | kbm | PC 500 LCE-10R | KOMATSU PC 300 - 17 | K
4 | KOMATSU PC 200 - 10 | 57 | 1000000 | 57000000 | 500 | 0 | 8.7719 | 57000000 | kbm | PC 500 LCE-10R | KOMATSU PC 200 - 10 | K
5 | KOMATSU HM 400 - 06 | 44 | 1000000 | 44000000 | 499.3985 | 0 | 11.35 | 44000000 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 06 | K
6 | KOMATSU HM 400 - 07 | 28 | 1000000 | 28000000 | 388.9005 | 0 | 13.8893 | 28000000 | kbm | PC 500 LCE-10R | KOMATSU HM 400 - 07 | K
7 | KOMATSU HM 400 - 08 | 85 | 950000 | 80750000 | 752.993 | 0 | 8.8587 | 80750000 | kbm | PC 400 LC SE-8 | KOMATSU HM 400 - 08 | K
8 | KOMATSU HM 400 - 09 | 97 | 950000 | 92150000 | 311.122 | 0 | 3.2074 | 92150000 | kbm | PC 400 LC SE-8 | KOMATSU HM 400 - 09 | K
9 | KOMATSU HM 400 - 10 | 29 | 950000 | 27550000 | 594.2857 | 0 | 20.4926 | 27550000 | kbm | PC 400 LC SE-8 | KOMATSU HM 400 - 10 | K
TOTAL |  | 457 | 983333.3333 | 446450000 | 5984.6516 | 0 | 13.0955 | 446450000
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit DEVELOP
COST UNIT DEVELOPT
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | GRADER GD535 - 03 |  | 350000 | 0 |  | 0 | 0 | 0 | kbm | GD 511 A-1 | GRADER GD535 - 03 | K
2 | SAKAI - 03 |  | 220000 | 0 |  | 0 | 0 | 0 | kbm | SV 525 D | SAKAI - 03 | K
3 | SAKAI - 07 |  | 220000 | 0 |  | 0 | 0 | 0 | kbm | SV 525 D | SAKAI - 07 | K
TOTAL |  | 0 | 263333.3333 | 0 | 0 | 0 | 0 | 0
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit ORE GETTING
COST UNIT ORE GETTING
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 400 - 01 | 8 | 950000 | 7600000 | 233.1009 | 0 | 29.1376 | 7600000 | kbm | PC 400 LC SE-8 | KOMATSU PC 400 - 01 | K
2 | KOMATSU PC 300 - 12 | 149 | 400000 | 59600000 | 4229.3077 | 0 | 28.3846 | 59600000 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 12 | K
3 | KOMATSU PC 300 - 17 | 127 | 400000 | 50800000 | 3385.5671 | 0 | 26.658 | 50800000 | kbm | PC 300 SE-8 | KOMATSU PC 300 - 17 | K
4 | KOMATSU PC 200 - 11 | 92 | 275000 | 25300000 | 1464.1143 | 0 | 15.9143 | 25300000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 11 | K
5 | KOMATSU PC 200 - 15 | 193 | 275000 | 53075000 | 2029.8276 | 0 | 10.5172 | 53075000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 15 | K
6 | KOMATSU PC 200 - 23 | 228 | 275000 | 62700000 | 3382 | 0 | 14.8333 | 62700000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 23 | K
7 | KOMATSU PC 200 - 24 | 240 | 275000 | 66000000 | 2392 | 0 | 9.9667 | 66000000 | kbm | PC 200-8 MO | KOMATSU PC 200 - 24 | K
8 | KOBELCO SK 200 - 19 | 206 | 275000 | 56650000 | 2753 | 0 | 13.3641 | 56650000 | kbm | SK 200-8 SX | KOBELCO SK 200 - 19 | K
9 | KOMATSU DOZER D85SS - 11 | 70 | 425000 | 29750000 | 1493.6047 | 0 | 21.3372 | 29750000 | kbm | D 85 ESS-2 | KOMATSU DOZER D85SS - 11 | K
10 | SAKAI - 01 | 156 | 220000 | 34320000 | 977 | 0 | 6.2628 | 34320000 | kbm | SV 525 D | SAKAI - 01 | K
TOTAL |  | 1469 | 377000 | 445795000 | 22339.5222 | 0 | 15.2073 | 445795000
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit DT HAUL
COST UNIT HAULING
NO | UNIT | TONNAGE |  | RENT |  | FUEL CONSUMPTION |  | RATIO |  |  | GRAND TOTAL COST | DESC. | TYPE
|  | Weight Bridge |  | Rate | Total | Fuel | Total
|  | Tonnage | Retase | ($/hour) |  | (liter) |  | (liter/ton) | (ton/ret) | (liter/ret)
1 | DT Hino 260 | 2125.95 | 54 | 460000 | 96600000 | 2383 | 0 | 1.1209 | 39.3694 | 44.1296 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 260
2 | DT Hino 261 | 2786.26 | 70 | 460000 | 96600000 | 2944 | 0 | 1.0566 | 39.8037 | 42.0571 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 261
3 | DT Hino 262 | 1811.57 | 46 | 460000 | 96600000 | 2014 | 0 | 1.1117 | 39.382 | 43.7826 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 262
4 | DT Hino 264 | 1786.72 | 45 | 460000 | 96600000 | 2082 | 0 | 1.1653 | 39.7049 | 46.2667 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 264
5 | DT Hino 265 | 2545.22 | 65 | 460000 | 96600000 | 2600 | 0 | 1.0215 | 39.1572 | 40 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 265
6 | DT Hino 266 | 471.26 | 12 | 460000 | 96600000 | 691 | 0 | 1.4663 | 39.2717 | 57.5833 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 266
7 | DT Hino 268 | 2859.44 | 73 | 460000 | 96600000 | 3245 | 0 | 1.1348 | 39.1704 | 44.4521 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 268
8 | DT Hino 271 | 2716.71 | 70 | 460000 | 96600000 | 3056 | 0 | 1.1249 | 38.8101 | 43.6571 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 271
9 | DT Hino 273 | 1791.76 | 45 | 460000 | 96600000 | 2119 | 0 | 1.1826 | 39.8169 | 47.0889 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 273
10 | DT Hino 275 | 2897.2 | 74 | 460000 | 96600000 | 3210 | 0 | 1.108 | 39.1514 | 43.3784 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 275
11 | DT Hino 278 | 353.89 | 9 | 460000 | 96600000 | 664 | 0 | 1.8763 | 39.3211 | 73.7778 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 278
12 | DT Hino 280 | 2977.86 | 76 | 460000 | 96600000 | 3443 | 0 | 1.1562 | 39.1824 | 45.3026 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 280
13 | DT Hino 282 | 550.21 | 14 | 460000 | 96600000 | 811 | 0 | 1.474 | 39.3007 | 57.9286 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 282
14 | DT Hino 283 | 1361.94 | 35 | 460000 | 96600000 | 1773 | 0 | 1.3018 | 38.9126 | 50.6571 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 283
15 | DT Hino 285 | 2116.68 | 55 | 460000 | 96600000 | 2366 | 0 | 1.1178 | 38.4851 | 43.0182 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 285
16 | DT Hino 286 | 2551.85 | 65 | 460000 | 96600000 | 2846 | 0 | 1.1153 | 39.2592 | 43.7846 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 286
17 | DT Hino 287 | 2962.74 | 77 | 460000 | 96600000 | 3300 | 0 | 1.1138 | 38.4771 | 42.8571 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 287
18 | DT Hino 288 | 2813.63 | 72 | 460000 | 96600000 | 3082 | 0 | 1.0954 | 39.0782 | 42.8056 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 288
19 | DT Hino 289 | 2208.6 | 56 | 460000 | 96600000 | 2158 | 0 | 0.97709 | 39.4393 | 38.5357 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 289
20 | DT Hino 290 | 2816.31 | 72 | 460000 | 96600000 | 2869 | 0 | 1.0187 | 39.1154 | 39.8472 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 290
21 | DT Hino 292 | 533.29 | 13 | 460000 | 96600000 | 759 | 0 | 1.4232 | 41.0223 | 58.3846 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 292
22 | DT Hino 293 | 2682.6 | 68 | 460000 | 96600000 | 2909 | 0 | 1.0844 | 39.45 | 42.7794 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 293
23 | DT Hino 294 | 76.71 | 2 | 460000 | 96600000 | 106 | 0 | 1.3818 | 38.355 | 53 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 294
24 | DT Hino 295 | 654.72 | 17 | 460000 | 96600000 | 702 | 0 | 1.0722 | 38.5129 | 41.2941 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 295
25 | DT Hino 296 | 996.71 | 25 | 460000 | 96600000 | 1017 | 0 | 1.0204 | 39.8684 | 40.68 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 296
26 | DT Hino 297 | 2484.66 | 63 | 460000 | 96600000 | 2698 | 0 | 1.0859 | 39.439 | 42.8254 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 297
27 | DT Hino 299 | 2263.42 | 58 | 460000 | 96600000 | 2547 | 0 | 1.1253 | 39.0245 | 43.9138 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 299
28 | DT Hino 301 | 1898.8 | 48 | 460000 | 96600000 | 2392 | 0 | 1.2597 | 39.5583 | 49.8333 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 301
29 | DT Hino 302 | 487.1 | 13 | 460000 | 96600000 | 778 | 0 | 1.5972 | 37.4692 | 59.8462 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 302
30 | DT Hino 304 | 780.71 | 20 | 460000 | 96600000 | 1111 | 0 | 1.4231 | 39.0355 | 55.55 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 304
31 | DT Hino 308 | 1291.8 | 33 | 460000 | 96600000 | 1433 | 0 | 1.1093 | 39.1455 | 43.4242 | 96600000 | ore hauling kbm | 700 Provia | DT Hino 308
TOTAL |  | 56656.32 | 1445 |  | 2994600000 | 64108 | 0 | 1.1315 | 39.2085 | 44.3654 | 2994600000
HINO 700
KURS USD | 14848
FUEL PRICE | 0
Min Charge | 210 | Hour

## REPORT unit LV & support
COST UNIT SUPPORT
NO | UNIT | RENT PER MONTH | FUEL CONSUMPTION |  | RATIO | GRAND TOTAL COST | DESC. | TYPE
|  |  | Fuel | Total
|  | (Rp/month) | (liter) |  | (liter/km)
1 | LV HILUX MERAH - 06 | 8000000 | 145 | 0 |  | 8000000 |  | LV | LV HILUX MERAH - 06
2 | LV TRITON PUTIH - 28 | 8000000 | 499 | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 28
3 | LV TRITON PUTIH - 31 | 8000000 | 234 | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 31
4 | FUEL TRUCK - 02 | 210000 | 1017 | 0 |  | 210000 |  | FM 260 Ti | FUEL TRUCK - 02
5 | WELDER CAR (LT-07) | 12000000 | 403 | 0 |  | 12000000 |  | LT | WELDER CAR (LT-07)
TOTAL |  | 36210000 | 2298 | 0 | 0 | 36210000
KURS USD | 14848
FUEL PRICE | 0

## HOUR METER (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
D | NO | ID UNIT | DAYLY REPORT HM | [30 empty] | TOTAL HM | TOTAL FUEL 1- 31
N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WEEK 1 | : | 0 | DAYLY REPORT HM 22: Di setujui oleh :; DAYLY REPORT HM 29: Di buat oleh :
WEEK 2 | : | 0
WEEK 3 | : | 0
WEEK 4 | : | 0 | bar: DAYLY REPORT HM 5
WEEK 5 | : | 0 | DAYLY REPORT HM 22: Internal Kontrol; DAYLY REPORT HM 29: MPE Team
0
BENAR

## FUEL UNIT (hidden)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| D | NO | ID UNIT | DAYLY REPORT FUEL | [30 empty] | TOTAL FUEL | TOTAL HM 1- 31
| N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
SM-BW 211-02 | TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
SM-BW 211-03 | TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
| TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
SM-D85ESS-08 | TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
| TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
| TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
| TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
| TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
| TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
| TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
| ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
| ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
| ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
| ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
| ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
| ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
| ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
| DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
| DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
| DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
| DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
| DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
| TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
| TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DAYLY REPORT FUEL 30: TOTAL FUEL | 0
| WEEK 1 | : | 0 | DAYLY REPORT FUEL 22: Di setujui oleh :; DAYLY REPORT FUEL 29: Di buat oleh :
| WEEK 2 | : | 0
| WEEK 3 | : | 0
| WEEK 4 | : | 0
| WEEK 5 | : | 0 | DAYLY REPORT FUEL 22: Internal Kontrol; DAYLY REPORT FUEL 29: MPE Team
0
BENAR

## list rate unit
RATE
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | unit | type
NO | UNIT | Ltr/Hr | Rent/Hr | Column1 | Column2 | Description | Column4 | Column5 | Column6 | Column7 |  | KOMATSU PC 500 - 01 | PC 500 LCE-10R
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  | KOMATSU PC 500 - 02 | PC 500 LCE-10R
|  |  | Unit Only (Internal) | Incl. Operator | Incl. Operator & Fuel | [6 empty] | KOMATSU PC 500 - 03 | PC 500 LCE-10R
1 | PC 195 LC-8 | 20 | 16.5432 | 19.5084 | 35.3704 | Excavator | 239875.7064 | 282871.4905 | 512871.4905 | 275000 | 200 | KOMATSU PC 500 - 04 | PC 500 LCE-10R
2 | PC 200-8 MO | 22 | 23.2254 | 26.1906 | 43.6389 | Excavator | 336767.7028 | 379763.4868 | 632763.4868 | 275000 | 200 | KOMATSU PC 400 - 01 | PC 400 LC SE-8
3 | PC 300 SE-8 | 30 | 41.2152 | 44.1804 | 69.5598 | Excavator | 597620.6927 | 640616.4768 | 1008616.4768 | 400000 | 300 | KOMATSU PC 400 - 03 | PC 400 LC SE-8
4 | PC 400 LC SE-8 | 38 | 58.29 | 61.6 | 87.81 | Excavator | 845205 | 893200 | 1273245 | 950000 | 400 | KOMATSU PC 400 - 04 | PC 400 LC SE-8
5 | PC 500 LCE-10R | 45 | 63.54 | 66.85 | 98.05 | Excavator | 921330 | 969325 | 1421725 | 1000000 |  | KOMATSU PC 400 - 05 | PC 400 LC SE-8
6 | SK 200-8 SX | 20 | 17.6502 | 20.6154 | 36.4775 | Excavator | 255927.8486 | 298923.6327 | 528923.6327 | 275000 | 200 | KOMATSU PC 400 - 06 | PC 400 LC SE-8
7 | SK 330-8 | 28 | 34.235 | 37.2002 | 59.4071 | Excavator | 496407.8395 | 539403.6235 | 861403.6235 | 400000 |  | KOMATSU PC 300 - 10 | PC 300 SE-8
8 | HM 400-3R | 30 | 98.2279 | 101.5379 | 127.7104 | Artic | 1424304.3668 | 1472300.1508 | 1851800.1508 | 1424304.3668 |  | KOMATSU PC 300 - 11 | PC 300 SE-8
9 | D 85 ESS-2 | 30 | 42.331 | 45.2962 | 69.0893 | Bulldozer | 613799.3709 | 656795.155 | 1001795.155 | 425000 |  | KOMATSU PC 300 - 12 | PC 300 SE-8
10 | D 65 P-12 | 33 | 42.7792 | 45.7445 | 71.9169 | Bulldozer | 620298.906 | 663294.6901 | 1042794.6901 | 425000 |  | KOMATSU PC 300 - 14 | PC 300 SE-8
11 | GD 511 A-1 | 15 | 32.851 | 35.8163 | 47.7128 | Grader | 476340.0889 | 519335.8729 | 691835.8729 | 350000 |  | KOMATSU PC 300 - 15 | PC 300 SE-8
12 | SV 525 D | 11 | 13.1981 | 16.1633 | 24.0943 | Compactor | 191372.0947 | 234367.8788 | 349367.8788 | 220000 |  | KOMATSU PC 300 - 16 | PC 300 SE-8
13 | BW 211 D-40 | 11 | 9.9397 | 12.9049 | 20.8359 | Compactor | 144125.031 | 187120.8151 | 302120.8151 | 220000 |  | KOMATSU PC 300 - 17 | PC 300 SE-8
14 | XG 6121 | 11 | 8.6243 | 11.5895 | 19.5206 | Compactor | 125052.5178 | 168048.3018 | 283048.3018 |  |  | KOBELCO SK 330 - 10 | SK 330-8
15 | XG 955-III | 20 | 12.8699 | 15.8352 | 31.6972 | Whell Loader | 186614.0656 | 229609.8497 | 459609.8497 |  |  | KOBELCO SK 330 - 11 | SK 330-8
16 | WA 380-3 | 20 | 34.0145 | 36.9797 | 52.8418 | Whell Loader | 493209.9817 | 536205.7657 | 766205.7657 |  |  | KOMATSU PC 200 - 11 | PC 200-8 MO
17 | FM 260 Ti | 15 | 17.3403 | 18.9483 | 30.0517 | Dump Truck | 251435.0252 | 274750.1408 | 435750.1408 | 210000 |  | KOMATSU PC 200 - 12 | PC 200-8 MO
18 | 700 Provia | 20 | 31.1718 | 32.9521 | 48.8142 | Dump Truck | 451990.7019 | 477805.8175 | 707805.8175 | 460000 |  | KOMATSU PC 200 - 14 | PC 200-8 MO
19 | 700 Provia/12 | 28 | 32.42 | 34.21 | 53.52 | Dump Truck | 470090 | 496045 | 776040 | 500000 |  | KOMATSU PC 200 - 15 | PC 200-8 MO
20 | LV | 10 |  |  |  |  | 8000000 |  |  | 8000000 |  | KOMATSU PC 200 - 16 | PC 200-8 MO
21 | GENSET | 4 |  |  |  |  | 3000000 |  |  | 3000000 |  | KOMATSU PC 200 - 22 | PC 200-8 MO
22 | LT | 10 |  |  |  |  | 12000000 |  |  | 12000000 |  | KOMATSU PC 200 - 23 | PC 200-8 MO
RATE MOBILISASI | [11 empty] | KOMATSU PC 200 - 24 | PC 200-8 MO
[9 empty] | source data ( owning & operating cost) |  |  | KOMATSU SK 200 - 19 | PC 200-8 MO
NO | UNIT | $ / KM | [9 empty] | KOMATSU PC 200 - 25 | PC 200-8 MO
1 | PC 400 | 24 | [9 empty] | KOMATSU PC 195 - 01 | PC 195 LC-8
2 | PC 300 | 16 | [9 empty] | KOBELCO SK 200 - 07 | SK 200-8 SX
3 | PC 200 | 8 | [9 empty] | KOBELCO SK 200 - 08 | SK 200-8 SX
4 | BULLDOZER | 16 | [9 empty] | KOBELCO SK 200 - 10 | SK 200-8 SX
5 | COMPACTOR | 8 | [9 empty] | KOBELCO SK 200 - 11 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 13 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 15 | SK 200-8 SX
| 14652.34 | [10 empty] | KOBELCO SK 200 - 16 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 18 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 19 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 20 | SK 200-8 SX
[12 empty] | KOMATSU HM 400 - 01 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 02 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 04 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 05 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 06 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 07 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 08 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 09 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 10 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 11 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 12 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 13 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 14 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 15 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 16 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 17 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 18 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 19 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 20 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 21 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 22 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 23 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 24 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 25 | HM 400-3R
[12 empty] | KOMATSU DOZER D65 - 05 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 10 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 11 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 12 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 13 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 15 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 16 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 18 | D 65 P-12
[12 empty] | KOMATSU DOZER D85SS - 11 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 14 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 17 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 18 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 20 | D 85 ESS-2
[12 empty] | GRADER GD535 - 03 | GD 511 A-1
[12 empty] | LOADER WA380 - 02 | WA 380-3
[12 empty] | SAKAI - 01 | SV 525 D
[12 empty] | SAKAI - 02 | SV 525 D
[12 empty] | SAKAI - 03 | SV 525 D
[12 empty] | SAKAI - 07 | SV 525 D
[12 empty] | LV HILUX HITAM - 05 | LV
[12 empty] | LV PAJERO PUTIH - 06 | LV
[12 empty] | LV TRITON HITAM - 08 | LV
[12 empty] | LV PAJERO PUTIH - 09 | LV
[12 empty] | LV HILUX SILVER - 10 | LV
[12 empty] | LV TRITON HITAM - 10 | LV
[12 empty] | LV TRITON PUTIH - 11 | LV
[12 empty] | LV HILUX HITAM - 11 | LV
[12 empty] | LV TRITON PUTIH - 12 | LV
[12 empty] | LV PAJERO HITAM - 15 | LV
[12 empty] | LV HILUX SILVER - 17 | LV
[12 empty] | LV HILUX HITAM - 18 | LV
[12 empty] | LV HILUX SILVER - 19 | LV
[12 empty] | LV PAJERO SILVER - 21 | LV
[12 empty] | LV HILUX PUTIH - 23 | LV
[12 empty] | LV TRITON PUTIH - 27 | LV
[12 empty] | LV LC-HIJAU - 29 | LV
[12 empty] | LV TRITON PUTIH (SAFETY) - 30 | LV
[12 empty] | LV TRITON PUTIH - 31 | LV
[12 empty] | LV TRITON PUTIH - 32 | LV
[12 empty] | MANHAUL - 02 | FM 260 Ti
[12 empty] | BUS APP - 03 | LT
[12 empty] | FUEL TRUCK - 02 | FM 260 Ti
[12 empty] | FUEL TRUCK - 03 | FM 260 Ti
[12 empty] | FUEL TRUCK - 05 | FM 260 Ti
[12 empty] | FUEL TRUCK - 06 | FM 260 Ti
[12 empty] | TRUCK WELDER - LT-04 | LT
[12 empty] | TRUCK TYRE - LT-08 | LT
[12 empty] | TRUCK MAINTENANCE - LT-09 | LT
[12 empty] | TRUCK TYRE - LT-10 | LT
MEKANIK CAMP
[12 empty] | LV TRITON PUTIH - 28 | LV
[12 empty] | TRUCK TYRE (LT-06) | LT
[12 empty] | WELDER CAR (LT-07) | LT
[12 empty] | LV HILUX MERAH - 06 | LV