## SUMMARY
MINING COST (JUNI)
| SUMMARY BDM BLOK 8 NAKULA | Juni 2023 |  |  | CV. SENTOSA ABADI
|  | PLAN | ACTUAL | ACH % | DAYS WORK |  | 30 | days
| OVERBURDEN REMOVAL | 35246.64 | 21341.3 | 60.55% | WORKING HOUR |  | 270 | hours
| ORE MINING | 76856.13 | 65676.39 | 85.45% | PHYSICHAL AVAILIBILITY |  | 90% | PA
| QUARRY MINING | 4229.5968 |  | 0%
| STRIPING RATIO | 0.45861 | 0.32495 | 141.1% | Fuel Price / liter |  | 0
| FUEL RATIO OVERALL (L/Ton) | 2.0142 | 2.0772 | 96.97% | (fuel not include in contract)
| ADT HM 400 (bcm/hour) |  |  |  | Total Fuel Consumption | PLAN | 154807.0963 | Liter
| PRODUCTION hauler | 63.2 | 39.5209 | 62.53% |  | ACTUAL | 136424 | Liter
[6 empty] | ACH % | 113.5%
| COST RENT + FUEL |  |  |  | COST ITEM / TON ORE
| COST OB REMOVAL | 1108555488.1971 |  |  | COST OB / TON | 23.78% | 16879.0564 | 1.1368
| COST QUARRY HAULING | 156750000 |  |  | COST QUARRY / TON | 3.363% | 2386.7024 | 0.16074
| COST DEVELOP ACT. | 0 |  |  | COST DEV / TON | 0% | 0 | 0
| COST ORE GETTING | 546440000 |  |  | COST ORE GETTING / TON | 11.72% | 8320.1893 | 0.56036
| COST ORE HAULING | 2801400000 |  |  | COST ORE HAULING / TON | 60.1% | 42654.5978 | 2.8728
| COST UNIT SUPPORT | 48210000 |  |  | COST SUPPORT / TON | 1.034% | 734.0537 | 0.049438
[6 empty] | 100% | 70974.5997 | 4.7801
| TOTAL COST | 4661355488.1971 |  |  | COST / TON ORE |  | 70974.5997
| INCOME | 7801304309.76 |  |  | ( USD / Ton ) |  | 4.7801
[5 empty] | KURS/$ |  | 14848
| RESULT | 3139948821.5629 |  |  | PRICE / TON ORE |  | 8
OKE…..

## SUMMARY MTD
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| last year (2022) | january | february | march | april | may | june | july | august | september | october | november | december | TOTAL 2022
OVERBURDEN REMOVAL | 25551.1 | 1 january: 23545.18; 2 february: 29931.98; 3 march: 18697.04; 4 april: 18697.04; 5 may: 15970.69; 6 june: 21341.3 | 128183.23
ORE MINING | 125448.88 | 1 january: 64719.62; 2 february: 76341.76; 3 march: 71048.76; 4 april: 71048.76; 5 may: 75392.73; 6 june: 65676.39 | 424228.02
QUARRY MINING | 12871.52 | 1 january: 746.51; 2 february: 647.58; 3 march: 7573.39; 4 april: 7573.39; 5 may: 16301.3; 6 june: 0 | 32842.17
STRIPING RATIO | 0.20368 | 1 january: 0.3638; 2 february: 0.39208; 3 march: 0.26316; 4 april: 0.26316; 5 may: 0.21183; 6 june: 0.32495 | 0.30216
ACH % OVERBURDEN |  | 1 january: 84.91%; 2 february: 103.6%; 3 march: 39.13%; 4 april: 39.13%; 5 may: 33.42%; 6 june: 60.55% | 60.12%
ACH % ORE MINING |  | 1 january: 118%; 2 february: 106.4%; 3 march: 81.72%; 4 april: 81.72%; 5 may: 86.72%; 6 june: 85.45% | 93.34%
ACH % QUARRY |  | 1 january: 8.974%; 2 february: 7.469%; 3 march: 132.1%; 4 april: 132.1%; 5 may: 113.7%; 6 june: 0% | 65.72%
PRODUCTION hauler | 249.917 | 1 january: 208.413; 2 february: 398.8638; 3 march: 250.4596; 4 april: 497.2039; 5 may: 43.26; 6 june: 39.5209 | 239.6202
COST OB REMOVAL | 980772683.1761 | 1 january: 913930747.1515; 2 february: 963632138.4179; 3 march: 1138721618.3285; 4 april: 1103086793.8723; 5 may: 1063487879.0274; 6 june: 1108555488.1971 | 6291414664.9948
COST QUARRY HAULING | 747900000 | 1 january: 334050000; 2 february: 264500000; 3 march: 446450000; 4 april: 446450000; 5 may: 383750000; 6 june: 156750000 | 2031950000
COST DEVELOP ACT. | 0 | 1 january: 0; 2 february: 0; 3 march: 0; 4 april: 0; 5 may: 0; 6 june: 0 | 0
COST ORE GETTING | 1089025000 | 1 january: 434195000; 2 february: 532270000; 3 march: 553530000; 4 april: 445795000; 5 may: 568760000; 6 june: 546440000 | 3080990000
COST ORE HAULING | 4733400000 | 1 january: 2318400000; 2 february: 2898000000; 3 march: 2608200000; 4 april: 2994600000; 5 may: 2898000000; 6 june: 2801400000 | 16518600000
COST UNIT SUPPORT | 80210000 | 1 january: 28210000; 2 february: 28210000; 3 march: 40210000; 4 april: 36210000; 5 may: 36210000; 6 june: 48210000 | 217260000
TOTAL COST | 7631307683.1761 | 1 january: 4028785747.1515; 2 february: 4686612138.4179; 3 march: 4787111618.3285; 4 april: 5026141793.8723; 5 may: 4950207879.0274; 6 june: 4661355488.1971 | 28140214664.9948
INCOME | 19557982187.52 | 1 january: 7687655342.08; 2 february: 9068179619.84; 3 march: 8439455907.84; 4 april: 6729864314.88; 5 may: 8955450040.32; 6 june: 7801304309.76 | 48681909534.72
PROFIT | 11926674504.3439 | 1 january: 3658869594.9285; 2 february: 4381567481.4221; 3 march: 3652344289.5115; 4 april: 1703722521.0077; 5 may: 4005242161.2926; 6 june: 3139948821.5629 | 20541694869.7252
PERCENT COST | 39.02% | 1 january: 52.41%; 2 february: 51.68%; 3 march: 56.72%; 4 april: 74.68%; 5 may: 55.28%; 6 june: 59.75% | 57.8%
PERCENT PROFIT | 60.98% | 1 january: 47.59%; 2 february: 48.32%; 3 march: 43.28%; 4 april: 25.32%; 5 may: 44.72%; 6 june: 40.25% | 42.2%
FUEL RATIO (L/Ton) | 1.8718 | 1 january: 2.0366; 2 february: 2.0066; 3 march: 2.045; 4 april: 1.6507; 5 may: 1.9537; 6 june: 2.0772 | 1.9595
ACH % FUEL RATIO |  | 1 january: 104.1%; 2 february: 96.68%; 3 march: 106.5%; 4 april: 106.8%; 5 may: 113.1%; 6 june: 96.97% | 104%
DAYS WORK | 61 | 1 january: 31; 2 february: 28; 3 march: 31; 4 april: 30; 5 may: 31; 6 june: 30 | 181
WORKING HOUR | 549 | 1 january: 279; 2 february: 252; 3 march: 279; 4 april: 270; 5 may: 270; 6 june: 270 | 1620
MECANICAL AVAILABILITY | 85% | 1 january: 85%; 2 february: 85%; 3 march: 85%; 4 april: 85%; 5 may: 90%; 6 june: 90% | 86.67%
Total Fuel Consumption | 234819.598 | 1 january: 131810; 2 february: 153187.8031; 3 march: 145293; 4 april: 117279.338; 5 may: 147292; 6 june: 136424 | 831286.1412
ACH % FUEL CONSUMPTION |  | 1 january: 88.23%; 2 february: 90.92%; 3 march: 130.3%; 4 april: 135.9%; 5 may: 128.3%; 6 june: 1.1347 | 114.5%
COST / TON ORE | 121718.5763 | 1 january: 62249.8362; 2 february: 61389.8886; 3 march: 67377.8349; 4 april: 88712.8178; 5 may: 65658.9552; 6 june: 70974.5997 | 416363.9323
( USD / Ton ) | 8.1976 | 1 january: 4.1925; 2 february: 4.1346; 3 march: 4.5378; 4 april: 5.9747; 5 may: 4.4221; 6 june: 4.7801 | 28.0418

## REPORT unit OB
COST UNIT OVERBURDEN
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 400 - 01 | 70 | 950000 | 66500000 | 2363.4211 | 0 | 33.7632 | 66500000 | bdm | PC 400 LC SE-8 | KOMATSU PC 400 - 01 | K
2 | KOMATSU PC 400 - 03 | 105 | 950000 | 99750000 | 3547.0909 | 0 | 33.7818 | 99750000 | bdm | PC 400 LC SE-8 | KOMATSU PC 400 - 03 | K
3 | KOMATSU HM 400 - 06 | 100 | 1424304.3668 | 142430436.6788 | 1542.5806 | 0 | 15.4258 | 142430436.6788 | bdm | HM 400-3R | KOMATSU HM 400 - 06 | K
4 | KOMATSU HM 400 - 07 | 68 | 1424304.3668 | 96852696.9416 | 965.7722 | 0 | 14.2025 | 96852696.9416 | bdm | HM 400-3R | KOMATSU HM 400 - 07 | K
5 | KOMATSU HM 400 - 08 | 116 | 1424304.3668 | 165219306.5475 | 2014.3492 | 0 | 17.3651 | 165219306.5475 | bdm | HM 400-3R | KOMATSU HM 400 - 08 | K
6 | KOMATSU HM 400 - 09 | 123 | 1424304.3668 | 175189437.115 | 1935.6788 | 0 | 15.7372 | 175189437.115 | bdm | HM 400-3R | KOMATSU HM 400 - 09 | K
7 | KOMATSU HM 400 - 10 | 117 | 1424304.3668 | 166643610.9142 | 1743.1172 | 0 | 14.8984 | 166643610.9142 | bdm | HM 400-3R | KOMATSU HM 400 - 10 | K
8 | KOMATSU DOZER D65 - 11 | 136 | 425000 | 57800000 | 2614.5799 | 0 | 19.2249 | 57800000 | bdm | D 65 P-12 | KOMATSU DOZER D65 - 11 | K
9 | KOMATSU DOZER D65 - 12 | 97 | 425000 | 41225000 | 1688.0896 | 0 | 17.403 | 41225000 | bdm | D 65 P-12 | KOMATSU DOZER D65 - 12 | K
10 | KOMATSU DOZER D85SS - 11 | 181 | 425000 | 76925000 | 3199.2713 | 0 | 17.6755 | 76925000 | bdm | D 85 ESS-2 | KOMATSU DOZER D85SS - 11 | K
11 | SAKAI - 01 | 91 | 220000 | 20020000 | 463.8584 | 0 | 5.0973 | 20020000 | bdm | SV 525 D | SAKAI - 01 | K
TOTAL |  | 1204 | 956047.4394 | 1108555488.1971 | 22077.8091 | 0 | 18.3371 | 1108555488.1971
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit QUARRY
COST UNIT QUARRY
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 400 - 01 | 44 | 1000000 | 44000000 | 1485.5789 | 0 | 33.7632 | 44000000 | bdm | PC 500 LCE-10R | KOMATSU PC 400 - 01 | K
2 | KOMATSU PC 400 - 03 | 5 | 1000000 | 5000000 | 168.9091 | 0 | 33.7818 | 5000000 | bdm | PC 500 LCE-10R | KOMATSU PC 400 - 03 | K
3 | KOMATSU PC 300 - 17 | 8 | 1000000 | 8000000 | 197.7761 | 0 | 24.722 | 8000000 | bdm | PC 500 LCE-10R | KOMATSU PC 300 - 17 | K
4 | KOMATSU HM 400 - 06 | 55 | 1000000 | 55000000 | 848.4194 | 0 | 15.4258 | 55000000 | bdm | PC 500 LCE-10R | KOMATSU HM 400 - 06 | K
5 | KOMATSU HM 400 - 07 | 11 | 1000000 | 11000000 | 156.2278 | 0 | 14.2025 | 11000000 | bdm | PC 500 LCE-10R | KOMATSU HM 400 - 07 | K
6 | KOMATSU HM 400 - 08 | 10 | 1000000 | 10000000 | 173.6508 | 0 | 17.3651 | 10000000 | bdm | PC 500 LCE-10R | KOMATSU HM 400 - 08 | K
7 | KOMATSU HM 400 - 09 | 14 | 950000 | 13300000 | 220.3212 | 0 | 15.7372 | 13300000 | bdm | PC 400 LC SE-8 | KOMATSU HM 400 - 09 | K
8 | KOMATSU HM 400 - 10 | 11 | 950000 | 10450000 | 163.8828 | 0 | 14.8984 | 10450000 | bdm | PC 400 LC SE-8 | KOMATSU HM 400 - 10 | K
TOTAL |  | 158 | 987500 | 156750000 | 3414.7661 | 0 | 21.6124 | 156750000
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit DEVELOP
COST UNIT DEVELOPT
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | GRADER GD535 - 03 |  | 350000 | 0 |  | 0 | 0 | 0 | kbm | GD 511 A-1 | GRADER GD535 - 03 | K
2 | SAKAI - 03 |  | 220000 | 0 |  | 0 | 0 | 0 | kbm | SV 525 D | SAKAI - 03 | K
3 | SAKAI - 07 |  | 220000 | 0 |  | 0 | 0 | 0 | kbm | SV 525 D | SAKAI - 07 | K
TOTAL |  | 0 | 263333.3333 | 0 | 0 | 0 | 0 | 0
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit ORE GETTING
COST UNIT ORE GETTING
NO | UNIT | HOURS METER |  |  | FUEL CONSUMPTION |  | FUEL RATIO | GRAND TOTAL COST | DESC. | TYPE
|  | HM | Rate HM | Total | Fuel | Total
|  | (hour) | ($/hour) |  | (liter) |  | (liter/hour)
1 | KOMATSU PC 300 - 12 | 245 | 400000 | 98000000 | 6364 | 0 | 25.9755 | 98000000 | bdm | PC 300 SE-8 | KOMATSU PC 300 - 12 | K
2 | KOMATSU PC 300 - 17 | 251 | 400000 | 100400000 | 6205.2239 | 0 | 24.722 | 100400000 | bdm | PC 300 SE-8 | KOMATSU PC 300 - 17 | K
3 | KOMATSU PC 200 - 11 | 69 | 275000 | 18975000 | 1274 | 0 | 18.4638 | 18975000 | bdm | PC 200-8 MO | KOMATSU PC 200 - 11 | K
4 | KOMATSU PC 200 - 15 | 290 | 275000 | 79750000 | 3290 | 0 | 11.3448 | 79750000 | bdm | PC 200-8 MO | KOMATSU PC 200 - 15 | K
5 | KOMATSU PC 200 - 23 | 254 | 275000 | 69850000 | 3854 | 0 | 15.1732 | 69850000 | bdm | PC 200-8 MO | KOMATSU PC 200 - 23 | K
6 | KOMATSU PC 200 - 24 | 288 | 275000 | 79200000 | 2910 | 0 | 10.1042 | 79200000 | bdm | PC 200-8 MO | KOMATSU PC 200 - 24 | K
7 | KOBELCO SK 200 - 19 | 228 | 275000 | 62700000 | 2786 | 0 | 12.2193 | 62700000 | bdm | SK 200-8 SX | KOBELCO SK 200 - 19 | K
8 | KOMATSU DOZER D65 - 11 | 33 | 425000 | 14025000 | 634.4201 | 0 | 19.2249 | 14025000 | bdm | D 65 P-12 | KOMATSU DOZER D65 - 11 | K
9 | KOMATSU DOZER D65 - 12 | 37 | 425000 | 15725000 | 643.9104 | 0 | 17.403 | 15725000 | bdm | D 65 P-12 | KOMATSU DOZER D65 - 12 | K
10 | KOMATSU DOZER D85SS - 11 | 7 | 425000 | 2975000 | 123.7287 | 0 | 17.6755 | 2975000 | bdm | D 85 ESS-2 | KOMATSU DOZER D85SS - 11 | K
11 | SAKAI - 01 | 22 | 220000 | 4840000 | 112.1416 | 0 | 5.0973 | 4840000 | bdm | SV 525 D | SAKAI - 01 | K
TOTAL |  | 1724 | 333636.3636 | 546440000 | 28197.4248 | 0 | 16.3558 | 546440000
KURS USD | 14848
FUEL PRICE | 0

## REPORT unit DT HAUL
COST UNIT HAULING
NO | UNIT | TONNAGE |  | RENT |  | FUEL CONSUMPTION |  | RATIO |  |  | GRAND TOTAL COST | DESC. | TYPE
|  | Weight Bridge |  | Rate | Total | Fuel | Total
|  | Tonnage | Retase | ($/hour) |  | (liter) |  | (liter/ton) | (ton/ret) | (liter/ret)
1 | DT Hino 260 | 1718.2 | 47 | 460000 | 96600000 | 2051 | 0 | 1.1937 | 36.5574 | 43.6383 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 260
2 | DT Hino 261 | 1891.99 | 52 | 460000 | 96600000 | 2320 | 0 | 1.2262 | 36.3844 | 44.6154 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 261
3 | DT Hino 262 | 1809.39 | 49 | 460000 | 96600000 | 2273 | 0 | 1.2562 | 36.9263 | 46.3878 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 262
4 | DT Hino 265 | 2855.04 | 78 | 460000 | 96600000 | 3166 | 0 | 1.1089 | 36.6031 | 40.5897 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 265
5 | DT Hino 266 | 2868.34 | 78 | 460000 | 96600000 | 3558 | 0 | 1.2404 | 36.7736 | 45.6154 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 266
6 | DT Hino 268 | 3176.96 | 86 | 460000 | 96600000 | 3978 | 0 | 1.2521 | 36.9414 | 46.2558 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 268
7 | DT Hino 271 | 1646.23 | 45 | 460000 | 96600000 | 2029 | 0 | 1.2325 | 36.5829 | 45.0889 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 271
8 | DT Hino 273 | 1885.06 | 51 | 460000 | 96600000 | 2411 | 0 | 1.279 | 36.962 | 47.2745 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 273
9 | DT Hino 275 | 2221.18 | 60 | 460000 | 96600000 | 2590 | 0 | 1.166 | 37.0197 | 43.1667 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 275
10 | DT Hino 278 | 1542.12 | 42 | 460000 | 96600000 | 2151 | 0 | 1.3948 | 36.7171 | 51.2143 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 278
11 | DT Hino 280 | 1681.88 | 45 | 460000 | 96600000 | 2229 | 0 | 1.3253 | 37.3751 | 49.5333 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 280
12 | DT Hino 282 | 4130.6 | 111 | 460000 | 96600000 | 4941 | 0 | 1.1962 | 37.2126 | 44.5135 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 282
13 | DT Hino 283 | 1840.72 | 50 | 460000 | 96600000 | 2164 | 0 | 1.1756 | 36.8144 | 43.28 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 283
14 | DT Hino 285 | 2895.78 | 79 | 460000 | 96600000 | 3471 | 0 | 1.1986 | 36.6554 | 43.9367 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 285
15 | DT Hino 286 | 2232.72 | 61 | 460000 | 96600000 | 2599 | 0 | 1.1641 | 36.602 | 42.6066 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 286
16 | DT Hino 287 | 2370.06 | 66 | 460000 | 96600000 | 2956 | 0 | 1.2472 | 35.91 | 44.7879 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 287
17 | DT Hino 288 | 1998.66 | 54 | 460000 | 96600000 | 2579 | 0 | 1.2904 | 37.0122 | 47.7593 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 288
18 | DT Hino 289 | 2283.34 | 62 | 460000 | 96600000 | 2636 | 0 | 1.1544 | 36.8281 | 42.5161 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 289
19 | DT Hino 290 | 2540.22 | 69 | 460000 | 96600000 | 3051 | 0 | 1.2011 | 36.8148 | 44.2174 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 290
20 | DT Hino 292 | 2374.65 | 65 | 460000 | 96600000 | 3046 | 0 | 1.2827 | 36.5331 | 46.8615 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 292
21 | DT Hino 293 | 2705.4 | 73 | 460000 | 96600000 | 3258 | 0 | 1.2043 | 37.0603 | 44.6301 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 293
22 | DT Hino 295 | 1059.8 | 29 | 460000 | 96600000 | 1369 | 0 | 1.2918 | 36.5448 | 47.2069 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 295
23 | DT Hino 296 | 2156.4 | 59 | 460000 | 96600000 | 2802 | 0 | 1.2994 | 36.5492 | 47.4915 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 296
24 | DT Hino 297 | 3040.94 | 83 | 460000 | 96600000 | 3708 | 0 | 1.2194 | 36.6378 | 44.6747 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 297
25 | DT Hino 299 | 1837.01 | 50 | 460000 | 96600000 | 2342 | 0 | 1.2749 | 36.7402 | 46.84 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 299
26 | DT Hino 301 | 2541.61 | 68 | 460000 | 96600000 | 3123 | 0 | 1.2287 | 37.3766 | 45.9265 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 301
27 | DT Hino 302 | 1889.53 | 53 | 460000 | 96600000 | 2638 | 0 | 1.3961 | 35.6515 | 49.7736 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 302
28 | DT Hino 304 | 2910.34 | 79 | 460000 | 96600000 | 3404 | 0 | 1.1696 | 36.8397 | 43.0886 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 304
29 | DT Hino 308 | 1572.22 | 42 | 460000 | 96600000 | 2110 | 0 | 1.3421 | 37.4338 | 50.2381 | 96600000 | ore hauling bdm | 700 Provia | DT Hino 308
TOTAL |  | 65676.39 | 1786 |  | 2801400000 | 80953 | 0 | 1.2326 | 36.7729 | 45.3264 | 2801400000
HINO 700
KURS USD | 14848
FUEL PRICE | 0
Min Charge | 210 | Hour

## REPORT unit LV & support
COST UNIT SUPPORT
NO | UNIT | RENT PER MONTH | FUEL CONSUMPTION |  | RATIO | GRAND TOTAL COST | DESC. | TYPE
|  |  | Fuel | Total
|  | (Rp/month) | (liter) |  | (liter/km)
1 | LV HILUX MERAH - 06 | 8000000 | 49 | 0 |  | 8000000 |  | LV | LV HILUX MERAH - 06
2 | LV TRITON PUTIH - 28 | 8000000 | 487 | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 28
3 | LV TRITON PUTIH - 31 | 8000000 | 112 | 0 |  | 8000000 |  | LV | LV TRITON PUTIH - 31
4 | FUEL TRUCK - 02 | 210000 | 857 | 0 |  | 210000 |  | FM 260 Ti | FUEL TRUCK - 02
5 | TRUCK TYRE (LT-06) | 12000000 | 128 | 0 |  | 12000000 |  | LT | TRUCK TYRE (LT-06)
6 | WELDER CAR (LT-07) | 12000000 | 148 | 0 |  | 12000000 |  | LT | WELDER CAR (LT-07)
TOTAL |  | 48210000 | 1781 | 0 | 0 | 48210000
KURS USD | 14848
FUEL PRICE | 0

## HOUR METER (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
D | NO | ID UNIT | DAYLY REPORT HM | [30 empty] | TOTAL HM | TOTAL FUEL 1- 31
N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WEEK 1 | : | 0 | DAYLY REPORT HM 22: Di setujui oleh :; DAYLY REPORT HM 29: Di buat oleh :
WEEK 2 | : | 0
WEEK 3 | : | 0
WEEK 4 | : | 0 | bar: DAYLY REPORT HM 5
WEEK 5 | : | 0 | DAYLY REPORT HM 22: Internal Kontrol; DAYLY REPORT HM 29: MPE Team
0
BENAR

## FUEL UNIT (hidden)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| D | NO | ID UNIT | DAYLY REPORT FUEL | [30 empty] | TOTAL FUEL | TOTAL HM 1- 31
| N |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
SM-BW 211-02 | TAP PC 400-03 | 1 | TAP PC 400-03 | [31 empty] | 0 | 0
SM-BW 211-03 | TAP PC 400-06 | 2 | TAP PC 400-06 | [31 empty] | 0 | 0
| TAP PC 300-11 | 3 | TAP PC 300-11 | [31 empty] | 0 | 0
SM-D85ESS-08 | TAP PC 300-12 | 4 | TAP PC 300-12 | [31 empty] | 0 | 0
| TAP PC 300-14 | 5 | TAP PC 300-14 | [31 empty] | 0 | 0
| TAP PC 200-11 | 6 | TAP PC 200-11 | [31 empty] | 0 | 0
| TAP PC 200-12 | 7 | TAP PC 200-12 | [31 empty] | 0 | 0
| TAP PC 200-14 | 8 | TAP PC 200-14 | [31 empty] | 0 | 0
| TAP PC 200-15 | 9 | TAP PC 200-15 | [31 empty] | 0 | 0
| TAP PC 200-16 | 10 | TAP PC 200-16 | [31 empty] | 0 | 0
| ADT HM 400-01 | 11 | ADT HM 400-01 | [31 empty] | 0 | 0
| ADT HM 400-02 | 12 | ADT HM 400-02 | [31 empty] | 0 | 0
| ADT HM 400-03 | 13 | ADT HM 400-03 | [31 empty] | 0 | 0
| ADT HM 400-05 | 14 | ADT HM 400-05 | [31 empty] | 0 | 0
| ADT HM 400-06 | 15 | ADT HM 400-06 | [31 empty] | 0 | 0
| ADT HM 400-07 | 16 | ADT HM 400-07 | [31 empty] | 0 | 0
| ADT HM 400-08 | 17 | ADT HM 400-08 | [31 empty] | 0 | 0
| DOZER D65P-04 | 18 | DOZER D65P-04 | [31 empty] | 0 | 0
| DOZER D65P-05 | 19 | DOZER D65P-05 | [31 empty] | 0 | 0
| DOZER D65P-11 | 20 | DOZER D65P-11 | [31 empty] | 0 | 0
| DOZER D85SS-02 | 21 | DOZER D85SS-02 | [31 empty] | 0 | 0
| DOZER D85SS-11 | 22 | DOZER D85SS-11 | [31 empty] | 0 | 0
| TAP GRADER-11 | 23 | TAP GRADER-11 | [31 empty] | 0 | 0
| TAP SAKAI-03 | 24 | TAP SAKAI-03 | [31 empty] | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DAYLY REPORT FUEL 30: TOTAL FUEL | 0
| WEEK 1 | : | 0 | DAYLY REPORT FUEL 22: Di setujui oleh :; DAYLY REPORT FUEL 29: Di buat oleh :
| WEEK 2 | : | 0
| WEEK 3 | : | 0
| WEEK 4 | : | 0
| WEEK 5 | : | 0 | DAYLY REPORT FUEL 22: Internal Kontrol; DAYLY REPORT FUEL 29: MPE Team
0
BENAR

## list rate unit
RATE
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | unit | type
NO | UNIT | Ltr/Hr | Rent/Hr | Column1 | Column2 | Description | Column4 | Column5 | Column6 | Column7 |  | KOMATSU PC 500 - 01 | PC 500 LCE-10R
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  | KOMATSU PC 500 - 02 | PC 500 LCE-10R
|  |  | Unit Only (Internal) | Incl. Operator | Incl. Operator & Fuel | [6 empty] | KOMATSU PC 500 - 03 | PC 500 LCE-10R
1 | PC 195 LC-8 | 20 | 16.5432 | 19.5084 | 35.3704 | Excavator | 239875.7064 | 282871.4905 | 512871.4905 | 275000 | 200 | KOMATSU PC 500 - 04 | PC 500 LCE-10R
2 | PC 200-8 MO | 22 | 23.2254 | 26.1906 | 43.6389 | Excavator | 336767.7028 | 379763.4868 | 632763.4868 | 275000 | 200 | KOMATSU PC 400 - 01 | PC 400 LC SE-8
3 | PC 300 SE-8 | 30 | 41.2152 | 44.1804 | 69.5598 | Excavator | 597620.6927 | 640616.4768 | 1008616.4768 | 400000 | 300 | KOMATSU PC 400 - 03 | PC 400 LC SE-8
4 | PC 400 LC SE-8 | 38 | 58.29 | 61.6 | 87.81 | Excavator | 845205 | 893200 | 1273245 | 950000 | 400 | KOMATSU PC 400 - 04 | PC 400 LC SE-8
5 | PC 500 LCE-10R | 45 | 63.54 | 66.85 | 98.05 | Excavator | 921330 | 969325 | 1421725 | 1000000 |  | KOMATSU PC 400 - 05 | PC 400 LC SE-8
6 | SK 200-8 SX | 20 | 17.6502 | 20.6154 | 36.4775 | Excavator | 255927.8486 | 298923.6327 | 528923.6327 | 275000 | 200 | KOMATSU PC 400 - 06 | PC 400 LC SE-8
7 | SK 330-8 | 28 | 34.235 | 37.2002 | 59.4071 | Excavator | 496407.8395 | 539403.6235 | 861403.6235 | 400000 |  | KOMATSU PC 300 - 10 | PC 300 SE-8
8 | HM 400-3R | 30 | 98.2279 | 101.5379 | 127.7104 | Artic | 1424304.3668 | 1472300.1508 | 1851800.1508 | 1424304.3668 |  | KOMATSU PC 300 - 11 | PC 300 SE-8
9 | D 85 ESS-2 | 30 | 42.331 | 45.2962 | 69.0893 | Bulldozer | 613799.3709 | 656795.155 | 1001795.155 | 425000 |  | KOMATSU PC 300 - 12 | PC 300 SE-8
10 | D 65 P-12 | 33 | 42.7792 | 45.7445 | 71.9169 | Bulldozer | 620298.906 | 663294.6901 | 1042794.6901 | 425000 |  | KOMATSU PC 300 - 14 | PC 300 SE-8
11 | GD 511 A-1 | 15 | 32.851 | 35.8163 | 47.7128 | Grader | 476340.0889 | 519335.8729 | 691835.8729 | 350000 |  | KOMATSU PC 300 - 15 | PC 300 SE-8
12 | SV 525 D | 11 | 13.1981 | 16.1633 | 24.0943 | Compactor | 191372.0947 | 234367.8788 | 349367.8788 | 220000 |  | KOMATSU PC 300 - 16 | PC 300 SE-8
13 | BW 211 D-40 | 11 | 9.9397 | 12.9049 | 20.8359 | Compactor | 144125.031 | 187120.8151 | 302120.8151 | 220000 |  | KOMATSU PC 300 - 17 | PC 300 SE-8
14 | XG 6121 | 11 | 8.6243 | 11.5895 | 19.5206 | Compactor | 125052.5178 | 168048.3018 | 283048.3018 |  |  | KOBELCO SK 330 - 10 | SK 330-8
15 | XG 955-III | 20 | 12.8699 | 15.8352 | 31.6972 | Whell Loader | 186614.0656 | 229609.8497 | 459609.8497 |  |  | KOBELCO SK 330 - 11 | SK 330-8
16 | WA 380-3 | 20 | 34.0145 | 36.9797 | 52.8418 | Whell Loader | 493209.9817 | 536205.7657 | 766205.7657 |  |  | KOMATSU PC 200 - 11 | PC 200-8 MO
17 | FM 260 Ti | 15 | 17.3403 | 18.9483 | 30.0517 | Dump Truck | 251435.0252 | 274750.1408 | 435750.1408 | 210000 |  | KOMATSU PC 200 - 12 | PC 200-8 MO
18 | 700 Provia | 20 | 31.1718 | 32.9521 | 48.8142 | Dump Truck | 451990.7019 | 477805.8175 | 707805.8175 | 460000 |  | KOMATSU PC 200 - 14 | PC 200-8 MO
19 | 700 Provia/12 | 28 | 32.42 | 34.21 | 53.52 | Dump Truck | 470090 | 496045 | 776040 | 500000 |  | KOMATSU PC 200 - 15 | PC 200-8 MO
20 | LV | 10 |  |  |  |  | 8000000 |  |  | 8000000 |  | KOMATSU PC 200 - 16 | PC 200-8 MO
21 | GENSET | 4 |  |  |  |  | 3000000 |  |  | 3000000 |  | KOMATSU PC 200 - 22 | PC 200-8 MO
22 | LT | 10 |  |  |  |  | 12000000 |  |  | 12000000 |  | KOMATSU PC 200 - 23 | PC 200-8 MO
RATE MOBILISASI | [11 empty] | KOMATSU PC 200 - 24 | PC 200-8 MO
[9 empty] | source data ( owning & operating cost) |  |  | KOMATSU SK 200 - 19 | PC 200-8 MO
NO | UNIT | $ / KM | [9 empty] | KOMATSU PC 200 - 25 | PC 200-8 MO
1 | PC 400 | 24 | [9 empty] | KOMATSU PC 195 - 01 | PC 195 LC-8
2 | PC 300 | 16 | [9 empty] | KOBELCO SK 200 - 07 | SK 200-8 SX
3 | PC 200 | 8 | [9 empty] | KOBELCO SK 200 - 08 | SK 200-8 SX
4 | BULLDOZER | 16 | [9 empty] | KOBELCO SK 200 - 10 | SK 200-8 SX
5 | COMPACTOR | 8 | [9 empty] | KOBELCO SK 200 - 11 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 13 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 15 | SK 200-8 SX
| 14652.34 | [10 empty] | KOBELCO SK 200 - 16 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 18 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 19 | SK 200-8 SX
[12 empty] | KOBELCO SK 200 - 20 | SK 200-8 SX
[12 empty] | KOMATSU HM 400 - 01 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 02 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 04 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 05 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 06 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 07 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 08 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 09 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 10 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 11 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 12 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 13 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 14 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 15 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 16 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 17 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 18 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 19 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 20 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 21 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 22 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 23 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 24 | HM 400-3R
[12 empty] | KOMATSU HM 400 - 25 | HM 400-3R
[12 empty] | KOMATSU DOZER D65 - 05 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 10 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 11 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 12 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 13 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 15 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 16 | D 65 P-12
[12 empty] | KOMATSU DOZER D65 - 18 | D 65 P-12
[12 empty] | KOMATSU DOZER D85SS - 11 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 14 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 17 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 18 | D 85 ESS-2
[12 empty] | KOMATSU DOZER D85SS - 20 | D 85 ESS-2
[12 empty] | GRADER GD535 - 03 | GD 511 A-1
[12 empty] | LOADER WA380 - 02 | WA 380-3
[12 empty] | SAKAI - 01 | SV 525 D
[12 empty] | SAKAI - 02 | SV 525 D
[12 empty] | SAKAI - 03 | SV 525 D
[12 empty] | SAKAI - 07 | SV 525 D
[12 empty] | LV HILUX HITAM - 05 | LV
[12 empty] | LV PAJERO PUTIH - 06 | LV
[12 empty] | LV TRITON HITAM - 08 | LV
[12 empty] | LV PAJERO PUTIH - 09 | LV
[12 empty] | LV HILUX SILVER - 10 | LV
[12 empty] | LV TRITON HITAM - 10 | LV
[12 empty] | LV TRITON PUTIH - 11 | LV
[12 empty] | LV HILUX HITAM - 11 | LV
[12 empty] | LV TRITON PUTIH - 12 | LV
[12 empty] | LV PAJERO HITAM - 15 | LV
[12 empty] | LV HILUX SILVER - 17 | LV
[12 empty] | LV HILUX HITAM - 18 | LV
[12 empty] | LV HILUX SILVER - 19 | LV
[12 empty] | LV PAJERO SILVER - 21 | LV
[12 empty] | LV HILUX PUTIH - 23 | LV
[12 empty] | LV TRITON PUTIH - 27 | LV
[12 empty] | LV LC-HIJAU - 29 | LV
[12 empty] | LV TRITON PUTIH (SAFETY) - 30 | LV
[12 empty] | LV TRITON PUTIH - 31 | LV
[12 empty] | LV TRITON PUTIH - 32 | LV
[12 empty] | MANHAUL - 02 | FM 260 Ti
[12 empty] | BUS APP - 03 | LT
[12 empty] | FUEL TRUCK - 02 | FM 260 Ti
[12 empty] | FUEL TRUCK - 03 | FM 260 Ti
[12 empty] | FUEL TRUCK - 05 | FM 260 Ti
[12 empty] | FUEL TRUCK - 06 | FM 260 Ti
[12 empty] | TRUCK WELDER - LT-04 | LT
[12 empty] | TRUCK TYRE - LT-08 | LT
[12 empty] | TRUCK MAINTENANCE - LT-09 | LT
[12 empty] | TRUCK TYRE - LT-10 | LT
MEKANIK CAMP
[12 empty] | LV TRITON PUTIH - 28 | LV
[12 empty] | TRUCK TYRE (LT-06) | LT
[12 empty] | WELDER CAR (LT-07) | LT
[12 empty] | LV HILUX MERAH - 06 | LV